## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Office Finishing Works (2) | 1 |  |  | 2011-02-14 08:00 | 2011-06-03 17:00 | 80d |  |  | 85847.8889 |  |  | 85847.8889 | 109.375
1 | Verplaatsbare wanden (1) | 1.1 |  | FS3 | 2011-02-14 08:00 | 2011-02-14 17:00 | 1d |  | 0 | 3325.21 | 0 | 0 | 3325.21 | 0.375
2 | Verplaatsbare wanden (2) | 1.2 |  | FS3 | 2011-02-14 08:00 | 2011-02-14 17:00 | 1d |  | 0 | 3736.01 | 0 | 0 | 3736.01 | 0.375
4 | Systeemwanden | 1.3 |  | FS8 | 2011-02-14 08:00 | 2011-05-11 17:00 | 63d |  | 0 | 22944.5195 | 0 | 0 | 22944.5195 | 86.375
3 | Zuivere OA (1) | 1.4 | 1FS;2FS | FS5;FS9 | 2011-02-15 08:00 | 2011-02-15 17:00 | 1d |  | 0 | 179.02 | 0 | 0 | 179.02 | 0.375
5 | Akoestische dammen | 1.5 | 3FS | SS6 | 2011-03-22 08:00 | 2011-03-23 17:00 | 2d |  | 0 | 1092.75 | 0 | 0 | 1092.75 | 1.375
9 | Plafonds + AKD | 1.6 | 3FS | SS6 | 2011-03-22 08:00 | 2011-03-23 17:00 | 2d |  | 0 | 607.77 | 0 | 0 | 607.77 | 1.375
6 | Verplaatsbare wanden (3) | 1.7 | 5SS;9SS | FS7 | 2011-03-23 08:00 | 2011-03-28 17:00 | 4d |  | 0 | 23 | 0 | 0 | 23 | 5.375
7 | Verplaatsbare wanden (4) | 1.8 | 6FS | FS8 | 2011-04-18 08:00 | 2011-05-11 17:00 | 18d |  | 0 | 49527.6094 | 0 | 0 | 49527.6094 | 23.375
8 | Zuivere OA (2) | 1.9 | 4FS;7FS |  | 2011-05-12 08:00 | 2011-06-03 17:00 | 17d |  | 0 | 4412 | 0 | 0 | 4412 | 22.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Office Finishing Works (2) | 640h |  |  |  |  | 99 | 100 | 101
1 | Verplaatsbare wanden (1) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Verplaatsbare wanden (2) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Systeemwanden | 504h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Zuivere OA (1) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Akoestische dammen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Plafonds + AKD | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Verplaatsbare wanden (3) | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Verplaatsbare wanden (4) | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Zuivere OA (2) | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2011-03-31 18:00 |  | TP Name | periode 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (2) | 2011-02-14 08:00 | 2011-06-03 17:00 | 80d |  |  | 85847.8889 |  |  | 85847.8889 |  | 23d | [5 empty] | 6418.97 |  | 8.434% |  | 7240.24 | 31908.2795
1 | Verplaatsbare wanden (1) | 2011-02-14 08:00 | 2011-02-14 17:00 | 1d |  | 0 | 3325.21 | 0 | 0 | 3325.21 | 2011-03-01 08:00 | 1d | 3325.21 | 0 | 0 | -271.73 | 0 | 3053.4799 | 0 | 100% | Finished | 3325.21 | 3325.21 | 100 | 100 | 100 | 100 | 91.8282 | 100
2 | Verplaatsbare wanden (2) | 2011-02-14 08:00 | 2011-02-14 17:00 | 1d |  | 0 | 3736.01 | 0 | 0 | 3736.01 | 2011-03-01 08:00 | 1d | 3736.01 | 0 | 0 | -509.15 | 0 | 3226.86 | 0 | 100% | Finished | 3736.01 | 3736.01 | 100 | 100 | 100 | 100 | 86.3718 | 100
4 | Systeemwanden | 2011-02-14 08:00 | 2011-05-11 17:00 | 63d |  | 0 | 22944.5195 | 0 | 0 | 22944.5195 |  | 0 | 0 | 22944.5195 | 63d | 0 | 0 | 0 | 22944.5195 | 0% | Not Started | 0 | 22944.5195 | 100 |  | 0 | 100 |  | 0
3 | Zuivere OA (1) | 2011-02-15 08:00 | 2011-02-15 17:00 | 1d |  | 0 | 179.02 | 0 | 0 | 179.02 | 2011-03-01 08:00 | 1d | 179.02 | 0 | 0 | -40.39 | 0 | 138.63 | 0 | 100% | Finished | 179.02 | 179.02 | 100 | 100 | 100 | 100 | 77.4383 | 100
5 | Akoestische dammen | 2011-03-22 08:00 | 2011-03-23 17:00 | 2d |  | 0 | 1092.75 | 0 | 0 | 1092.75 |  | 0 | 0 | 1092.75 | 2d | 0 | 0 | 0 | 1092.75 | 0% | Not Started | 0 | 1092.75 | 100 |  | 0 | 100 |  | 0
9 | Plafonds + AKD | 2011-03-22 08:00 | 2011-03-23 17:00 | 2d |  | 0 | 607.77 | 0 | 0 | 607.77 |  | 0 | 0 | 607.77 | 2d | 0 | 0 | 0 | 607.77 | 0% | Not Started | 0 | 607.77 | 100 |  | 0 | 100 |  | 0
6 | Verplaatsbare wanden (3) | 2011-03-23 08:00 | 2011-03-28 17:00 | 4d |  | 0 | 23 | 0 | 0 | 23 |  | 0 | 0 | 23 | 4d | 0 | 0 | 0 | 23 | 0% | Not Started | 0 | 23 | 100 |  | 0 | 100 |  | 0
7 | Verplaatsbare wanden (4) | 2011-04-18 08:00 | 2011-05-11 17:00 | 18d |  | 0 | 49527.6094 | 0 | 0 | 49527.6094 |  | 0 | 0 | 49527.6094 | 18d | 0 | 0 | 0 | 49527.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Zuivere OA (2) | 2011-05-12 08:00 | 2011-06-03 17:00 | 17d |  | 0 | 4412 | 0 | 0 | 4412 |  | 0 | 0 | 4412 | 17d | 0 | 0 | 0 | 4412 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2011-06-30 18:00 |  | TP Name | periode 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (2) | 2011-02-14 08:00 | 2011-06-03 17:00 | 80d |  |  | 85847.8889 |  |  | 85847.8889 |  | 88d | [5 empty] | 75468.2987 |  | 100% |  | 85847.8889 | 85847.8889
1 | Verplaatsbare wanden (1) | 2011-02-14 08:00 | 2011-02-14 17:00 | 1d |  | 0 | 3325.21 | 0 | 0 | 3325.21 | 2011-03-01 08:00 | 1d | 3325.21 | 0 | 0 | -271.73 | 0 | 3053.4799 | 0 | 100% | Finished | 3325.21 | 3325.21 | 100 | 100 | 100 | 100 | 91.8282 | 100
2 | Verplaatsbare wanden (2) | 2011-02-14 08:00 | 2011-02-14 17:00 | 1d |  | 0 | 3736.01 | 0 | 0 | 3736.01 | 2011-03-01 08:00 | 1d | 3736.01 | 0 | 0 | -509.15 | 0 | 3226.86 | 0 | 100% | Finished | 3736.01 | 3736.01 | 100 | 100 | 100 | 100 | 86.3718 | 100
4 | Systeemwanden | 2011-02-14 08:00 | 2011-05-11 17:00 | 63d |  | 0 | 22944.5195 | 0 | 0 | 22944.5195 | 2011-06-01 08:00 | 22d | 22944.5195 | 0 | 0 | -1486.78 | 0 | 21457.7395 | 0 | 100% | Finished | 22944.5195 | 22944.5195 | 100 | 34.9206 | 100 | 100 | 93.5201 | 100
3 | Zuivere OA (1) | 2011-02-15 08:00 | 2011-02-15 17:00 | 1d |  | 0 | 179.02 | 0 | 0 | 179.02 | 2011-03-01 08:00 | 1d | 179.02 | 0 | 0 | -40.39 | 0 | 138.63 | 0 | 100% | Finished | 179.02 | 179.02 | 100 | 100 | 100 | 100 | 77.4383 | 100
5 | Akoestische dammen | 2011-03-22 08:00 | 2011-03-23 17:00 | 2d |  | 0 | 1092.75 | 0 | 0 | 1092.75 | 2011-06-01 08:00 | 2d | 1092.75 | 0 | 0 | -72.09 | 0 | 1020.66 | 0 | 100% | Finished | 1092.75 | 1092.75 | 100 | 100 | 100 | 100 | 93.4029 | 100
9 | Plafonds + AKD | 2011-03-22 08:00 | 2011-03-23 17:00 | 2d |  | 0 | 607.77 | 0 | 0 | 607.77 | 2011-06-01 08:00 | 2d | 607.77 | 0 | 0 | -40.09 | 0 | 567.68 | 0 | 100% | Finished | 607.77 | 607.77 | 100 | 100 | 100 | 100 | 93.4038 | 100
6 | Verplaatsbare wanden (3) | 2011-03-23 08:00 | 2011-03-28 17:00 | 4d |  | 0 | 23 | 0 | 0 | 23 | 2011-06-01 08:00 | 4d | 23 | 0 | 0 | -2.85 | 0 | 20.15 | 0 | 100% | Finished | 23 | 23 | 100 | 100 | 100 | 100 | 87.6087 | 100
7 | Verplaatsbare wanden (4) | 2011-04-18 08:00 | 2011-05-11 17:00 | 18d |  | 0 | 49527.6094 | 0 | 0 | 49527.6094 | 2011-06-01 08:00 | 18d | 49527.6094 | 0 | 0 | -6960.4702 | 0 | 42567.1392 | 0 | 100% | Finished | 49527.6094 | 49527.6094 | 100 | 100 | 100 | 100 | 85.9463 | 100
8 | Zuivere OA (2) | 2011-05-12 08:00 | 2011-06-03 17:00 | 17d |  | 0 | 4412 | 0 | 0 | 4412 | 2011-06-01 08:00 | 17d | 4412 | 0 | 0 | -996.04 | 0 | 3415.96 | 0 | 100% | Finished | 4412 | 4412 | 100 | 100 | 100 | 100 | 77.4243 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
periode 1 | 2011-02-14 08:00 | 2011-03-31 18:00 | 31908.2795 | 7240.24 | 6418.97 | 2011-02-14 08:00 | -24668.0396 | 22.69% | 821.27 | 112.8% | -34d | 0% | 100% | 2011-07-06 17:00 | 2012-06-20 14:00 | 2012-04-25 14:00 | 2011-07-12 10:00 | 2012-06-20 14:00 | 2012-05-01 11:00 | 2011-07-21 17:00 | 2011-07-21 17:00 | 2011-07-21 17:00 | 85026.6189 | 76110.0492 | 352848.7628 | 85026.6189 | 313552.7729 | 76110.0492 | 89361.4466 | 77727.7798 | 0 | 1.1279 | 0.22691 | 1 | -34 | 1.1279 | 1 | 0 | 1
periode 2 | 2011-03-31 18:00 | 2011-06-30 18:00 | 85847.8889 | 85847.8889 | 75468.2987 | 2011-06-03 17:00 | 0 | 100% | 10379.5902 | 113.8% | -19d | 80.81% | 100% | 2011-06-03 17:00 | 2011-06-03 17:00 | 2011-05-23 11:00 | 2011-06-30 17:00 | 2011-06-30 17:00 | 2011-06-30 17:00 | 2011-06-30 17:00 | 2011-06-30 17:00 | 2011-06-30 17:00 | 75468.2987 | 75468.2987 | 75468.2987 | 75468.2987 | 75468.2987 | 75468.2987 | 75468.2987 | 75468.2987 | 0.80808 | 1.1375 | 1 | 1 | -19 | 1.1375 | 1 | 0.80808 | 1