## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Claeys-Verhelst Premises | 1 |  |  | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.3057 |  |  | 3027133.1861 | 618.0833
46 | preparation | 1.1 |  |  | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9701 |  |  | 253804.5701 | 235.375
2 | building permit | 1.1.1 |  | FS3 | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 81.375
3 | hire contractor | 1.1.2 | 2FS | FS16 | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 25.375
4 | temporary offices | 1.1.3 |  |  | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 25.375
5 | temporary facilities | 1.1.4 |  |  | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 81.375
16 | preparation contractor | 1.1.5 | 3FS | FS6 | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 81.375
6 | demolition | 1.1.6 | 16FS | FS17;FS69 | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.00 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 39.375
47 | foundation | 1.2 |  |  | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.894 |  |  | 401436.374 | 52.375
17 | excavation | 1.2.1 | 6FS | FS18;FS21 | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 17.375
69 | soil analyses | 1.2.2 | 6FS | FS18 | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 1.375
18 | foundation beam | 1.2.3 | 17FS;69FS | FS19 | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 34.375
21 | placing sewerage | 1.2.4 | 17FS | FS23 | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.00 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 13.375
23 | foundation plate | 1.2.5 | 21FS | FS19 | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.00 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 0.375
48 | shell | 1.3 |  |  | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4531 |  |  | 542212.4531 | 83.375
19 | steelframe I | 1.3.1 | 18FS;23FS | FS20 | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.00 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 27.375
20 | concrete vaults I | 1.3.2 | 19FS | FS22 | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.00 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 13.375
22 | steelframe II | 1.3.3 | 20FS | FS24 | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.00 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 20.375
24 | concrete volt II | 1.3.4 | 22FS | FS25;FS49 | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.00 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 20.375
50 | wind and water proof | 1.4 |  |  | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1641 |  |  | 597047.364 | 41.375
25 | facades | 1.4.1 | 24FS | FS26 | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.00 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 27.375
26 | outside windows | 1.4.2 | 25FS | FS28;FS29 | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 13.375
49 | roof | 1.4.3 | 24FS |  | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.00 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 13.375
62 | warehouse | 1.5 |  |  | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9609 |  |  | 301814.5611 | 145.0833
28 | v0 polierbeton | 1.5.1 | 26FS | FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51 | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.00 #8] | 15424 | 134400 | 0 | 0 | 149824 | 13.375
30 | v0 sanitary | 1.5.2 | 31FS;28FS | FS35 | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 14
27 | v0 -masonry | 1.5.3 | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 14
59 | v0 heating | 1.5.4 | 31FS;28FS | FS35 | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 28
29 | v0 electricity | 1.5.5 | 26FS;31FS | FS35 | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 35
35 | v0 floors | 1.5.6 | 59FS;29FS;30FS | FS41;FS37 | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 28
66 | construction leave | 1.6 |  |  | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 | 14
31 | construction leave | 1.6.1 |  | FS53;FS55;FS56;FS61;FS54;FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51;FS29 | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 14
63 | level 1 | 1.7 |  |  | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9709 |  |  | 262542.5712 | 56
52 | vI sanitary | 1.7.1 | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 14
45 | vI masonry | 1.7.2 | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 14
34 | v1screed | 1.7.3 | 31FS;28FS | FS67 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.00 #3] | 0 | 106140 | 0 | 0 | 106140 | 21
60 | v1 heating | 1.7.4 | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 28
51 | vI electricity | 1.7.5 | 31FS;28FS |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 35
67 | v1 drying screed | 1.7.6 | 34FS | FS57;FS32 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 7
57 | v1flooring | 1.7.7 | 67FS | FS41;FS37;FS36 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 28
64 | level 2 | 1.8 |  |  | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9709 |  |  | 149562.5709 | 56
53 | v2 sanitary | 1.8.1 | 31FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 14
55 | v2 masonry | 1.8.2 | 31FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 14
56 | v2 screed | 1.8.3 | 31FS | FS68;FS36 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 21
61 | v2 heating | 1.8.4 | 31FS |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 28
54 | v2 electricity | 1.8.5 | 31FS |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 35
68 | v2 drying screed | 1.8.6 | 56FS | FS58;FS32 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 7
58 | v2 flooring | 1.8.7 | 68FS | FS41;FS37;FS36 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 28
65 | completion | 1.9 |  |  | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9116 |  |  | 518712.7116 | 91
32 | stucco | 1.9.1 | 68FS;67FS | FS41;FS37 | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.00 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 21
36 | drywall | 1.9.2 | 58FS;57FS;56FS |  | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 35
41 | kitchen and bar | 1.9.3 | 32FS;58FS;57FS;35FS |  | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 21
37 | techniques | 1.9.4 | 32FS;58FS;57FS;35FS | FS38;FS42;FS43;FS44 | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 21
44 | stairs | 1.9.5 | 37FS |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 14
42 | entrance doors | 1.9.6 | 37FS |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 14
43 | elevator | 1.9.7 | 37FS |  | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 7
38 | suspended ceiling | 1.9.8 | 37FS | FS39 | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 7
39 | painting | 1.9.9 | 38FS | FS40 | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.00 #6] | 16800 | 83000 | 0 | 0 | 99800 | 21
40 | furniture | 1.9.10 | 39FS |  | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.00 #5] | 8400 | 130000 | 0 | 0 | 138400 | 7

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | plumber | Renewable | 4 #4 | 0 | 36 | 30;52;53; | 8640
2 | electrician | Renewable | 4 #4 | 0 | 32 | 29;51;61;54; | 24320
3 | team VDW | Renewable | 8 #8 | 0 | 38.56 | 6[4.00 team VDW];17;69;18[3.00 team VDW];21[3.00 team VDW];23[5.00 team VDW];19[4.00 team VDW];20[4.00 team VDW];22[3.00 team VDW];24[4.00 team VDW];25[2.00 team VDW];28[5.00 team VDW]; | 173057.2812
4 | mason | Renewable | 4 #4 | 0 | 40.65 | 27;45;55; | 9756
5 | heating | Renewable | 2 #2 | 0 | 43.2 | 59;60; | 13824
6 | roofing | Renewable | 4 #4 | 0 | 36 | 49[4.00 roofing]; | 11520
7 | windows | Renewable | 3 #3 | 0 | 38 | 26[3.00 windows]; | 9120
8 | flooring | Renewable | 4 #4 | 0 | 41.56 | 35;57;58; | 19948.8008
9 | chapen | Renewable | 3 #3 | 0 | 0 | 34[2.00 chapen];56; | 0
10 | stucco | Renewable | 4 #4 | 0 | 41.38 | 32[3.00 stucco]; | 14896.8008
11 | painter | Renewable | 6 #6 | 0 | 35 | 39[4.00 painter]; | 16800
12 | furniture | Renewable | 5 #5 | 0 | 42 | 40[5.00 furniture]; | 8400

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Claeys-Verhelst Premises | 3538h |  |  |  |  | 99 | 100 | 101
46 | preparation | 1360h |  |  |  |  | 99 | 100 | 101
2 | building permit | 480h | manual - absolute | 402 | 480 | 812 | 83 | 100 | 169
3 | hire contractor | 160h | manual - absolute | 127 | 160 | 326 | 79 | 100 | 203
4 | temporary offices | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | temporary facilities | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | preparation contractor | 480h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
6 | demolition | 240h | manual - absolute | 219 | 240 | 302 | 91 | 100 | 125
47 | foundation | 312h |  |  |  |  | 99 | 100 | 101
17 | excavation | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | soil analyses | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | foundation beam | 200h | manual - absolute | 159 | 200 | 363 | 79 | 100 | 181
21 | placing sewerage | 80h | manual - absolute | 63 | 80 | 98 | 78 | 100 | 122
23 | foundation plate | 8h | manual - absolute | 6 | 8 | 10 | 75 | 100 | 125
48 | shell | 480h |  |  |  |  | 99 | 100 | 101
19 | steelframe I | 160h | manual - absolute | 104 | 120 | 166 | 65 | 75 | 103
20 | concrete vaults I | 80h | manual - absolute | 32 | 40 | 48 | 40 | 50 | 60
22 | steelframe II | 120h | manual - absolute | 64 | 80 | 113 | 53 | 66 | 94
24 | concrete volt II | 120h | manual - absolute | 66 | 80 | 121 | 55 | 66 | 100
50 | wind and water proof | 240h |  |  |  |  | 99 | 100 | 101
25 | facades | 160h | manual - absolute | 128 | 160 | 463 | 80 | 100 | 289
26 | outside windows | 80h | manual - absolute | 64 | 80 | 175 | 80 | 100 | 218
49 | roof | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | warehouse | 826h |  |  |  |  | 99 | 100 | 101
28 | v0 polierbeton | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | v0 sanitary | 80h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
27 | v0 -masonry | 80h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
59 | v0 heating | 160h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
29 | v0 electricity | 200h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
35 | v0 floors | 160h | manual - absolute | 128 | 163 | 543 | 80 | 101 | 339
66 | construction leave | 80h |  |  |  |  | 99 | 100 | 101
31 | construction leave | 80h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
63 | level 1 | 320h |  |  |  |  | 99 | 100 | 101
52 | vI sanitary | 80h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
45 | vI masonry | 80h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
34 | v1screed | 120h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
60 | v1 heating | 160h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
51 | vI electricity | 200h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
67 | v1 drying screed | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
57 | v1flooring | 160h | manual - absolute | 128 | 160 | 577 | 80 | 100 | 360
64 | level 2 | 320h |  |  |  |  | 99 | 100 | 101
53 | v2 sanitary | 80h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
55 | v2 masonry | 80h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
56 | v2 screed | 120h | manual - relative | 80 | 110 | 120 | 80 | 110 | 120
61 | v2 heating | 160h | manual - relative | 80 | 110 | 120 | 80 | 110 | 120
54 | v2 electricity | 200h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
68 | v2 drying screed | 40h | manual - relative | 80 | 110 | 120 | 80 | 110 | 120
58 | v2 flooring | 160h | manual - absolute | 128 | 160 | 556 | 80 | 100 | 347
65 | completion | 520h |  |  |  |  | 99 | 100 | 101
32 | stucco | 120h | manual - absolute | 96 | 120 | 451 | 80 | 100 | 375
36 | drywall | 200h | manual - absolute | 160 | 200 | 528 | 80 | 100 | 264
41 | kitchen and bar | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | techniques | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | stairs | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | entrance doors | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | elevator | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | suspended ceiling | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | painting | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | furniture | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2006-07-07 08:00 |  | TP Name | Preparation1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Claeys-Verhelst Premises | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.3057 |  |  | 3027133.1861 |  | 59d | [5 empty] | 5716.8501 |  | 0.1889% |  | 5716.8501 | 5716.8501
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9701 |  |  | 253804.5701 |  | 59d | [5 empty] | 5716.8501 |  | 2.252% |  | 5716.8501 | 5716.8501
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 1d | 0 | 0 | 75 | 0 | 99.01% | Started | 75 | 75 | 100 | 166.6667 | 99.0099 | 100 | 100 | 99.0099
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 |  | 0 | 0 | 210000 | 20d | 0 | 0 | 0 | 210000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 100 | 100 | 100 | 100 | 100 | 100
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 1d | 0 | 0 | 1876.54 | 0 | 98.36% | Started | 1876.54 | 1876.54 | 100 | 100 | 98.3607 | 100 | 100 | 98.3607
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 60d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.00 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 |  | 0 | 0 | 38087.71 | 30d | 0 | 0 | 0 | 38087.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.894 |  |  | 401436.374 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 |  | 0 | 0 | 30318.72 | 14d | 0 | 0 | 0 | 30318.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 |  | 0 | 0 | 2616.96 | 2d | 0 | 0 | 0 | 2616.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 |  | 0 | 0 | 121659.7266 | 25d | 0 | 0 | 0 | 121659.7266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.00 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 |  | 0 | 0 | 10479.13 | 10d | 0 | 0 | 0 | 10479.13 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.00 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 |  | 0 | 0 | 236361.8375 | 1d | 0 | 0 | 0 | 236361.8375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4531 |  |  | 542212.4531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.00 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 |  | 0 | 0 | 143670.9078 | 20d | 0 | 0 | 0 | 143670.9078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.00 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 |  | 0 | 0 | 129748.9187 | 10d | 0 | 0 | 0 | 129748.9187 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.00 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 |  | 0 | 0 | 132874.1078 | 15d | 0 | 0 | 0 | 132874.1078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.00 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 |  | 0 | 0 | 135918.5187 | 15d | 0 | 0 | 0 | 135918.5187 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1641 |  |  | 597047.364 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.00 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 |  | 0 | 0 | 351653.2 | 20d | 0 | 0 | 0 | 351653.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 |  | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.00 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 |  | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9609 |  |  | 301814.5611 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.00 #8] | 15424 | 134400 | 0 | 0 | 149824 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 |  | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 |  | 0 | 0 | 81649.6 | 20d | 0 | 0 | 0 | 81649.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9709 |  |  | 262542.5712 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 |  | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.00 #3] | 0 | 106140 | 0 | 0 | 106140 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 |  | 0 | 0 | 25475.0001 | 20d | 0 | 0 | 0 | 25475.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 |  | 0 | 0 | 79149.6 | 20d | 0 | 0 | 0 | 79149.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9709 |  |  | 149562.5709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 |  | 0 | 0 | 38149.6 | 20d | 0 | 0 | 0 | 38149.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9116 |  |  | 518712.7116 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.00 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 |  | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2007-02-08 08:00 |  | TP Name | Preparation2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Claeys-Verhelst Premises | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.3057 |  |  | 3027133.1861 |  | 214d | [5 empty] | 283418.6501 |  | 8.384% |  | 253804.5701 | 779169.1319
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9701 |  |  | 253804.5701 |  | 214d | [5 empty] | 283418.6501 |  | 100% |  | 253804.5701 | 253804.5701
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 166.6667 | 100 | 100 | 100 | 100
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 100 | 150 | 100 | 100 | 100 | 100
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 100 | 100 | 100 | 100 | 100 | 100
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 100 | 100 | 100 | 100 | 100 | 100
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.00 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 67701.79 | 0 | 0 | 0 | 0 | 67701.79 | 0 | 100% | Finished | 38087.71 | 38087.71 | 100 | 180 | 100 | 100 | 177.7523 | 100
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.894 |  |  | 401436.374 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 401436.374
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 |  | 0 | 0 | 30318.72 | 14d | 0 | 0 | 0 | 30318.72 | 0% | Not Started | 0 | 30318.72 | 100 |  | 0 | 100 |  | 0
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 |  | 0 | 0 | 2616.96 | 2d | 0 | 0 | 0 | 2616.96 | 0% | Not Started | 0 | 2616.96 | 100 |  | 0 | 100 |  | 0
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 |  | 0 | 0 | 121659.7266 | 25d | 0 | 0 | 0 | 121659.7266 | 0% | Not Started | 0 | 121659.7266 | 100 |  | 0 | 100 |  | 0
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.00 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 |  | 0 | 0 | 10479.13 | 10d | 0 | 0 | 0 | 10479.13 | 0% | Not Started | 0 | 10479.13 | 100 |  | 0 | 100 |  | 0
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.00 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 |  | 0 | 0 | 236361.8375 | 1d | 0 | 0 | 0 | 236361.8375 | 0% | Not Started | 0 | 236361.8375 | 100 |  | 0 | 100 |  | 0
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4531 |  |  | 542212.4531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 123928.1878
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.00 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 |  | 0 | 0 | 143670.9078 | 20d | 0 | 0 | 0 | 143670.9078 | 0% | Not Started | 0 | 123928.1878 | 100 |  | 0 | 100 |  | 0
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.00 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 |  | 0 | 0 | 129748.9187 | 10d | 0 | 0 | 0 | 129748.9187 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.00 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 |  | 0 | 0 | 132874.1078 | 15d | 0 | 0 | 0 | 132874.1078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.00 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 |  | 0 | 0 | 135918.5187 | 15d | 0 | 0 | 0 | 135918.5187 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1641 |  |  | 597047.364 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.00 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 |  | 0 | 0 | 351653.2 | 20d | 0 | 0 | 0 | 351653.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 |  | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.00 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 |  | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9609 |  |  | 301814.5611 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.00 #8] | 15424 | 134400 | 0 | 0 | 149824 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 |  | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 |  | 0 | 0 | 81649.6 | 20d | 0 | 0 | 0 | 81649.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9709 |  |  | 262542.5712 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 |  | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.00 #3] | 0 | 106140 | 0 | 0 | 106140 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 |  | 0 | 0 | 25475.0001 | 20d | 0 | 0 | 0 | 25475.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 |  | 0 | 0 | 79149.6 | 20d | 0 | 0 | 0 | 79149.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9709 |  |  | 149562.5709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 |  | 0 | 0 | 38149.6 | 20d | 0 | 0 | 0 | 38149.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9116 |  |  | 518712.7116 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.00 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 |  | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2007-03-17 08:00 |  | TP Name | Foundation
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Claeys-Verhelst Premises | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.3057 |  |  | 3027133.1861 |  | 240d | [5 empty] | 685780.4641 |  | 21.38% |  | 647075.3017 | 1048578.7185
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9701 |  |  | 253804.5701 |  | 214d | [5 empty] | 283418.6501 |  | 100% |  | 253804.5701 | 253804.5701
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 166.6667 | 100 | 100 | 100 | 100
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 100 | 150 | 100 | 100 | 100 | 100
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 100 | 100 | 100 | 100 | 100 | 100
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 100 | 100 | 100 | 100 | 100 | 100
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.00 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 67701.79 | 0 | 0 | 0 | 0 | 67701.79 | 0 | 100% | Finished | 38087.71 | 38087.71 | 100 | 180 | 100 | 100 | 177.7523 | 100
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.894 |  |  | 401436.374 |  | 27d | [5 empty] | 402361.814 |  | 97.97% |  | 393270.7316 | 401436.374
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 29084.8 | 0 | 0 | 0 | 0 | 29084.8 | 0 | 100% | Finished | 30318.72 | 30318.72 | 100 | 71.4286 | 100 | 100 | 95.9302 | 100
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.76 | 0 | 0 | 0 | 0 | 5701.76 | 0 | 100% | Finished | 2616.96 | 2616.96 | 100 | 600 | 100 | 100 | 217.8772 | 100
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4066 | 11105.28 | 12d | 0 | 0 | 118883.4066 | 11105.28 | 64.71% | Started | 113494.0841 | 121659.7266 | 100 | 88 | 64.7059 | 100 | 97.718 | 64.7059
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.00 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 12330.01 | 0 | 0 | 0 | 0 | 12330.01 | 0 | 100% | Finished | 10479.13 | 10479.13 | 100 | 120 | 100 | 100 | 117.6625 | 100
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.00 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100% | Finished | 236361.8375 | 236361.8375 | 100 | 100 | 100 | 100 | 100 | 100
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4531 |  |  | 542212.4531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 393337.7744
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.00 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 |  | 0 | 0 | 143670.9078 | 20d | 0 | 0 | 0 | 143670.9078 | 0% | Not Started | 0 | 143670.9078 | 100 |  | 0 | 100 |  | 0
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.00 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 |  | 0 | 0 | 129748.9187 | 10d | 0 | 0 | 0 | 129748.9187 | 0% | Not Started | 0 | 129748.9187 | 100 |  | 0 | 100 |  | 0
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.00 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 |  | 0 | 0 | 132874.1078 | 15d | 0 | 0 | 0 | 132874.1078 | 0% | Not Started | 0 | 119917.9478 | 100 |  | 0 | 100 |  | 0
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.00 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 |  | 0 | 0 | 135918.5187 | 15d | 0 | 0 | 0 | 135918.5187 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1641 |  |  | 597047.364 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.00 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 |  | 0 | 0 | 351653.2 | 20d | 0 | 0 | 0 | 351653.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 |  | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.00 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 |  | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9609 |  |  | 301814.5611 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.00 #8] | 15424 | 134400 | 0 | 0 | 149824 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 |  | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 |  | 0 | 0 | 81649.6 | 20d | 0 | 0 | 0 | 81649.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9709 |  |  | 262542.5712 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 |  | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.00 #3] | 0 | 106140 | 0 | 0 | 106140 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 |  | 0 | 0 | 25475.0001 | 20d | 0 | 0 | 0 | 25475.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 |  | 0 | 0 | 79149.6 | 20d | 0 | 0 | 0 | 79149.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9709 |  |  | 149562.5709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 |  | 0 | 0 | 38149.6 | 20d | 0 | 0 | 0 | 38149.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9116 |  |  | 518712.7116 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.00 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 |  | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2007-06-04 08:00 |  | TP Name | Shell
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Claeys-Verhelst Premises | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.3057 |  |  | 3027133.1861 |  | 295d | [5 empty] | 1209484.1173 |  | 39.09% |  | 1183389.3748 | 1790852.7613
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9701 |  |  | 253804.5701 |  | 214d | [5 empty] | 283418.6501 |  | 100% |  | 253804.5701 | 253804.5701
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 166.6667 | 100 | 100 | 100 | 100
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 100 | 150 | 100 | 100 | 100 | 100
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 100 | 100 | 100 | 100 | 100 | 100
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 100 | 100 | 100 | 100 | 100 | 100
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.00 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 67701.79 | 0 | 0 | 0 | 0 | 67701.79 | 0 | 100% | Finished | 38087.71 | 38087.71 | 100 | 180 | 100 | 100 | 177.7523 | 100
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.894 |  |  | 401436.374 |  | 36d | [5 empty] | 402361.814 |  | 100% |  | 401436.374 | 401436.374
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 29084.8 | 0 | 0 | 0 | 0 | 29084.8 | 0 | 100% | Finished | 30318.72 | 30318.72 | 100 | 71.4286 | 100 | 100 | 95.9302 | 100
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.76 | 0 | 0 | 0 | 0 | 5701.76 | 0 | 100% | Finished | 2616.96 | 2616.96 | 100 | 600 | 100 | 100 | 217.8772 | 100
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4066 | 0 | 0 | 0 | 0 | 118883.4066 | 0 | 100% | Finished | 121659.7266 | 121659.7266 | 100 | 88 | 100 | 100 | 97.718 | 100
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.00 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 12330.01 | 0 | 0 | 0 | 0 | 12330.01 | 0 | 100% | Finished | 10479.13 | 10479.13 | 100 | 120 | 100 | 100 | 117.6625 | 100
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.00 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100% | Finished | 236361.8375 | 236361.8375 | 100 | 100 | 100 | 100 | 100 | 100
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4531 |  |  | 542212.4531 |  | 45d | [5 empty] | 523703.6531 |  | 97.41% |  | 528148.4307 | 542212.4531
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.00 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 137501.3078 | 24524.16 | 19d 7h | 0 | 0 | 137501.3078 | 24524.16 | 43.01% | Started | 129606.8853 | 143670.9078 | 100 | 75 | 43.0108 | 100 | 95.7057 | 43.0108
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.00 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 123579.3188 | 0 | 0 | 0 | 0 | 123579.3188 | 0 | 100% | Finished | 129748.9187 | 129748.9187 | 100 | 50 | 100 | 100 | 95.245 | 100
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.00 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 132874.1078 | 0 | 0 | 0 | 0 | 132874.1078 | 0 | 100% | Finished | 132874.1078 | 132874.1078 | 100 | 100 | 100 | 100 | 100 | 100
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.00 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 129748.9187 | 0 | 0 | 0 | 0 | 129748.9187 | 0 | 100% | Finished | 135918.5187 | 135918.5187 | 100 | 66.6667 | 100 | 100 | 95.4608 | 100
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1641 |  |  | 597047.364 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 593399.364
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.00 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 |  | 0 | 0 | 351653.2 | 20d | 0 | 0 | 0 | 351653.2 | 0% | Not Started | 0 | 351653.2 | 100 |  | 0 | 100 |  | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 |  | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0% | Not Started | 0 | 156222.5938 | 100 |  | 0 | 100 |  | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.00 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 |  | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0% | Not Started | 0 | 85523.5703 | 100 |  | 0 | 100 |  | 0
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9609 |  |  | 301814.5611 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.00 #8] | 15424 | 134400 | 0 | 0 | 149824 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 |  | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 |  | 0 | 0 | 81649.6 | 20d | 0 | 0 | 0 | 81649.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9709 |  |  | 262542.5712 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 |  | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.00 #3] | 0 | 106140 | 0 | 0 | 106140 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 |  | 0 | 0 | 25475.0001 | 20d | 0 | 0 | 0 | 25475.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 |  | 0 | 0 | 79149.6 | 20d | 0 | 0 | 0 | 79149.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9709 |  |  | 149562.5709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 |  | 0 | 0 | 38149.6 | 20d | 0 | 0 | 0 | 38149.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9116 |  |  | 518712.7116 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.00 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 |  | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2007-07-02 08:00 |  | TP Name | Wind&Waterproof
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Claeys-Verhelst Premises | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.3057 |  |  | 3027133.1861 |  | 315d | [5 empty] | 1881315.4813 |  | 59.13% |  | 1790091.2511 | 1944324.7613
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9701 |  |  | 253804.5701 |  | 214d | [5 empty] | 283418.6501 |  | 100% |  | 253804.5701 | 253804.5701
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 166.6667 | 100 | 100 | 100 | 100
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 100 | 150 | 100 | 100 | 100 | 100
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 100 | 100 | 100 | 100 | 100 | 100
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 100 | 100 | 100 | 100 | 100 | 100
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.00 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 67701.79 | 0 | 0 | 0 | 0 | 67701.79 | 0 | 100% | Finished | 38087.71 | 38087.71 | 100 | 180 | 100 | 100 | 177.7523 | 100
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.894 |  |  | 401436.374 |  | 36d | [5 empty] | 402361.814 |  | 100% |  | 401436.374 | 401436.374
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 29084.8 | 0 | 0 | 0 | 0 | 29084.8 | 0 | 100% | Finished | 30318.72 | 30318.72 | 100 | 71.4286 | 100 | 100 | 95.9302 | 100
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.76 | 0 | 0 | 0 | 0 | 5701.76 | 0 | 100% | Finished | 2616.96 | 2616.96 | 100 | 600 | 100 | 100 | 217.8772 | 100
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4066 | 0 | 0 | 0 | 0 | 118883.4066 | 0 | 100% | Finished | 121659.7266 | 121659.7266 | 100 | 88 | 100 | 100 | 97.718 | 100
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.00 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 12330.01 | 0 | 0 | 0 | 0 | 12330.01 | 0 | 100% | Finished | 10479.13 | 10479.13 | 100 | 120 | 100 | 100 | 117.6625 | 100
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.00 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100% | Finished | 236361.8375 | 236361.8375 | 100 | 100 | 100 | 100 | 100 | 100
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4531 |  |  | 542212.4531 |  | 45d | [5 empty] | 523703.6531 |  | 100% |  | 542212.4531 | 542212.4531
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.00 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 137501.3078 | 0 | 0 | 0 | 0 | 137501.3078 | 0 | 100% | Finished | 143670.9078 | 143670.9078 | 100 | 75 | 100 | 100 | 95.7057 | 100
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.00 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 123579.3188 | 0 | 0 | 0 | 0 | 123579.3188 | 0 | 100% | Finished | 129748.9187 | 129748.9187 | 100 | 50 | 100 | 100 | 95.245 | 100
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.00 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 132874.1078 | 0 | 0 | 0 | 0 | 132874.1078 | 0 | 100% | Finished | 132874.1078 | 132874.1078 | 100 | 100 | 100 | 100 | 100 | 100
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.00 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 129748.9187 | 0 | 0 | 0 | 0 | 129748.9187 | 0 | 100% | Finished | 135918.5187 | 135918.5187 | 100 | 66.6667 | 100 | 100 | 95.4608 | 100
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1641 |  |  | 597047.364 |  | 20d | [5 empty] | 671831.364 |  | 99.26% |  | 592637.8538 | 597047.364
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.00 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 351653.2 | 4935.68 | 8d | 0 | 0 | 351653.2 | 4935.68 | 71.43% | Started | 348127.7145 | 351653.2 | 100 | 100 | 71.4286 | 100 | 100 | 71.4286
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 234654.5938 | 9006 | 9d 7h | 0 | 0 | 234654.5938 | 9006 | 90.31% | Started | 158986.5691 | 159870.5938 | 100 | 920 | 90.3067 | 100 | 146.7778 | 90.3067
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.00 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100% | Finished | 85523.5703 | 85523.5703 | 100 | 100 | 100 | 100 | 100 | 100
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9609 |  |  | 301814.5611 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 149824
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.00 #8] | 15424 | 134400 | 0 | 0 | 149824 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0% | Not Started | 0 | 149824 | 100 |  | 0 | 100 |  | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 |  | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 |  | 0 | 0 | 81649.6 | 20d | 0 | 0 | 0 | 81649.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9709 |  |  | 262542.5712 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 |  | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.00 #3] | 0 | 106140 | 0 | 0 | 106140 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 |  | 0 | 0 | 25475.0001 | 20d | 0 | 0 | 0 | 25475.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 |  | 0 | 0 | 79149.6 | 20d | 0 | 0 | 0 | 79149.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9709 |  |  | 149562.5709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 |  | 0 | 0 | 38149.6 | 20d | 0 | 0 | 0 | 38149.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9116 |  |  | 518712.7116 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.00 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 |  | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2007-10-24 08:00 |  | TP Name | WH, L1, L2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Claeys-Verhelst Premises | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.3057 |  |  | 3027133.1861 |  | 397d | [5 empty] | 2583683.1944 |  | 82.79% |  | 2506206.5298 | 2530047.5144
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9701 |  |  | 253804.5701 |  | 214d | [5 empty] | 283418.6501 |  | 100% |  | 253804.5701 | 253804.5701
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 166.6667 | 100 | 100 | 100 | 100
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 100 | 150 | 100 | 100 | 100 | 100
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 100 | 100 | 100 | 100 | 100 | 100
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 100 | 100 | 100 | 100 | 100 | 100
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.00 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 67701.79 | 0 | 0 | 0 | 0 | 67701.79 | 0 | 100% | Finished | 38087.71 | 38087.71 | 100 | 180 | 100 | 100 | 177.7523 | 100
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.894 |  |  | 401436.374 |  | 36d | [5 empty] | 402361.814 |  | 100% |  | 401436.374 | 401436.374
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 29084.8 | 0 | 0 | 0 | 0 | 29084.8 | 0 | 100% | Finished | 30318.72 | 30318.72 | 100 | 71.4286 | 100 | 100 | 95.9302 | 100
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.76 | 0 | 0 | 0 | 0 | 5701.76 | 0 | 100% | Finished | 2616.96 | 2616.96 | 100 | 600 | 100 | 100 | 217.8772 | 100
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4066 | 0 | 0 | 0 | 0 | 118883.4066 | 0 | 100% | Finished | 121659.7266 | 121659.7266 | 100 | 88 | 100 | 100 | 97.718 | 100
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.00 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 12330.01 | 0 | 0 | 0 | 0 | 12330.01 | 0 | 100% | Finished | 10479.13 | 10479.13 | 100 | 120 | 100 | 100 | 117.6625 | 100
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.00 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100% | Finished | 236361.8375 | 236361.8375 | 100 | 100 | 100 | 100 | 100 | 100
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4531 |  |  | 542212.4531 |  | 45d | [5 empty] | 523703.6531 |  | 100% |  | 542212.4531 | 542212.4531
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.00 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 137501.3078 | 0 | 0 | 0 | 0 | 137501.3078 | 0 | 100% | Finished | 143670.9078 | 143670.9078 | 100 | 75 | 100 | 100 | 95.7057 | 100
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.00 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 123579.3188 | 0 | 0 | 0 | 0 | 123579.3188 | 0 | 100% | Finished | 129748.9187 | 129748.9187 | 100 | 50 | 100 | 100 | 95.245 | 100
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.00 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 132874.1078 | 0 | 0 | 0 | 0 | 132874.1078 | 0 | 100% | Finished | 132874.1078 | 132874.1078 | 100 | 100 | 100 | 100 | 100 | 100
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.00 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 129748.9187 | 0 | 0 | 0 | 0 | 129748.9187 | 0 | 100% | Finished | 135918.5187 | 135918.5187 | 100 | 66.6667 | 100 | 100 | 95.4608 | 100
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1641 |  |  | 597047.364 |  | 102d | [5 empty] | 671831.364 |  | 99.85% |  | 596163.3393 | 597047.364
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.00 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 351653.2 | 0 | 0 | 0 | 0 | 351653.2 | 0 | 100% | Finished | 351653.2 | 351653.2 | 100 | 100 | 100 | 100 | 100 | 100
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 234654.5938 | 9006 | 9d 7h | 0 | 0 | 234654.5938 | 9006 | 90.31% | Started | 158986.5691 | 159870.5938 | 100 | 920 | 90.3067 | 100 | 146.7778 | 90.3067
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.00 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100% | Finished | 85523.5703 | 85523.5703 | 100 | 100 | 100 | 100 | 100 | 100
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9609 |  |  | 301814.5611 |  | 65d | [5 empty] | 291542.5611 |  | 100% |  | 301814.5611 | 300069.0411
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.00 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 142112 | 0 | 0 | 0 | 0 | 142112 | 0 | 100% | Finished | 149824 | 149824 | 100 | 50 | 100 | 100 | 94.8526 | 100
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 100 | 100 | 100 | 100 | 100 | 100
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100% | Finished | 37704.9611 | 37704.9611 | 100 | 100 | 100 | 100 | 100 | 100
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 18563 | 0 | 0 | 0 | 0 | 18563 | 0 | 100% | Finished | 18563 | 18563 | 100 | 100 | 100 | 100 | 100 | 100
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 6400 | 6400 | 100 | 60 | 100 | 100 | 60 | 100
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2007-09-26 08:00 | 20d | 81649.6 | 0 | 0 | 0 | 0 | 81649.6 | 0 | 100% | Finished | 81649.6 | 79904.08 | 100 | 100 | 100 | 100 | 100 | 100
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 |  | 10d | [5 empty] | 0.01 |  | 100% |  | 0.01 | 0.01
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9709 |  |  | 262542.5712 |  | 40d | [5 empty] | 262542.5712 |  | 99.49% |  | 261212.6513 | 262459.4512
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 100 | 100 | 100 | 100 | 100 | 100
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100% | Finished | 37704.9611 | 37704.9611 | 100 | 100 | 100 | 100 | 100 | 100
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.00 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 106140 | 0 | 0 | 0 | 0 | 106140 | 0 | 100% | Finished | 106140 | 106140 | 100 | 100 | 100 | 100 | 100 | 100
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2007-08-29 08:00 | 20d | 25475.0001 | 0 | 0 | 0 | 0 | 25475.0001 | 0 | 100% | Finished | 25475.0001 | 25475.0001 | 100 | 100 | 100 | 100 | 100 | 100
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400 | 100 | 100 | 100 | 100 | 100 | 100
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2007-10-03 08:00 | 20d | 79149.6 | 1662.4 | 5d | 0 | 0 | 79149.6 | 1662.4 | 80% | Started | 77819.6801 | 79066.48 | 100 | 100 | 80 | 100 | 100 | 80
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9709 |  |  | 149562.5709 |  | 40d | [5 empty] | 148282.5709 |  | 100% |  | 149562.5709 | 149479.4509
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 100 | 100 | 100 | 100 | 100 | 100
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 34452.9609 | 0 | 0 | 0 | 0 | 34452.9609 | 0 | 100% | Finished | 34452.9609 | 34452.9609 | 100 | 100 | 100 | 100 | 100 | 100
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 46116 | 0 | 0 | 0 | 0 | 46116 | 0 | 100% | Finished | 46116 | 46116 | 100 | 100 | 100 | 100 | 100 | 100
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 16771 | 0 | 0 | 0 | 0 | 16771 | 0 | 100% | Finished | 16771 | 16771 | 100 | 100 | 100 | 100 | 100 | 100
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 5120 | 0 | 0 | 0 | 0 | 5120 | 0 | 100% | Finished | 6400 | 6400 | 100 | 80 | 100 | 100 | 80 | 100
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2007-09-26 08:00 | 20d | 38149.6 | 0 | 0 | 0 | 0 | 38149.6 | 0 | 100% | Finished | 38149.6 | 38066.48 | 100 | 100 | 100 | 100 | 100 | 100
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9116 |  |  | 518712.7116 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 23538.8
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.00 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 |  | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0% | Not Started | 0 | 23538.8 | 100 |  | 0 | 100 |  | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2008-01-10 08:00 |  | TP Name | Completion
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Claeys-Verhelst Premises | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.3057 |  |  | 3027133.1861 |  | 453d | [5 empty] | 3102395.9061 |  | 100% |  | 3027133.1861 | 3027133.1861
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9701 |  |  | 253804.5701 |  | 214d | [5 empty] | 283418.6501 |  | 100% |  | 253804.5701 | 253804.5701
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 166.6667 | 100 | 100 | 100 | 100
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 100 | 150 | 100 | 100 | 100 | 100
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 100 | 100 | 100 | 100 | 100 | 100
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 100 | 100 | 100 | 100 | 100 | 100
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.00 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 67701.79 | 0 | 0 | 0 | 0 | 67701.79 | 0 | 100% | Finished | 38087.71 | 38087.71 | 100 | 180 | 100 | 100 | 177.7523 | 100
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.894 |  |  | 401436.374 |  | 36d | [5 empty] | 402361.814 |  | 100% |  | 401436.374 | 401436.374
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 29084.8 | 0 | 0 | 0 | 0 | 29084.8 | 0 | 100% | Finished | 30318.72 | 30318.72 | 100 | 71.4286 | 100 | 100 | 95.9302 | 100
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.76 | 0 | 0 | 0 | 0 | 5701.76 | 0 | 100% | Finished | 2616.96 | 2616.96 | 100 | 600 | 100 | 100 | 217.8772 | 100
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4066 | 0 | 0 | 0 | 0 | 118883.4066 | 0 | 100% | Finished | 121659.7266 | 121659.7266 | 100 | 88 | 100 | 100 | 97.718 | 100
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.00 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 12330.01 | 0 | 0 | 0 | 0 | 12330.01 | 0 | 100% | Finished | 10479.13 | 10479.13 | 100 | 120 | 100 | 100 | 117.6625 | 100
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.00 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100% | Finished | 236361.8375 | 236361.8375 | 100 | 100 | 100 | 100 | 100 | 100
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4531 |  |  | 542212.4531 |  | 45d | [5 empty] | 523703.6531 |  | 100% |  | 542212.4531 | 542212.4531
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.00 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 137501.3078 | 0 | 0 | 0 | 0 | 137501.3078 | 0 | 100% | Finished | 143670.9078 | 143670.9078 | 100 | 75 | 100 | 100 | 95.7057 | 100
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.00 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 123579.3188 | 0 | 0 | 0 | 0 | 123579.3188 | 0 | 100% | Finished | 129748.9187 | 129748.9187 | 100 | 50 | 100 | 100 | 95.245 | 100
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.00 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 132874.1078 | 0 | 0 | 0 | 0 | 132874.1078 | 0 | 100% | Finished | 132874.1078 | 132874.1078 | 100 | 100 | 100 | 100 | 100 | 100
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.00 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 129748.9187 | 0 | 0 | 0 | 0 | 129748.9187 | 0 | 100% | Finished | 135918.5187 | 135918.5187 | 100 | 66.6667 | 100 | 100 | 95.4608 | 100
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1641 |  |  | 597047.364 |  | 112d | [5 empty] | 671831.364 |  | 100% |  | 597047.364 | 597047.364
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.00 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 351653.2 | 0 | 0 | 0 | 0 | 351653.2 | 0 | 100% | Finished | 351653.2 | 351653.2 | 100 | 100 | 100 | 100 | 100 | 100
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 234654.5938 | 0 | 0 | 0 | 0 | 234654.5938 | 0 | 100% | Finished | 159870.5938 | 159870.5938 | 100 | 920 | 100 | 100 | 146.7778 | 100
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.00 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100% | Finished | 85523.5703 | 85523.5703 | 100 | 100 | 100 | 100 | 100 | 100
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9609 |  |  | 301814.5611 |  | 65d | [5 empty] | 291542.5611 |  | 100% |  | 301814.5611 | 301814.5611
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.00 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 142112 | 0 | 0 | 0 | 0 | 142112 | 0 | 100% | Finished | 149824 | 149824 | 100 | 50 | 100 | 100 | 94.8526 | 100
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 100 | 100 | 100 | 100 | 100 | 100
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100% | Finished | 37704.9611 | 37704.9611 | 100 | 100 | 100 | 100 | 100 | 100
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 18563 | 0 | 0 | 0 | 0 | 18563 | 0 | 100% | Finished | 18563 | 18563 | 100 | 100 | 100 | 100 | 100 | 100
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 6400 | 6400 | 100 | 60 | 100 | 100 | 60 | 100
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2007-09-26 08:00 | 20d | 81649.6 | 0 | 0 | 0 | 0 | 81649.6 | 0 | 100% | Finished | 81649.6 | 81649.6 | 100 | 100 | 100 | 100 | 100 | 100
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 |  | 10d | [5 empty] | 0.01 |  | 100% |  | 0.01 | 0.01
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9709 |  |  | 262542.5712 |  | 45d | [5 empty] | 262542.5712 |  | 100% |  | 262542.5712 | 262542.5712
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 100 | 100 | 100 | 100 | 100 | 100
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100% | Finished | 37704.9611 | 37704.9611 | 100 | 100 | 100 | 100 | 100 | 100
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.00 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 106140 | 0 | 0 | 0 | 0 | 106140 | 0 | 100% | Finished | 106140 | 106140 | 100 | 100 | 100 | 100 | 100 | 100
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2007-08-29 08:00 | 20d | 25475.0001 | 0 | 0 | 0 | 0 | 25475.0001 | 0 | 100% | Finished | 25475.0001 | 25475.0001 | 100 | 100 | 100 | 100 | 100 | 100
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400 | 100 | 100 | 100 | 100 | 100 | 100
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2007-10-03 08:00 | 20d | 79149.6 | 0 | 0 | 0 | 0 | 79149.6 | 0 | 100% | Finished | 79149.6 | 79149.6 | 100 | 100 | 100 | 100 | 100 | 100
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9709 |  |  | 149562.5709 |  | 40d | [5 empty] | 148282.5709 |  | 100% |  | 149562.5709 | 149562.5709
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 100 | 100 | 100 | 100 | 100 | 100
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 34452.9609 | 0 | 0 | 0 | 0 | 34452.9609 | 0 | 100% | Finished | 34452.9609 | 34452.9609 | 100 | 100 | 100 | 100 | 100 | 100
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 46116 | 0 | 0 | 0 | 0 | 46116 | 0 | 100% | Finished | 46116 | 46116 | 100 | 100 | 100 | 100 | 100 | 100
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 16771 | 0 | 0 | 0 | 0 | 16771 | 0 | 100% | Finished | 16771 | 16771 | 100 | 100 | 100 | 100 | 100 | 100
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 5120 | 0 | 0 | 0 | 0 | 5120 | 0 | 100% | Finished | 6400 | 6400 | 100 | 80 | 100 | 100 | 80 | 100
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2007-09-26 08:00 | 20d | 38149.6 | 0 | 0 | 0 | 0 | 38149.6 | 0 | 100% | Finished | 38149.6 | 38149.6 | 100 | 100 | 100 | 100 | 100 | 100
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9116 |  |  | 518712.7116 |  | 48d | [5 empty] | 518712.7116 |  | 100% |  | 518712.7116 | 518712.7116
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.00 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2007-11-05 08:00 | 15d | 23538.8 | 0 | 0 | 0 | 0 | 23538.8 | 0 | 100% | Finished | 23538.8 | 23538.8 | 100 | 100 | 100 | 100 | 100 | 100
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2007-11-05 08:00 | 25d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2007-11-26 08:00 | 20d | 87000 | 0 | 0 | 0 | 0 | 87000 | 0 | 100% | Finished | 87000 | 87000 | 100 | 133.3333 | 100 | 100 | 100 | 100
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2007-11-26 08:00 | 15d | 2156.0601 | 0 | 0 | 0 | 0 | 2156.0601 | 0 | 100% | Finished | 2156.0601 | 2156.0601 | 100 | 100 | 100 | 100 | 100 | 100
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2007-12-10 08:00 | 10d | 33000 | 0 | 0 | 0 | 0 | 33000 | 0 | 100% | Finished | 33000 | 33000 | 100 | 100 | 100 | 100 | 100 | 100
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2007-12-10 08:00 | 10d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100% | Finished | 16000 | 16000 | 100 | 100 | 100 | 100 | 100 | 100
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2007-12-10 08:00 | 5d | 38817.8516 | 0 | 0 | 0 | 0 | 38817.8516 | 0 | 100% | Finished | 38817.8516 | 38817.8516 | 100 | 100 | 100 | 100 | 100 | 100
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2007-12-10 08:00 | 5d | 32000 | 0 | 0 | 0 | 0 | 32000 | 0 | 100% | Finished | 32000 | 32000 | 100 | 100 | 100 | 100 | 100 | 100
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.00 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2007-12-17 08:00 | 15d | 99800 | 0 | 0 | 0 | 0 | 99800 | 0 | 100% | Finished | 99800 | 99800 | 100 | 100 | 100 | 100 | 100 | 100
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.00 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2008-01-03 08:00 | 5d | 138400 | 0 | 0 | 0 | 0 | 138400 | 0 | 100% | Finished | 138400 | 138400 | 100 | 100 | 100 | 100 | 100 | 100

## TP8
| TP Status Date | 2008-01-11 08:00 |  | TP Name | Finish
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Claeys-Verhelst Premises | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.3057 |  |  | 3027133.1861 |  | 453d | [5 empty] | 3102395.9061 |  | 100% |  | 3027133.1861 | 3027133.1861
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9701 |  |  | 253804.5701 |  | 214d | [5 empty] | 283418.6501 |  | 100% |  | 253804.5701 | 253804.5701
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 166.6667 | 100 | 100 | 100 | 100
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 100 | 150 | 100 | 100 | 100 | 100
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 100 | 100 | 100 | 100 | 100 | 100
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 100 | 100 | 100 | 100 | 100 | 100
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.00 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 67701.79 | 0 | 0 | 0 | 0 | 67701.79 | 0 | 100% | Finished | 38087.71 | 38087.71 | 100 | 180 | 100 | 100 | 177.7523 | 100
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.894 |  |  | 401436.374 |  | 36d | [5 empty] | 402361.814 |  | 100% |  | 401436.374 | 401436.374
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 29084.8 | 0 | 0 | 0 | 0 | 29084.8 | 0 | 100% | Finished | 30318.72 | 30318.72 | 100 | 71.4286 | 100 | 100 | 95.9302 | 100
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.76 | 0 | 0 | 0 | 0 | 5701.76 | 0 | 100% | Finished | 2616.96 | 2616.96 | 100 | 600 | 100 | 100 | 217.8772 | 100
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4066 | 0 | 0 | 0 | 0 | 118883.4066 | 0 | 100% | Finished | 121659.7266 | 121659.7266 | 100 | 88 | 100 | 100 | 97.718 | 100
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.00 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 12330.01 | 0 | 0 | 0 | 0 | 12330.01 | 0 | 100% | Finished | 10479.13 | 10479.13 | 100 | 120 | 100 | 100 | 117.6625 | 100
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.00 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100% | Finished | 236361.8375 | 236361.8375 | 100 | 100 | 100 | 100 | 100 | 100
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4531 |  |  | 542212.4531 |  | 45d | [5 empty] | 523703.6531 |  | 100% |  | 542212.4531 | 542212.4531
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.00 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 137501.3078 | 0 | 0 | 0 | 0 | 137501.3078 | 0 | 100% | Finished | 143670.9078 | 143670.9078 | 100 | 75 | 100 | 100 | 95.7057 | 100
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.00 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 123579.3188 | 0 | 0 | 0 | 0 | 123579.3188 | 0 | 100% | Finished | 129748.9187 | 129748.9187 | 100 | 50 | 100 | 100 | 95.245 | 100
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.00 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 132874.1078 | 0 | 0 | 0 | 0 | 132874.1078 | 0 | 100% | Finished | 132874.1078 | 132874.1078 | 100 | 100 | 100 | 100 | 100 | 100
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.00 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 129748.9187 | 0 | 0 | 0 | 0 | 129748.9187 | 0 | 100% | Finished | 135918.5187 | 135918.5187 | 100 | 66.6667 | 100 | 100 | 95.4608 | 100
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1641 |  |  | 597047.364 |  | 112d | [5 empty] | 671831.364 |  | 100% |  | 597047.364 | 597047.364
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.00 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 351653.2 | 0 | 0 | 0 | 0 | 351653.2 | 0 | 100% | Finished | 351653.2 | 351653.2 | 100 | 100 | 100 | 100 | 100 | 100
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 234654.5938 | 0 | 0 | 0 | 0 | 234654.5938 | 0 | 100% | Finished | 159870.5938 | 159870.5938 | 100 | 920 | 100 | 100 | 146.7778 | 100
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.00 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100% | Finished | 85523.5703 | 85523.5703 | 100 | 100 | 100 | 100 | 100 | 100
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9609 |  |  | 301814.5611 |  | 65d | [5 empty] | 291542.5611 |  | 100% |  | 301814.5611 | 301814.5611
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.00 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 142112 | 0 | 0 | 0 | 0 | 142112 | 0 | 100% | Finished | 149824 | 149824 | 100 | 50 | 100 | 100 | 94.8526 | 100
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 100 | 100 | 100 | 100 | 100 | 100
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100% | Finished | 37704.9611 | 37704.9611 | 100 | 100 | 100 | 100 | 100 | 100
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 18563 | 0 | 0 | 0 | 0 | 18563 | 0 | 100% | Finished | 18563 | 18563 | 100 | 100 | 100 | 100 | 100 | 100
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 6400 | 6400 | 100 | 60 | 100 | 100 | 60 | 100
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2007-09-26 08:00 | 20d | 81649.6 | 0 | 0 | 0 | 0 | 81649.6 | 0 | 100% | Finished | 81649.6 | 81649.6 | 100 | 100 | 100 | 100 | 100 | 100
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 |  | 10d | [5 empty] | 0.01 |  | 100% |  | 0.01 | 0.01
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9709 |  |  | 262542.5712 |  | 45d | [5 empty] | 262542.5712 |  | 100% |  | 262542.5712 | 262542.5712
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 100 | 100 | 100 | 100 | 100 | 100
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100% | Finished | 37704.9611 | 37704.9611 | 100 | 100 | 100 | 100 | 100 | 100
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.00 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 106140 | 0 | 0 | 0 | 0 | 106140 | 0 | 100% | Finished | 106140 | 106140 | 100 | 100 | 100 | 100 | 100 | 100
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2007-08-29 08:00 | 20d | 25475.0001 | 0 | 0 | 0 | 0 | 25475.0001 | 0 | 100% | Finished | 25475.0001 | 25475.0001 | 100 | 100 | 100 | 100 | 100 | 100
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400 | 100 | 100 | 100 | 100 | 100 | 100
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2007-10-03 08:00 | 20d | 79149.6 | 0 | 0 | 0 | 0 | 79149.6 | 0 | 100% | Finished | 79149.6 | 79149.6 | 100 | 100 | 100 | 100 | 100 | 100
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9709 |  |  | 149562.5709 |  | 40d | [5 empty] | 148282.5709 |  | 100% |  | 149562.5709 | 149562.5709
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 100 | 100 | 100 | 100 | 100 | 100
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 34452.9609 | 0 | 0 | 0 | 0 | 34452.9609 | 0 | 100% | Finished | 34452.9609 | 34452.9609 | 100 | 100 | 100 | 100 | 100 | 100
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 46116 | 0 | 0 | 0 | 0 | 46116 | 0 | 100% | Finished | 46116 | 46116 | 100 | 100 | 100 | 100 | 100 | 100
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 16771 | 0 | 0 | 0 | 0 | 16771 | 0 | 100% | Finished | 16771 | 16771 | 100 | 100 | 100 | 100 | 100 | 100
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 5120 | 0 | 0 | 0 | 0 | 5120 | 0 | 100% | Finished | 6400 | 6400 | 100 | 80 | 100 | 100 | 80 | 100
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2007-09-26 08:00 | 20d | 38149.6 | 0 | 0 | 0 | 0 | 38149.6 | 0 | 100% | Finished | 38149.6 | 38149.6 | 100 | 100 | 100 | 100 | 100 | 100
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9116 |  |  | 518712.7116 |  | 48d | [5 empty] | 518712.7116 |  | 100% |  | 518712.7116 | 518712.7116
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.00 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2007-11-05 08:00 | 15d | 23538.8 | 0 | 0 | 0 | 0 | 23538.8 | 0 | 100% | Finished | 23538.8 | 23538.8 | 100 | 100 | 100 | 100 | 100 | 100
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2007-11-05 08:00 | 25d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2007-11-26 08:00 | 20d | 87000 | 0 | 0 | 0 | 0 | 87000 | 0 | 100% | Finished | 87000 | 87000 | 100 | 133.3333 | 100 | 100 | 100 | 100
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2007-11-26 08:00 | 15d | 2156.0601 | 0 | 0 | 0 | 0 | 2156.0601 | 0 | 100% | Finished | 2156.0601 | 2156.0601 | 100 | 100 | 100 | 100 | 100 | 100
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2007-12-10 08:00 | 10d | 33000 | 0 | 0 | 0 | 0 | 33000 | 0 | 100% | Finished | 33000 | 33000 | 100 | 100 | 100 | 100 | 100 | 100
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2007-12-10 08:00 | 10d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100% | Finished | 16000 | 16000 | 100 | 100 | 100 | 100 | 100 | 100
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2007-12-10 08:00 | 5d | 38817.8516 | 0 | 0 | 0 | 0 | 38817.8516 | 0 | 100% | Finished | 38817.8516 | 38817.8516 | 100 | 100 | 100 | 100 | 100 | 100
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2007-12-10 08:00 | 5d | 32000 | 0 | 0 | 0 | 0 | 32000 | 0 | 100% | Finished | 32000 | 32000 | 100 | 100 | 100 | 100 | 100 | 100
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.00 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2007-12-17 08:00 | 15d | 99800 | 0 | 0 | 0 | 0 | 99800 | 0 | 100% | Finished | 99800 | 99800 | 100 | 100 | 100 | 100 | 100 | 100
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.00 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2008-01-03 08:00 | 5d | 138400 | 0 | 0 | 0 | 0 | 138400 | 0 | 100% | Finished | 138400 | 138400 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Preparation1 | 2006-04-17 08:00 | 2006-07-07 08:00 | 5716.8501 | 5716.8501 | 5716.8501 | 2006-07-06 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2007-12-26 10:00 | 2007-12-26 10:00 | 2007-12-26 10:00 | 2007-12-26 10:00 | 2007-12-26 10:00 | 2007-12-26 10:00 | 2007-12-26 10:00 | 2007-12-26 10:00 | 2007-12-26 10:00 | 3027133.1861 | 3027133.1861 | 3027133.1861 | 3027133.1861 | 3027133.1861 | 3027133.1861 | 3027133.1861 | 3027133.1861 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
Preparation2 | 2006-07-07 08:00 | 2007-02-08 08:00 | 779169.1319 | 253804.5701 | 283418.6501 | 2006-12-08 17:00 | -525364.5619 | 32.57% | -29614.08 | 89.55% | -43d | 79.81% | 100% | 2008-04-10 17:00 | 2011-06-29 15:00 | 2012-02-07 09:00 | 2008-07-14 16:00 | 2011-06-29 15:00 | 2012-01-03 10:00 | 2008-02-25 10:00 | 2008-05-30 09:00 | 2008-07-24 16:00 | 3056747.2661 | 3380341.0275 | 8797418.416 | 3758236.2689 | 9790837.3687 | 4163680.2171 | 3831887.4344 | 3449198.3439 | 0.79812 | 0.89551 | 0.32574 | 1 | -43 | 0.89551 | 1 | 0.79812 | 1
Foundation | 2007-02-08 08:00 | 2007-03-17 08:00 | 1048578.7185 | 647075.3017 | 685780.4641 | 2007-01-22 09:00 | -401503.4168 | 61.71% | -38705.1624 | 94.36% | -39d 7h | 83.39% | 100% | 2008-03-17 16:00 | 2009-01-13 14:00 | 2009-03-13 12:00 | 2008-05-02 09:00 | 2009-01-13 14:00 | 2009-02-23 09:00 | 2008-02-20 09:00 | 2008-04-28 11:00 | 2008-05-21 15:00 | 3065838.3485 | 3208202.8102 | 4542639.2251 | 3540065.9969 | 4773339.3375 | 3710796.6443 | 3395725.8729 | 3268254.8383 | 0.83385 | 0.94356 | 0.6171 | 1 | -39.875 | 0.94356 | 1 | 0.83385 | 1
Shell | 2007-03-17 08:00 | 2007-06-04 08:00 | 1790852.7613 | 1183389.3748 | 1209484.1173 | 2007-04-11 12:00 | -607463.3865 | 66.08% | -26094.7425 | 97.84% | -37d 4h | 87.29% | 98.81% | 2008-04-28 17:00 | 2008-11-07 10:00 | 2008-11-27 17:00 | 2008-05-14 11:00 | 2008-11-07 10:00 | 2008-11-19 12:00 | 2008-02-15 15:00 | 2008-03-25 14:00 | 2008-04-01 11:00 | 3053227.9285 | 3093884.0481 | 3999667.776 | 3321734.3088 | 4061193.6994 | 3368311.2225 | 3224726.6075 | 3135434.8432 | 0.87288 | 0.97842 | 0.6608 | 0.98811 | -37.5 | 0.97842 | 1 | 0.87288 | 1
Wind&Waterproof | 2007-06-04 08:00 | 2007-07-02 08:00 | 1944324.7613 | 1790091.2511 | 1881315.4813 | 2007-06-01 09:00 | -154233.5102 | 92.07% | -91224.2302 | 95.15% | -20d 7h | 93.37% | 99.8% | 2008-01-25 15:00 | 2008-02-18 11:00 | 2008-03-21 16:00 | 2008-01-30 10:00 | 2008-02-18 11:00 | 2008-02-28 15:00 | 2008-01-24 09:00 | 2008-02-07 14:00 | 2008-02-19 15:00 | 3118357.4162 | 3181397.8887 | 3224940.4297 | 3206154.2726 | 3293412.4428 | 3273668.9308 | 3189879.1524 | 3186274.8708 | 0.93373 | 0.95151 | 0.92068 | 0.99803 | -20.875 | 0.95151 | 1 | 0.93373 | 1
WH, L1, L2 | 2007-07-02 08:00 | 2007-10-24 08:00 | 2530047.5144 | 2506206.5298 | 2583683.1944 | 2007-10-03 14:00 | -23840.9846 | 99.06% | -77476.6646 | 97% | -14d 3h | 96.38% | 99.41% | 2007-12-31 15:00 | 2008-01-01 12:00 | 2008-01-21 10:00 | 2007-12-31 17:00 | 2008-01-01 12:00 | 2008-01-02 17:00 | 2008-01-15 14:00 | 2008-01-17 16:00 | 2008-01-21 15:00 | 3104609.8507 | 3120713.7349 | 3109565.3099 | 3124180.7639 | 3125822.3868 | 3140889.6618 | 3118446.395 | 3121403.5778 | 0.96379 | 0.97001 | 0.99058 | 0.99407 | -14.375 | 0.97001 | 1 | 0.96379 | 1
Completion | 2007-10-24 08:00 | 2008-01-10 08:00 | 3027133.1861 | 3027133.1861 | 3102395.9061 | 2007-12-26 10:00 | 0 | 100% | -75262.72 | 97.57% | -10d 6h | 97.63% | 100% | 2007-12-26 10:00 | 2007-12-26 10:00 | 2008-01-10 10:00 | 2008-01-09 17:00 | 2008-01-09 17:00 | 2008-01-09 17:00 | 2008-01-09 17:00 | 2008-01-09 17:00 | 2008-01-09 17:00 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 0.97627 | 0.97574 | 1 | 1 | -10.75 | 0.97574 | 1 | 0.97627 | 1
Finish | 2008-01-10 08:00 | 2008-01-11 08:00 | 3027133.1861 | 3027133.1861 | 3102395.9061 | 2007-12-26 10:00 | 0 | 100% | -75262.72 | 97.57% | -11d 6h | 97.41% | 100% | 2007-12-26 10:00 | 2007-12-26 10:00 | 2008-01-10 10:00 | 2008-01-10 17:00 | 2008-01-10 17:00 | 2008-01-10 17:00 | 2008-01-10 17:00 | 2008-01-10 17:00 | 2008-01-10 17:00 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 3102395.9061 | 0.97412 | 0.97574 | 1 | 1 | -11.75 | 0.97574 | 1 | 0.97412 | 1