## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Kitchen Tower Anderlecht | 1 |  |  | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 | 464.375
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 1.1 |  | SS2;SS10;SS11;SS12;SS13+3d | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 464.375
2 | UITZETTEN HOOFDASSEN | 1.2 | 1SS | FS3 | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 0.375
3 | AFGRAVEN TEELAARDE | 1.3 | 2FS | FS4 | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 3.375
4 | AANLEGGEN RIOLERING EN WERFWEG | 1.4 | 3FS | FS5;FS20 | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 3.375
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 1.5 | 4FS |  | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 4.375
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 1.6 | 23FS+1d |  | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 426.375
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 1.7 |  |  | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 | 280.375
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 1.7.1 | 1SS |  | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 4.375
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 1.7.2 | 1SS |  | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 0.375
12 | BETON EN WAPENING PREFABTRAPPEN | 1.7.3 | 1SS |  | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 0.375
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 1.7.4 | 1SS+3d |  | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 0.375
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 1.7.5 |  |  | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 0.375
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 1.7.6 |  |  | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 0.375
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 1.7.7 |  |  | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 0.375
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 1.7.8 |  |  | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 0.375
18 | RUWBOUW BETONWERKEN $$ | 1.8 |  |  | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 | 450.375
19 | BETON KELDER | 1.8.1 |  |  | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 | 253.375
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 1.8.1.1 | 4FS | FS21 | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 8.375
21 | INSTALLATIE BEMALING BOUWPUT | 1.8.1.2 | 20FS | FS22;FS23+1w | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 1.375
22 | BEMALING | 1.8.1.3 | 21FS |  | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 55.375
23 | UITGRAVING KELDER EN ZOLEN | 1.8.1.4 | 21FS+1w | FS6+1d;FS24 | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 4.375
24 | ZUIVERHEIDSBETON | 1.8.1.5 | 23FS | FS25+2d | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 0.375
25 | AFSCHIETEN PAALKOPPEN | 1.8.1.6 | 24FS+2d | FS26 | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2.375
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 1.8.1.7 | 25FS |  | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 5.375
27 | WAPENING FUNDERINGSPLAAT KELDER | 1.8.1.8 |  |  | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2.375
28 | RIOLERING IN FUNDERINGSPLAAT | 1.8.1.9 |  | FS29 | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 1.375
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 1.8.1.10 | 28FS | FS30+1d | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 0.375
30 | BETON KELDERWANDEN | 1.8.1.11 | 29FS+1d | FS31;FS33;FS35 | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 14.375
31 | WATERDICHTE ROK OP KELDERWANDEN | 1.8.1.12 | 30FS | FS32+3d | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2.375
32 | AANVULLING KELDER | 1.8.1.13 | 31FS+3d | FS34 | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 4.375
33 | BETON BORDES KOKER A | 1.8.1.14 | 30FS |  | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 0.375
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 1.8.1.15 | 32FS |  | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 0.375
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 1.8.1.16 | 30FS |  | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 6.375
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 1.8.1.17 |  | FS37 | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 3.375
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 1.8.1.18 | 36FS | SS44+2d | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 0.375
38 | PREFABBETON KOKERWANDEN | 1.8.1.19 |  |  | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 | 237.375
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 1.8.1.19.1 |  |  | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 6.375
40 | PRODUCTIE DEUVELKOPPELPLATEN | 1.8.1.19.2 |  |  | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 6.375
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 1.8.1.19.3 |  | SS42+2w 2d | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 216.375
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 1.8.1.19.4 | 41SS+2w 2d |  | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 0.375
43 | BETON GELIJKVLOERS | 1.8.2 |  |  | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 | 19.375
44 | WANDEN KOKER A | 1.8.2.1 | 37SS+2d | FS45;FS47+3d | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
45 | WANDEN KOKER F | 1.8.2.2 | 44FS | FS46;FS48+2d;FS50+1d | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
46 | WANDEN KOKER B tot E | 1.8.2.3 | 45FS | FS49;FS51+1d | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 3.375
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.2.4 | 44FS+3d |  | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
48 | BEKISTEN TUSSENBORDES KOKER F | 1.8.2.5 | 45FS+2d |  | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
49 | PL. WERKVLOEREN KOKERS B tot E | 1.8.2.6 | 46FS |  | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
50 | BETON DRAAGWAND KOKER A en F | 1.8.2.7 | 45FS+1d | FS52;FS53+1d;FS54 | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 1.375
51 | BETON DRAAGWAND KOKER B tot E | 1.8.2.8 | 46FS+1d |  | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
52 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.2.9 | 50FS |  | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
53 | BEKISTEN PLAAT KOKER F | 1.8.2.10 | 50FS+1d |  | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
54 | BEKISTEN RANDBALK PLAAT | 1.8.2.11 | 50FS | SS55+2d | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
55 | BEKISTEN PLAAT (met tafels) | 1.8.2.12 | 54SS+2d | SS56+2d | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 4.375
56 | WAPENING VLOERPLATEN | 1.8.2.13 | 55SS+2d | FS57 | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2.375
57 | BETON VLOERPLATEN ( grof vlinderen) | 1.8.2.14 | 56FS | FS58 | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 1.8.2.15 | 57FS | FS60 | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
59 | BETON EERSTE VERDIEPING | 1.8.3 |  |  | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 | 17.375
60 | WANDEN KOKER A | 1.8.3.1 | 58FS | FS61;FS63+3d | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
61 | WANDEN KOKER F | 1.8.3.2 | 60FS | FS62;FS64+2d;FS66+1d | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
62 | WANDEN KOKER B tot E | 1.8.3.3 | 61FS | FS65;FS67+1d | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 1.375
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.3.4 | 60FS+3d |  | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
64 | BEKISTEN TUSSENBORDES KOKER F | 1.8.3.5 | 61FS+2d |  | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
65 | PL. WERKVLOEREN KOKERS B tot E | 1.8.3.6 | 62FS |  | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
66 | BETON DRAAGWAND KOKER A en F | 1.8.3.7 | 61FS+1d | FS68;FS69+1d;FS70 | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 3.375
67 | BETON DRAAGWAND KOKER B tot E | 1.8.3.8 | 62FS+1d |  | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
68 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.3.9 | 66FS |  | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
69 | BEKISTEN PLAAT KOKER F | 1.8.3.10 | 66FS+1d |  | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
70 | BEKISTEN RANDBALK PLAAT | 1.8.3.11 | 66FS | SS71+2d | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
71 | BEKISTEN PLAAT (met tafels) | 1.8.3.12 | 70SS+2d | SS72+2d | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 4.375
72 | WAPENING VLOERPLATEN | 1.8.3.13 | 71SS+2d | FS73 | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2.375
73 | BETON VLOERPLATEN (grof vlinderen) | 1.8.3.14 | 72FS | FS74 | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.3.15 | 73FS | FS76 | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
75 | BETON TWEEDE VERDIEPING | 1.8.4 |  |  | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 | 17.375
76 | WANDEN KOKER A | 1.8.4.1 | 74FS | FS77;FS79+3d | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
77 | WANDEN KOKER F | 1.8.4.2 | 76FS | FS78;FS80+2d;FS82+1d | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
78 | WANDEN KOKER B tot E | 1.8.4.3 | 77FS | FS81;FS83+1d | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 1.375
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.4.4 | 76FS+3d |  | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
80 | BEKISTEN TUSSENBORDES KOKER F | 1.8.4.5 | 77FS+2d |  | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
81 | PL. WERKVLOEREN KOKERS B tot E | 1.8.4.6 | 78FS |  | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
82 | BETON DRAAGWAND KOKER A en F | 1.8.4.7 | 77FS+1d | FS84;FS85+1d;FS86 | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 1.375
83 | BETON DRAAGWAND KOKER B tot E | 1.8.4.8 | 78FS+1d |  | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
84 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.4.9 | 82FS |  | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
85 | BEKISTEN PLAAT KOKER F | 1.8.4.10 | 82FS+1d |  | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
86 | BEKISTEN RANDBALK PLAAT | 1.8.4.11 | 82FS | SS87+2d | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
87 | BEKISTEN PLAAT (met tafels) | 1.8.4.12 | 86SS+2d | SS88+2d | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
88 | WAPENING VLOERPLATEN | 1.8.4.13 | 87SS+2d | FS89 | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 4.375
89 | BETON VLOERPLATEN (grof vlinderen) | 1.8.4.14 | 88FS | FS90 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.4.15 | 89FS | FS92 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
91 | BETON DERDE VERDIEPING | 1.8.5 |  |  | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 | 20.375
92 | WANDEN KOKER A | 1.8.5.1 | 90FS | FS93;FS95+3d | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
93 | WANDEN KOKER F | 1.8.5.2 | 92FS | FS94;FS96+2d;FS98+1d | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
94 | WANDEN KOKER B tot E | 1.8.5.3 | 93FS | FS97;FS99+1d | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 1.375
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.5.4 | 92FS+3d |  | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
96 | BEKISTEN TUSSENBORDES KOKER F | 1.8.5.5 | 93FS+2d |  | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
97 | PL. WERKVLOEREN KOKERS B tot E | 1.8.5.6 | 94FS |  | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
98 | BETON DRAAGWAND KOKER A en F | 1.8.5.7 | 93FS+1d | FS100;FS101+1d;FS102 | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 1.375
99 | BETON DRAAGWAND KOKER B tot E | 1.8.5.8 | 94FS+1d |  | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
100 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.5.9 | 98FS |  | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
101 | BEKISTEN PLAAT KOKER F | 1.8.5.10 | 98FS+1d |  | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
102 | BEKISTEN RANDBALK PLAAT | 1.8.5.11 | 98FS | SS103+2d | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 4.375
103 | BEKISTEN PLAAT (met tafels) | 1.8.5.12 | 102SS+2d | SS104+2d | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
104 | WAPENING VLOERPLATEN | 1.8.5.13 | 103SS+2d | FS105 | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 4.375
105 | BETON VLOERPLATEN (grof vlinderen) | 1.8.5.14 | 104FS | FS106 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.5.15 | 105FS | FS108 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
107 | BETON VIERDE VERDIEPING | 1.8.6 |  |  | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 | 21.375
108 | WANDEN KOKER A | 1.8.6.1 | 106FS | FS109;FS111+3d | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
109 | WANDEN KOKER F | 1.8.6.2 | 108FS | FS110;FS112+2d;FS114+1d | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
110 | WANDEN KOKER B tot E | 1.8.6.3 | 109FS | FS113;FS115+1d | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 1.375
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.6.4 | 108FS+3d |  | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
112 | BEKISTEN TUSSENBORDES KOKER F | 1.8.6.5 | 109FS+2d |  | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
113 | PL. WERKVLOEREN KOKERS B tot E | 1.8.6.6 | 110FS |  | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
114 | BETON DRAAGWAND KOKER A en F | 1.8.6.7 | 109FS+1d | FS116;FS117+1d;FS118 | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 3.375
115 | BETON DRAAGWAND KOKER B tot E | 1.8.6.8 | 110FS+1d |  | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
116 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.6.9 | 114FS |  | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
117 | BEKISTEN PLAAT KOKER F | 1.8.6.10 | 114FS+1d |  | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
118 | BEKISTEN RANDBALK PLAAT | 1.8.6.11 | 114FS | SS119+2d | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
119 | BEKISTEN PLAAT (met tafels) | 1.8.6.12 | 118SS+2d | SS120+2d | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 4.375
120 | WAPENING VLOERPLATEN | 1.8.6.13 | 119SS+2d | FS121 | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2.375
121 | BETON VLOERPLATEN (grof vlinderen) | 1.8.6.14 | 120FS | FS122 | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.6.15 | 121FS | FS124 | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
123 | BETON VIJFDE VERDIEPING | 1.8.7 |  |  | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 | 17.375
124 | WANDEN KOKER A | 1.8.7.1 | 122FS | FS125;FS127+3d | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
125 | WANDEN KOKER F | 1.8.7.2 | 124FS | FS126;FS128+2d;FS130+1d | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
126 | WANDEN KOKER B tot E | 1.8.7.3 | 125FS | FS129;FS131+1d | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 1.375
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.7.4 | 124FS+3d |  | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
128 | BEKISTEN TUSSENBORDES KOKER F | 1.8.7.5 | 125FS+2d |  | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
129 | PL. WERKVLOEREN KOKERS B tot E | 1.8.7.6 | 126FS |  | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
130 | BETON DRAAGWAND KOKER A en F | 1.8.7.7 | 125FS+1d | FS132;FS133+1d;FS134 | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 1.375
131 | BETON DRAAGWAND KOKER B tot E | 1.8.7.8 | 126FS+1d |  | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
132 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.7.9 | 130FS |  | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
133 | BEKISTEN PLAAT KOKER F | 1.8.7.10 | 130FS+1d |  | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
134 | BEKISTEN RANDBALK PLAAT | 1.8.7.11 | 130FS | SS135+2d | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
135 | BEKISTEN PLAAT (met tafels) | 1.8.7.12 | 134SS+2d | SS136+2d | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
136 | WAPENING VLOERPLATEN | 1.8.7.13 | 135SS+2d | FS137 | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 4.375
137 | BETON VLOERPLATEN (grof vlinderen) | 1.8.7.14 | 136FS | FS138 | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.7.15 | 137FS | FS140 | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
139 | BETON ZESDE VERDIEPING | 1.8.8 |  |  | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 | 33.375
140 | WANDEN KOKER A | 1.8.8.1 | 138FS | FS141;FS143+3d | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
141 | WANDEN KOKER F | 1.8.8.2 | 140FS | FS142;FS144+2d;FS146+1d | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
142 | WANDEN KOKER B tot E | 1.8.8.3 | 141FS | FS145;FS147+1d | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 1.375
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.8.4 | 140FS+3d |  | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
144 | BEKISTEN TUSSENBORDES KOKER F | 1.8.8.5 | 141FS+2d |  | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
145 | PL. WERKVLOEREN KOKERS B tot E | 1.8.8.6 | 142FS |  | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
146 | BETON DRAAGWAND KOKER A en F | 1.8.8.7 | 141FS+1d | FS148;FS149+1d;FS150 | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 1.375
147 | BETON DRAAGWAND KOKER B tot E | 1.8.8.8 | 142FS+1d |  | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
148 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.8.9 | 146FS |  | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
149 | BEKISTEN PLAAT KOKER F | 1.8.8.10 | 146FS+1d |  | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
150 | BEKISTEN RANDBALK PLAAT | 1.8.8.11 | 146FS | SS151+2d | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 4.375
151 | BEKISTEN PLAAT (met tafels) | 1.8.8.12 | 150SS+2d | SS152+2d | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
152 | WAPENING VLOERPLATEN | 1.8.8.13 | 151SS+2d | FS153 | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 4.375
153 | BETON VLOERPLATEN (grof vlinderen) | 1.8.8.14 | 152FS | FS154 | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.8.15 | 153FS | FS156 | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
155 | BETON ZEVENDE VERDIEPING | 1.8.9 |  |  | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 | 19.375
156 | WANDEN KOKER A | 1.8.9.1 | 154FS | FS157;FS159+3d | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
157 | WANDEN KOKER F | 1.8.9.2 | 156FS | FS158;FS160+2d;FS162+1d | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
158 | WANDEN KOKER B tot E | 1.8.9.3 | 157FS | FS161;FS163+1d | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 1.375
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.9.4 | 156FS+3d |  | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
160 | BEKISTEN TUSSENBORDES KOKER F | 1.8.9.5 | 157FS+2d |  | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
161 | PL. WERKVLOEREN KOKERS B tot E | 1.8.9.6 | 158FS |  | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
162 | BETON DRAAGWAND KOKER A en F | 1.8.9.7 | 157FS+1d | FS164;FS165+1d;FS166 | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 1.375
163 | BETON DRAAGWAND KOKER B tot E | 1.8.9.8 | 158FS+1d |  | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
164 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.9.9 | 162FS |  | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
165 | BEKISTEN PLAAT KOKER F | 1.8.9.10 | 162FS+1d |  | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
166 | BEKISTEN RANDBALK PLAAT | 1.8.9.11 | 162FS | SS167+2d | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 4.375
167 | BEKISTEN PLAAT (met tafels) | 1.8.9.12 | 166SS+2d | SS168+2d | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
168 | WAPENING VLOERPLATEN | 1.8.9.13 | 167SS+2d | FS169 | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2.375
169 | BETON VLOERPLATEN (grof vlinderen) | 1.8.9.14 | 168FS | FS170 | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.9.15 | 169FS | FS172 | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
171 | BETON ACHTSTE VERDIEPING | 1.8.10 |  |  | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 | 19.375
172 | WANDEN KOKER A | 1.8.10.1 | 170FS | FS173;FS175+3d | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
173 | WANDEN KOKER F | 1.8.10.2 | 172FS | FS174;FS176+2d;FS178+1d | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
174 | WANDEN KOKER B tot E | 1.8.10.3 | 173FS | FS177;FS179+1d | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 3.375
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.10.4 | 172FS+3d |  | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
176 | BEKISTEN TUSSENBORDES KOKER F | 1.8.10.5 | 173FS+2d |  | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
177 | PL. WERKVLOEREN KOKERS B tot E | 1.8.10.6 | 174FS |  | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
178 | BETON DRAAGWAND KOKER A en F | 1.8.10.7 | 173FS+1d | FS180;FS181+1d;FS182 | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 1.375
179 | BETON DRAAGWAND KOKER B tot E | 1.8.10.8 | 174FS+1d |  | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
180 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.10.9 | 178FS |  | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
181 | BEKISTEN PLAAT KOKER F | 1.8.10.10 | 178FS+1d |  | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
182 | BEKISTEN RANDBALK PLAAT | 1.8.10.11 | 178FS | SS183+2d | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
183 | BEKISTEN PLAAT (met tafels) | 1.8.10.12 | 182SS+2d | SS184+2d | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 4.375
184 | WAPENING VLOERPLATEN | 1.8.10.13 | 183SS+2d | FS185 | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2.375
185 | BETON VLOERPLATEN (grof vlinderen) | 1.8.10.14 | 184FS | FS186 | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.10.15 | 185FS | FS188 | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
187 | BETON NEGENDE VERDIEPING | 1.8.11 |  |  | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 | 17.375
188 | WANDEN KOKER A | 1.8.11.1 | 186FS | FS189;FS191+3d | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
189 | WANDEN KOKER F | 1.8.11.2 | 188FS | FS190;FS192+2d;FS194+1d | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
190 | WANDEN KOKER B tot E | 1.8.11.3 | 189FS | FS193;FS195+1d | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 1.375
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.11.4 | 188FS+3d |  | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
192 | BEKISTEN TUSSENBORDES KOKER F | 1.8.11.5 | 189FS+2d |  | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
193 | PL. WERKVLOEREN KOKERS B tot E | 1.8.11.6 | 190FS |  | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
194 | BETON DRAAGWAND KOKER A en F | 1.8.11.7 | 189FS+1d | FS196;FS197+1d;FS198 | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 3.375
195 | BETON DRAAGWAND KOKER B tot E | 1.8.11.8 | 190FS+1d |  | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
196 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.11.9 | 194FS |  | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
197 | BEKISTEN PLAAT KOKER F | 1.8.11.10 | 194FS+1d |  | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
198 | BEKISTEN RANDBALK PLAAT | 1.8.11.11 | 194FS | SS199+2d | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
199 | BEKISTEN PLAAT (met tafels) | 1.8.11.12 | 198SS+2d | SS200+2d | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 4.375
200 | WAPENING VLOERPLATEN | 1.8.11.13 | 199SS+2d | FS201 | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2.375
201 | BETON VLOERPLATEN (grof vlinderen) | 1.8.11.14 | 200FS | FS202 | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.11.15 | 201FS | FS204 | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
203 | BETON TIENDE VERDIEPING | 1.8.12 |  |  | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 | 17.375
204 | WANDEN KOKER A | 1.8.12.1 | 202FS | FS205;FS207+3d | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
205 | WANDEN KOKER F | 1.8.12.2 | 204FS | FS206;FS208+2d;FS210+1d | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
206 | WANDEN KOKER B tot E | 1.8.12.3 | 205FS | FS209;FS211+1d | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 1.375
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.12.4 | 204FS+3d |  | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
208 | BEKISTEN TUSSENBORDES KOKER F | 1.8.12.5 | 205FS+2d |  | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
209 | PL. WERKVLOEREN KOKERS B tot E | 1.8.12.6 | 206FS |  | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
210 | BETON DRAAGWAND KOKER A en F | 1.8.12.7 | 205FS+1d | FS212;FS213+1d;FS214 | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 1.375
211 | BETON DRAAGWAND KOKER B tot E | 1.8.12.8 | 206FS+1d |  | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
212 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.12.9 | 210FS |  | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
213 | BEKISTEN PLAAT KOKER F | 1.8.12.10 | 210FS+1d |  | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
214 | BEKISTEN RANDBALK PLAAT | 1.8.12.11 | 210FS | SS215+2d | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
215 | BEKISTEN PLAAT (met tafels) | 1.8.12.12 | 214SS+2d | SS216+2d | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
216 | WAPENING VLOERPLATEN | 1.8.12.13 | 215SS+2d | FS217 | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 4.375
217 | BETON VLOERPLATEN (grof vlinderen) | 1.8.12.14 | 216FS | FS218 | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.12.15 | 217FS | FS220 | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
219 | BETON ELFDE VERDIEPING | 1.8.13 |  |  | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 | 20.375
220 | WANDEN KOKER A | 1.8.13.1 | 218FS | FS221;FS223+3d | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
221 | WANDEN KOKER F | 1.8.13.2 | 220FS | FS222;FS224+2d;FS226+1d | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
222 | WANDEN KOKER B tot E | 1.8.13.3 | 221FS | FS225;FS227+1d | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 1.375
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.13.4 | 220FS+3d |  | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
224 | BEKISTEN TUSSENBORDES KOKER F | 1.8.13.5 | 221FS+2d |  | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
225 | PL. WERKVLOEREN KOKERS B tot E | 1.8.13.6 | 222FS |  | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
226 | BETON DRAAGWAND KOKER A en F | 1.8.13.7 | 221FS+1d | FS228;FS229+1d;FS230 | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 1.375
227 | BETON DRAAGWAND KOKER B tot E | 1.8.13.8 | 222FS+1d |  | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
228 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.13.9 | 226FS |  | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
229 | BEKISTEN PLAAT KOKER F | 1.8.13.10 | 226FS+1d |  | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
230 | BEKISTEN RANDBALK PLAAT | 1.8.13.11 | 226FS | SS231+2d | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
231 | BEKISTEN PLAAT (met tafels) | 1.8.13.12 | 230SS+2d | SS232+2d | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
232 | WAPENING VLOERPLATEN | 1.8.13.13 | 231SS+2d | FS233 | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 4.375
233 | BETON VLOERPLATEN (grof vlinderen) | 1.8.13.14 | 232FS | FS234 | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.13.15 | 233FS | FS236 | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
235 | BETON TWAALFDE VERDIEPING | 1.8.14 |  |  | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 | 19.375
236 | WANDEN KOKER A | 1.8.14.1 | 234FS | FS237;FS239+3d | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
237 | WANDEN KOKER F | 1.8.14.2 | 236FS | FS238;FS240+2d;FS242+1d | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
238 | WANDEN KOKER B tot E | 1.8.14.3 | 237FS | FS241;FS243+1d | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 | 0.375
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.14.4 | 236FS+3d |  | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
240 | BEKISTEN TUSSENBORDES KOKER F | 1.8.14.5 | 237FS+2d |  | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
241 | PL. WERKVLOEREN KOKERS B tot E | 1.8.14.6 | 238FS |  | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
242 | BETON DRAAGWAND KOKER A en F | 1.8.14.7 | 237FS+1d | FS244;FS245+1d;FS246 | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 1.375
243 | BETON DRAAGWAND KOKER B tot E | 1.8.14.8 | 238FS+1d |  | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
244 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.14.9 | 242FS |  | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
245 | BEKISTEN PLAAT KOKER F | 1.8.14.10 | 242FS+1d |  | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
246 | BEKISTEN RANDBALK PLAAT | 1.8.14.11 | 242FS | SS247+2d | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 4.375
247 | BEKISTEN PLAAT (met tafels) | 1.8.14.12 | 246SS+2d | SS248+2d | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
248 | WAPENING VLOERPLATEN | 1.8.14.13 | 247SS+2d | FS249 | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 4.375
249 | BETON VLOERPLATEN (grof vlinderen) | 1.8.14.14 | 248FS | FS250 | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.14.15 | 249FS | FS252 | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
251 | BETON DERTIENDE VERDIEPING | 1.8.15 |  |  | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 | 18.375
252 | WANDEN KOKER A | 1.8.15.1 | 250FS | FS253;FS255+3d | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
253 | WANDEN KOKER F | 1.8.15.2 | 252FS | FS254;FS256+2d;FS258+1d | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
254 | WANDEN KOKER B tot E | 1.8.15.3 | 253FS | FS257;FS259+1d | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 1.375
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 1.8.15.4 | 252FS+3d |  | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
256 | BEKISTEN TUSSENBORDES KOKER F | 1.8.15.5 | 253FS+2d |  | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
257 | PL. WERKVLOEREN KOKERS B tot E | 1.8.15.6 | 254FS |  | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
258 | BETON DRAAGWAND KOKER A en F | 1.8.15.7 | 253FS+1d | FS260;FS261+1d;FS262 | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 1.375
259 | BETON DRAAGWAND KOKER B tot E | 1.8.15.8 | 254FS+1d |  | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 0.375
260 | BEKISTEN PLAAT KOKER A (zwart) | 1.8.15.9 | 258FS |  | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
261 | BEKISTEN PLAAT KOKER F | 1.8.15.10 | 258FS+1d |  | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
262 | BEKISTEN RANDBALK PLAAT | 1.8.15.11 | 258FS | SS263+2d | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2.375
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 1.8.15.12 | 262SS+2d | SS264+2d | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 | 5.375
264 | WAPENING VLOERPLATEN | 1.8.15.13 | 263SS+2d | FS265 | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2.375
265 | BETON VLOERPLATEN (grof vlinderen) | 1.8.15.14 | 264FS | FS266;FS273+4w | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 0.375
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 1.8.15.15 | 265FS | FS268 | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 0.375
267 | BETON VEERTIENDE DAKVERDIEPING | 1.8.16 |  |  | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 | 58.375
268 | WANDEN KOKER A | 1.8.16.1 | 266FS | FS269 | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
269 | WANDEN KOKER F | 1.8.16.2 | 268FS | FS270+1d | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 0.375
270 | BETON DRAAGWAND KOKER F | 1.8.16.3 | 269FS+1d | FS271+1d | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 | 1.375
271 | BEKISTEN DAKPLAAT KOKER F | 1.8.16.4 | 270FS+1d | FS272 | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 | 1.375
272 | HELLINGSBETON DAK enkel boven kokers | 1.8.16.5 | 271FS |  | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 | 1.375
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 1.8.16.6 | 265FS+4w |  | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 | 5.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Kitchen Tower Anderlecht | 2664h |  |  |  |  | 99 | 100 | 101
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2664h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | UITZETTEN HOOFDASSEN | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | AFGRAVEN TEELAARDE | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | AANLEGGEN RIOLERING EN WERFWEG | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2440h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 1608h |  |  |  |  | 99 | 100 | 101
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | BETON EN WAPENING PREFABTRAPPEN | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | RUWBOUW BETONWERKEN $$ | 2584h |  |  |  |  | 99 | 100 | 101
19 | BETON KELDER | 1456h |  |  |  |  | 99 | 100 | 101
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | INSTALLATIE BEMALING BOUWPUT | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | BEMALING | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | UITGRAVING KELDER EN ZOLEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | ZUIVERHEIDSBETON | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | AFSCHIETEN PAALKOPPEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | WAPENING FUNDERINGSPLAAT KELDER | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | RIOLERING IN FUNDERINGSPLAAT | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | BETON KELDERWANDEN | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | WATERDICHTE ROK OP KELDERWANDEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | AANVULLING KELDER | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | BETON BORDES KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | PREFABBETON KOKERWANDEN | 1360h |  |  |  |  | 99 | 100 | 101
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | PRODUCTIE DEUVELKOPPELPLATEN | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 1240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | BETON GELIJKVLOERS | 112h |  |  |  |  | 99 | 100 | 101
44 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | BETON VLOERPLATEN ( grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | BETON EERSTE VERDIEPING | 112h |  |  |  |  | 99 | 100 | 101
60 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | BETON TWEEDE VERDIEPING | 112h |  |  |  |  | 99 | 100 | 101
76 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | BETON DERDE VERDIEPING | 120h |  |  |  |  | 99 | 100 | 101
92 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | BETON VIERDE VERDIEPING | 128h |  |  |  |  | 99 | 100 | 101
108 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
110 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
116 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
118 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | BETON VIJFDE VERDIEPING | 112h |  |  |  |  | 99 | 100 | 101
124 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
136 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | BETON ZESDE VERDIEPING | 192h |  |  |  |  | 99 | 100 | 101
140 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
144 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
145 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
146 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
147 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
148 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
149 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
150 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
151 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
152 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
153 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
155 | BETON ZEVENDE VERDIEPING | 112h |  |  |  |  | 99 | 100 | 101
156 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
157 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
158 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
161 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
162 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
163 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
164 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
165 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
166 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
167 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
168 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
169 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
171 | BETON ACHTSTE VERDIEPING | 112h |  |  |  |  | 99 | 100 | 101
172 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
173 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
174 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
176 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
177 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
178 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
179 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
180 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
181 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
182 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
183 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
184 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
185 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
187 | BETON NEGENDE VERDIEPING | 112h |  |  |  |  | 99 | 100 | 101
188 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
189 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
190 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
192 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
193 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
194 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
195 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
196 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
197 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
198 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
199 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
200 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
201 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
203 | BETON TIENDE VERDIEPING | 112h |  |  |  |  | 99 | 100 | 101
204 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
205 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
206 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
208 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
209 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
210 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
211 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
212 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
213 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
214 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
215 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
216 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
217 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
219 | BETON ELFDE VERDIEPING | 120h |  |  |  |  | 99 | 100 | 101
220 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
221 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
222 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
224 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
225 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
226 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
227 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
228 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
229 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
230 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
231 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
232 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
233 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
235 | BETON TWAALFDE VERDIEPING | 112h |  |  |  |  | 99 | 100 | 101
236 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
237 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
238 | WANDEN KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
240 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
241 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
242 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
243 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
244 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
245 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
246 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
247 | BEKISTEN PLAAT (met tafels) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
248 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
249 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
251 | BETON DERTIENDE VERDIEPING | 120h |  |  |  |  | 99 | 100 | 101
252 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
253 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
254 | WANDEN KOKER B tot E | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
256 | BEKISTEN TUSSENBORDES KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
257 | PL. WERKVLOEREN KOKERS B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
258 | BETON DRAAGWAND KOKER A en F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
259 | BETON DRAAGWAND KOKER B tot E | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
260 | BEKISTEN PLAAT KOKER A (zwart) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
261 | BEKISTEN PLAAT KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
262 | BEKISTEN RANDBALK PLAAT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
264 | WAPENING VLOERPLATEN | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
265 | BETON VLOERPLATEN (grof vlinderen) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
267 | BETON VEERTIENDE DAKVERDIEPING | 344h |  |  |  |  | 99 | 100 | 101
268 | WANDEN KOKER A | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
269 | WANDEN KOKER F | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
270 | BETON DRAAGWAND KOKER F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
271 | BEKISTEN DAKPLAAT KOKER F | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
272 | HELLINGSBETON DAK enkel boven kokers | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2008-10-30 17:00 |  | TP Name | 30/10, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 129d | [5 empty] | 559006 |  | 25.53% |  | 539567.7653 | 933607
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 129d | 51600 | 90400 | 226d | 0 | 0 | 51600 | 90400 | 36.34% | Started | 48402.2537 | 51600 | 100 | 38.7387 | 36.338 | 100 | 38.7387 | 36.338
2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 100% | Finished | 24800 | 24800 | 100 | 100 | 100 | 100 | 100 | 100
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 107d | 60120 | 35360 | 221d | 0 | 0 | 60120 | 35360 | 32.62% | Started | 58919.5116 | 59160 | 100 | 35.082 | 32.6219 | 100 | 65.4902 | 32.6219
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 100% |  | 8 | 7
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 125d | [5 empty] | 415038 |  | 21.55% |  | 399998 | 790600
19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 125d | [5 empty] | 415038 |  | 100% |  | 399998 | 400000
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 100% | Finished | 88510 | 88510 | 100 | 100 | 100 | 100 | 100 | 100
21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 3300 | 3300 | 100 | 100 | 100 | 100 | 100 | 100
22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 100% | Finished | 79442 | 79442 | 100 | 100 | 100 | 100 | 100 | 100
23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1440 | 1440 | 100 | 100 | 100 | 100 | 100 | 100
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 100% | Finished | 4980 | 4980 | 100 | 100 | 100 | 100 | 100 | 100
27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 100% | Finished | 42880 | 42880 | 100 | 100 | 100 | 100 | 137.3134 | 100
28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 100% | Finished | 2440 | 2440 | 100 | 100 | 100 | 100 | 100 | 100
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 100% | Finished | 103030 | 103030 | 100 | 90.9091 | 100 | 100 | 99.0682 | 100
31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 100% | Finished | 21440 | 21440 | 100 | 100 | 100 | 100 | 100 | 100
32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 100% | Finished | 4160 | 4160 | 100 | 100 | 100 | 100 | 100 | 100
33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 100% | Finished | 10217 | 10217 | 100 | 100 | 100 | 100 | 100 | 100
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 100% | Finished | 7523 | 7523 | 100 | 100 | 100 | 100 | 100 | 100
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 15d | [5 empty] | 2 |  | 50% |  | 2 | 4
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 155d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 90600
92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 |  | 0 | 0 | 21200 | 1d | 0 | 0 | 0 | 21200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 |  | 0 | 0 | 6800 | 4d | 0 | 0 | 0 | 6800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 |  | 0 | 0 | 3400 | 2d | 0 | 0 | 0 | 3400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 |  | 0 | 0 | 5836 | 4d | 0 | 0 | 0 | 5836 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2008-12-31 17:00 |  | TP Name | 31/12, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 173d | [5 empty] | 678368 |  | 30.08% |  | 635769.7653 | 1178847
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 150d | 60000 | 129600 | 324d | 0 | 0 | 60000 | 129600 | 36.34% | Started | 48402.2537 | 69200 | 100 | 45.045 | 36.338 | 100 | 45.045 | 36.338
2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 100% | Finished | 24800 | 24800 | 100 | 100 | 100 | 100 | 100 | 100
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 128d | 63480 | 51840 | 324d | 0 | 0 | 63480 | 51840 | 32.62% | Started | 58919.5116 | 66200 | 100 | 41.9672 | 32.6219 | 100 | 69.1503 | 32.6219
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 100% |  | 8 | 7
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 169d | [5 empty] | 522640 |  | 26.73% |  | 496200 | 1011200
19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 169d | [5 empty] | 415040 |  | 100% |  | 400000 | 400000
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 100% | Finished | 88510 | 88510 | 100 | 100 | 100 | 100 | 100 | 100
21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 3300 | 3300 | 100 | 100 | 100 | 100 | 100 | 100
22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 100% | Finished | 79442 | 79442 | 100 | 100 | 100 | 100 | 100 | 100
23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1440 | 1440 | 100 | 100 | 100 | 100 | 100 | 100
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 100% | Finished | 4980 | 4980 | 100 | 100 | 100 | 100 | 100 | 100
27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 100% | Finished | 42880 | 42880 | 100 | 100 | 100 | 100 | 137.3134 | 100
28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 100% | Finished | 2440 | 2440 | 100 | 100 | 100 | 100 | 100 | 100
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 100% | Finished | 103030 | 103030 | 100 | 90.9091 | 100 | 100 | 99.0682 | 100
31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 100% | Finished | 21440 | 21440 | 100 | 100 | 100 | 100 | 100 | 100
32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 100% | Finished | 4160 | 4160 | 100 | 100 | 100 | 100 | 100 | 100
33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 100% | Finished | 10217 | 10217 | 100 | 100 | 100 | 100 | 100 | 100
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 100% | Finished | 7523 | 7523 | 100 | 100 | 100 | 100 | 100 | 100
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 59d | [5 empty] | 4 |  | 100% |  | 4 | 4
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 43d | 1 | 0 | 87d | 0 | 0 | 1 | 0 | 33.08% | Started | 1 | 1 | 100 | 27.7419 | 33.0769 | 100 | 100 | 33.0769
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 23d | [5 empty] | 107600 |  | 96.2% |  | 96200 | 100000
44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-05 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 11200 | 11200 | 100 | 200 | 100 | 100 | 110.7143 | 100
45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-03 08:00 | 1d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2008-12-01 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 22400 | 22400 | 100 | 50 | 100 | 100 | 116.9643 | 100
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2008-12-10 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2008-12-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-12 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-15 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2008-12-17 08:00 | 2d | 12400 | 0 | 0 | 10000 | 0 | 22400 | 0 | 100% | Finished | 13600 | 13600 | 100 | 66.6667 | 100 | 100 | 164.7059 | 100
57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 11200
140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 |  | 0 | 0 | 21200 | 1d | 0 | 0 | 0 | 21200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 |  | 0 | 0 | 6800 | 4d | 0 | 0 | 0 | 6800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 |  | 0 | 0 | 3400 | 2d | 0 | 0 | 0 | 3400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 |  | 0 | 0 | 5836 | 4d | 0 | 0 | 0 | 5836 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2009-01-31 17:00 |  | TP Name | 31/01, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 195d | [5 empty] | 800488 |  | 34.67% |  | 732773.6016 | 1352567
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 170d | 68000 | 121600 | 304d | 0 | 0 | 68000 | 121600 | 36.34% | Started | 48402.2537 | 78000 | 100 | 51.0511 | 36.338 | 100 | 51.0511 | 36.338
2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 100% | Finished | 24800 | 24800 | 100 | 100 | 100 | 100 | 100 | 100
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 150d | 67000 | 48640 | 304d | 0 | 0 | 67000 | 48640 | 33.04% | Started | 59123.3479 | 69720 | 100 | 49.1803 | 33.0396 | 100 | 72.9847 | 33.0396
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 100% |  | 8 | 7
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 191d | [5 empty] | 633240 |  | 31.94% |  | 593000 | 1172600
19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 191d | [5 empty] | 415040 |  | 100% |  | 400000 | 400000
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 100% | Finished | 88510 | 88510 | 100 | 100 | 100 | 100 | 100 | 100
21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 3300 | 3300 | 100 | 100 | 100 | 100 | 100 | 100
22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 100% | Finished | 79442 | 79442 | 100 | 100 | 100 | 100 | 100 | 100
23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1440 | 1440 | 100 | 100 | 100 | 100 | 100 | 100
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 100% | Finished | 4980 | 4980 | 100 | 100 | 100 | 100 | 100 | 100
27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 100% | Finished | 42880 | 42880 | 100 | 100 | 100 | 100 | 137.3134 | 100
28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 100% | Finished | 2440 | 2440 | 100 | 100 | 100 | 100 | 100 | 100
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 100% | Finished | 103030 | 103030 | 100 | 90.9091 | 100 | 100 | 99.0682 | 100
31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 100% | Finished | 21440 | 21440 | 100 | 100 | 100 | 100 | 100 | 100
32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 100% | Finished | 4160 | 4160 | 100 | 100 | 100 | 100 | 100 | 100
33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 100% | Finished | 10217 | 10217 | 100 | 100 | 100 | 100 | 100 | 100
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 100% | Finished | 7523 | 7523 | 100 | 100 | 100 | 100 | 100 | 100
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 81d | [5 empty] | 4 |  | 100% |  | 4 | 4
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 65d | 1 | 0 | 65d | 0 | 0 | 1 | 0 | 50% | Started | 1 | 1 | 100 | 41.9355 | 50 | 100 | 100 | 50
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 32d | [5 empty] | 111400 |  | 100% |  | 100000 | 100000
44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-05 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 11200 | 11200 | 100 | 200 | 100 | 100 | 110.7143 | 100
45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-03 08:00 | 1d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2008-12-01 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 22400 | 22400 | 100 | 50 | 100 | 100 | 116.9643 | 100
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2008-12-10 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2008-12-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-12 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-15 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2008-12-17 08:00 | 2d | 12400 | 0 | 0 | 10000 | 0 | 22400 | 0 | 100% | Finished | 13600 | 13600 | 100 | 66.6667 | 100 | 100 | 164.7059 | 100
57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-01-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 12d | [5 empty] | 106800 |  | 93% |  | 93000 | 100000
60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-15 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-01-20 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-01-21 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-01-26 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-01-30 08:00 | 1d | 11200 | 0 | 0 | 11000 | 0 | 22200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 163.2353 | 100
73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 72600
156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 4400 | 100 |  | 0 | 100 |  | 0
167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 |  | 0 | 0 | 21200 | 1d | 0 | 0 | 0 | 21200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 |  | 0 | 0 | 6800 | 4d | 0 | 0 | 0 | 6800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 |  | 0 | 0 | 3400 | 2d | 0 | 0 | 0 | 3400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 |  | 0 | 0 | 5836 | 4d | 0 | 0 | 0 | 5836 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2009-02-28 17:00 |  | TP Name | 28/02, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 215d | [5 empty] | 989288 |  | 42.19% |  | 891713.5339 | 1487368
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 190d | 76000 | 113600 | 284d | 0 | 0 | 76000 | 113600 | 40.08% | Started | 53392.406 | 86000 | 100 | 57.0571 | 40.0844 | 100 | 57.0571 | 40.0844
2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 100% | Finished | 24800 | 24800 | 100 | 100 | 100 | 100 | 100 | 100
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 170d | 70200 | 45440 | 284d | 0 | 0 | 70200 | 45440 | 37.44% | Started | 61273.1279 | 72920 | 100 | 55.7377 | 37.4449 | 100 | 76.4706 | 37.4449
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 100% |  | 8 | 8
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 211d | [5 empty] | 810840 |  | 40.12% |  | 744800 | 1296200
19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 211d | [5 empty] | 415040 |  | 100% |  | 400000 | 400000
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 100% | Finished | 88510 | 88510 | 100 | 100 | 100 | 100 | 100 | 100
21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 3300 | 3300 | 100 | 100 | 100 | 100 | 100 | 100
22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 100% | Finished | 79442 | 79442 | 100 | 100 | 100 | 100 | 100 | 100
23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1440 | 1440 | 100 | 100 | 100 | 100 | 100 | 100
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 100% | Finished | 4980 | 4980 | 100 | 100 | 100 | 100 | 100 | 100
27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 100% | Finished | 42880 | 42880 | 100 | 100 | 100 | 100 | 137.3134 | 100
28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 100% | Finished | 2440 | 2440 | 100 | 100 | 100 | 100 | 100 | 100
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 100% | Finished | 103030 | 103030 | 100 | 90.9091 | 100 | 100 | 99.0682 | 100
31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 100% | Finished | 21440 | 21440 | 100 | 100 | 100 | 100 | 100 | 100
32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 100% | Finished | 4160 | 4160 | 100 | 100 | 100 | 100 | 100 | 100
33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 100% | Finished | 10217 | 10217 | 100 | 100 | 100 | 100 | 100 | 100
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 100% | Finished | 7523 | 7523 | 100 | 100 | 100 | 100 | 100 | 100
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 101d | [5 empty] | 4 |  | 100% |  | 4 | 4
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 85d | 1 | 0 | 75d | 0 | 0 | 1 | 0 | 53.12% | Started | 1 | 1 | 100 | 54.8387 | 53.125 | 100 | 100 | 53.125
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 32d | [5 empty] | 111400 |  | 100% |  | 100000 | 100000
44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-05 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 11200 | 11200 | 100 | 200 | 100 | 100 | 110.7143 | 100
45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-03 08:00 | 1d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2008-12-01 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 22400 | 22400 | 100 | 50 | 100 | 100 | 116.9643 | 100
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2008-12-10 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2008-12-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-12 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-15 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2008-12-17 08:00 | 2d | 12400 | 0 | 0 | 10000 | 0 | 22400 | 0 | 100% | Finished | 13600 | 13600 | 100 | 66.6667 | 100 | 100 | 164.7059 | 100
57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-01-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 15d | [5 empty] | 113800 |  | 100% |  | 100000 | 100000
60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-15 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-01-20 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-01-21 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-01-26 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-01-30 08:00 | 1d | 11200 | 0 | 0 | 11000 | 0 | 22200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 163.2353 | 100
73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-04 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 115800 |  | 100% |  | 100000 | 100000
76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-12 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-02-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-02-13 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-17 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-02-19 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 4d | [5 empty] | 54800 |  | 44.8% |  | 44800 | 100000
92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 96200
172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 |  | 0 | 0 | 21200 | 1d | 0 | 0 | 0 | 21200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 |  | 0 | 0 | 6800 | 4d | 0 | 0 | 0 | 6800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 |  | 0 | 0 | 3400 | 2d | 0 | 0 | 0 | 3400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 |  | 0 | 0 | 5836 | 4d | 0 | 0 | 0 | 5836 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2009-04-30 17:00 |  | TP Name | 30/04, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 259d | [5 empty] | 1393688 |  | 57.74% |  | 1220536.7429 | 1815808
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 245d | 98000 | 72000 | 180d | 0 | 0 | 98000 | 72000 | 57.65% | Started | 76785.8857 | 103600 | 100 | 73.5736 | 57.6471 | 100 | 73.5736 | 57.6471
2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 100% | Finished | 24800 | 24800 | 100 | 100 | 100 | 100 | 100 | 100
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 170d | 70200 | 28800 | 180d | 20000 | 0 | 90200 | 28800 | 48.57% | Started | 66702.8572 | 79960 | 100 | 55.7377 | 48.5714 | 100 | 98.2571 | 48.5714
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 100% |  | 8 | 8
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 255d | [5 empty] | 1173240 |  | 56.28% |  | 1044800 | 1600000
19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 255d | [5 empty] | 415040 |  | 100% |  | 400000 | 400000
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 100% | Finished | 88510 | 88510 | 100 | 100 | 100 | 100 | 100 | 100
21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 3300 | 3300 | 100 | 100 | 100 | 100 | 100 | 100
22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 100% | Finished | 79442 | 79442 | 100 | 100 | 100 | 100 | 100 | 100
23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1440 | 1440 | 100 | 100 | 100 | 100 | 100 | 100
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 100% | Finished | 4980 | 4980 | 100 | 100 | 100 | 100 | 100 | 100
27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 100% | Finished | 42880 | 42880 | 100 | 100 | 100 | 100 | 137.3134 | 100
28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 100% | Finished | 2440 | 2440 | 100 | 100 | 100 | 100 | 100 | 100
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 100% | Finished | 103030 | 103030 | 100 | 90.9091 | 100 | 100 | 99.0682 | 100
31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 100% | Finished | 21440 | 21440 | 100 | 100 | 100 | 100 | 100 | 100
32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 100% | Finished | 4160 | 4160 | 100 | 100 | 100 | 100 | 100 | 100
33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 100% | Finished | 10217 | 10217 | 100 | 100 | 100 | 100 | 100 | 100
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 100% | Finished | 7523 | 7523 | 100 | 100 | 100 | 100 | 100 | 100
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 145d | [5 empty] | 4 |  | 100% |  | 4 | 4
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 130d | 1 | 0 | 30d | 0 | 0 | 1 | 0 | 81.25% | Started | 1 | 1 | 100 | 83.871 | 81.25 | 100 | 100 | 81.25
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 32d | [5 empty] | 111400 |  | 100% |  | 100000 | 100000
44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-05 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 11200 | 11200 | 100 | 200 | 100 | 100 | 110.7143 | 100
45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-03 08:00 | 1d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2008-12-01 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 22400 | 22400 | 100 | 50 | 100 | 100 | 116.9643 | 100
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2008-12-10 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2008-12-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-12 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-15 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2008-12-17 08:00 | 2d | 12400 | 0 | 0 | 10000 | 0 | 22400 | 0 | 100% | Finished | 13600 | 13600 | 100 | 66.6667 | 100 | 100 | 164.7059 | 100
57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-01-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 15d | [5 empty] | 113800 |  | 100% |  | 100000 | 100000
60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-15 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-01-20 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-01-21 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-01-26 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-01-30 08:00 | 1d | 11200 | 0 | 0 | 11000 | 0 | 22200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 163.2353 | 100
73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-04 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 115800 |  | 100% |  | 100000 | 100000
76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-12 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-02-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-02-13 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-17 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-02-19 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-02 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-03-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-03-18 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-19 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-23 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-31 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-02 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-03 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-07 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-04-08 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-04-10 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-04-23 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-27 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 4d | [5 empty] | 54800 |  | 44.8% |  | 44800 | 100000
140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-27 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-29 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 |  | 0 | 0 | 21200 | 1d | 0 | 0 | 0 | 21200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 |  | 0 | 0 | 6800 | 4d | 0 | 0 | 0 | 6800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 |  | 0 | 0 | 3400 | 2d | 0 | 0 | 0 | 3400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 |  | 0 | 0 | 5836 | 4d | 0 | 0 | 0 | 5836 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2009-06-30 17:00 |  | TP Name | 30/06, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 302d | [5 empty] | 1816788 |  | 73.66% |  | 1556958.9339 | 2090488
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 290d | 116000 | 54000 | 135d | 0 | 0 | 116000 | 54000 | 68.24% | Started | 90889.4143 | 120800 | 100 | 87.0871 | 68.2353 | 100 | 87.0871 | 68.2353
2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 100% | Finished | 24800 | 24800 | 100 | 100 | 100 | 100 | 100 | 100
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 260d | 84600 | 21600 | 135d | 15000 | 0 | 99600 | 21600 | 65.82% | Started | 75121.5196 | 86840 | 100 | 85.2459 | 65.8228 | 100 | 108.4967 | 65.8228
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 100% |  | 8 | 8
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 298d | [5 empty] | 1568940 |  | 73.19% |  | 1358700 | 1850600
19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 286d | [5 empty] | 415040 |  | 100% |  | 400000 | 400000
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 100% | Finished | 88510 | 88510 | 100 | 100 | 100 | 100 | 100 | 100
21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 3300 | 3300 | 100 | 100 | 100 | 100 | 100 | 100
22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 100% | Finished | 79442 | 79442 | 100 | 100 | 100 | 100 | 100 | 100
23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1440 | 1440 | 100 | 100 | 100 | 100 | 100 | 100
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 100% | Finished | 4980 | 4980 | 100 | 100 | 100 | 100 | 100 | 100
27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 100% | Finished | 42880 | 42880 | 100 | 100 | 100 | 100 | 137.3134 | 100
28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 100% | Finished | 2440 | 2440 | 100 | 100 | 100 | 100 | 100 | 100
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 100% | Finished | 103030 | 103030 | 100 | 90.9091 | 100 | 100 | 99.0682 | 100
31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 100% | Finished | 21440 | 21440 | 100 | 100 | 100 | 100 | 100 | 100
32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 100% | Finished | 4160 | 4160 | 100 | 100 | 100 | 100 | 100 | 100
33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 100% | Finished | 10217 | 10217 | 100 | 100 | 100 | 100 | 100 | 100
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 100% | Finished | 7523 | 7523 | 100 | 100 | 100 | 100 | 100 | 100
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 176d | [5 empty] | 4 |  | 100% |  | 4 | 4
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 160d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 103.2258 | 100 | 100 | 100 | 100
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 32d | [5 empty] | 111400 |  | 100% |  | 100000 | 100000
44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-05 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 11200 | 11200 | 100 | 200 | 100 | 100 | 110.7143 | 100
45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-03 08:00 | 1d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2008-12-01 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 22400 | 22400 | 100 | 50 | 100 | 100 | 116.9643 | 100
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2008-12-10 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2008-12-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-12 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-15 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2008-12-17 08:00 | 2d | 12400 | 0 | 0 | 10000 | 0 | 22400 | 0 | 100% | Finished | 13600 | 13600 | 100 | 66.6667 | 100 | 100 | 164.7059 | 100
57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-01-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 15d | [5 empty] | 113800 |  | 100% |  | 100000 | 100000
60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-15 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-01-20 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-01-21 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-01-26 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-01-30 08:00 | 1d | 11200 | 0 | 0 | 11000 | 0 | 22200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 163.2353 | 100
73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-04 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 115800 |  | 100% |  | 100000 | 100000
76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-12 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-02-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-02-13 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-17 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-02-19 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-02 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-03-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-03-18 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-19 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-23 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-31 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-02 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-03 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-07 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-04-08 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-04-10 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-04-23 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-27 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-27 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-29 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-01 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-05 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-05-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-12 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-13 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-05-14 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-15 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-19 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-19 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-25 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-27 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-08 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-09 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-06-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-06-17 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-22 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 27d | [5 empty] | 73700 |  | 58.7% |  | 58700 | 100000
188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-29 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 100000
220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 98800
236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 |  | 0 | 0 | 21200 | 1d | 0 | 0 | 0 | 21200 | 0% | Not Started | 0 | 21200 | 100 |  | 0 | 100 |  | 0
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 101200
252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 |  | 0 | 0 | 6800 | 4d | 0 | 0 | 0 | 6800 | 0% | Not Started | 0 | 6800 | 100 |  | 0 | 100 |  | 0
264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 50600
268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 12400 | 100 |  | 0 | 100 |  | 0
271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 |  | 0 | 0 | 3400 | 2d | 0 | 0 | 0 | 3400 | 0% | Not Started | 0 | 3400 | 100 |  | 0 | 100 |  | 0
272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 12400 | 100 |  | 0 | 100 |  | 0
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 |  | 0 | 0 | 5836 | 4d | 0 | 0 | 0 | 5836 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2009-09-30 17:00 |  | TP Name | 30/09, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 368d | [5 empty] | 2198088 |  | 88.48% |  | 1870261.0751 | 2113684
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 355d | 142000 | 28000 | 70d | 0 | 0 | 142000 | 28000 | 83.53% | Started | 111261.1778 | 133200 | 100 | 106.6066 | 83.5294 | 100 | 106.6066 | 83.5294
2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 100% | Finished | 24800 | 24800 | 100 | 100 | 100 | 100 | 100 | 100
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 325d | 95000 | 11200 | 70d | 12000 | 0 | 107000 | 11200 | 82.28% | Started | 83151.8973 | 91800 | 100 | 106.5574 | 82.2785 | 100 | 116.5577 | 82.2785
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 100% |  | 8 | 8
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 364d | [5 empty] | 1916840 |  | 88.54% |  | 1643600 | 1856436
19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 286d | [5 empty] | 415040 |  | 100% |  | 400000 | 400000
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 100% | Finished | 88510 | 88510 | 100 | 100 | 100 | 100 | 100 | 100
21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 3300 | 3300 | 100 | 100 | 100 | 100 | 100 | 100
22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 100% | Finished | 79442 | 79442 | 100 | 100 | 100 | 100 | 100 | 100
23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1440 | 1440 | 100 | 100 | 100 | 100 | 100 | 100
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 100% | Finished | 4980 | 4980 | 100 | 100 | 100 | 100 | 100 | 100
27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 100% | Finished | 42880 | 42880 | 100 | 100 | 100 | 100 | 137.3134 | 100
28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 100% | Finished | 2440 | 2440 | 100 | 100 | 100 | 100 | 100 | 100
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 100% | Finished | 103030 | 103030 | 100 | 90.9091 | 100 | 100 | 99.0682 | 100
31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 100% | Finished | 21440 | 21440 | 100 | 100 | 100 | 100 | 100 | 100
32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 100% | Finished | 4160 | 4160 | 100 | 100 | 100 | 100 | 100 | 100
33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 100% | Finished | 10217 | 10217 | 100 | 100 | 100 | 100 | 100 | 100
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 100% | Finished | 7523 | 7523 | 100 | 100 | 100 | 100 | 100 | 100
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 176d | [5 empty] | 4 |  | 100% |  | 4 | 4
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 160d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 103.2258 | 100 | 100 | 100 | 100
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 32d | [5 empty] | 111400 |  | 100% |  | 100000 | 100000
44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-05 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 11200 | 11200 | 100 | 200 | 100 | 100 | 110.7143 | 100
45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-03 08:00 | 1d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2008-12-01 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 22400 | 22400 | 100 | 50 | 100 | 100 | 116.9643 | 100
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2008-12-10 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2008-12-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-12 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-15 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2008-12-17 08:00 | 2d | 12400 | 0 | 0 | 10000 | 0 | 22400 | 0 | 100% | Finished | 13600 | 13600 | 100 | 66.6667 | 100 | 100 | 164.7059 | 100
57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-01-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 15d | [5 empty] | 113800 |  | 100% |  | 100000 | 100000
60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-15 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-01-20 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-01-21 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-01-26 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-01-30 08:00 | 1d | 11200 | 0 | 0 | 11000 | 0 | 22200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 163.2353 | 100
73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-04 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 115800 |  | 100% |  | 100000 | 100000
76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-12 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-02-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-02-13 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-17 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-02-19 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-02 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-03-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-03-18 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-19 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-23 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-31 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-02 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-03 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-07 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-04-08 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-04-10 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-04-23 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-27 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-27 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-29 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-01 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-05 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-05-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-12 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-13 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-05-14 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-15 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-19 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-19 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-25 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-27 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-08 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-09 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-06-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-06-17 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-22 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 51d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-29 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-07-01 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-01 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-03 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-07-07 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-08-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 25d | [5 empty] | 120000 |  | 100% |  | 100000 | 100000
204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-08-06 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-08-07 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-08-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-13 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-08-18 08:00 | 3d | 13600 | 0 | 0 | 10000 | 0 | 23600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 173.5294 | 100
217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-07 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120000 |  | 100% |  | 100000 | 100000
220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-08 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-09 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-09-10 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-09-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-09-15 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-17 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-09-21 08:00 | 3d | 13600 | 0 | 0 | 10000 | 0 | 23600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 173.5294 | 100
233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-25 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 3d | [5 empty] | 53600 |  | 44.13% |  | 43600 | 98800
236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-29 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 | 2009-09-30 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 21200 | 21200 | 100 | 100 | 100 | 100 | 123.5849 | 100
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 101200
252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 |  | 0 | 0 | 22400 | 2d | 0 | 0 | 0 | 22400 | 0% | Not Started | 0 | 22400 | 100 |  | 0 | 100 |  | 0
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 |  | 0 | 0 | 4300 | 2d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 |  | 0 | 0 | 3100 | 1d | 0 | 0 | 0 | 3100 | 0% | Not Started | 0 | 3100 | 100 |  | 0 | 100 |  | 0
260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 |  | 0 | 0 | 5600 | 3d | 0 | 0 | 0 | 5600 | 0% | Not Started | 0 | 5600 | 100 |  | 0 | 100 |  | 0
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 |  | 0 | 0 | 6800 | 4d | 0 | 0 | 0 | 6800 | 0% | Not Started | 0 | 6800 | 100 |  | 0 | 100 |  | 0
264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 56436
268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 12400 | 100 |  | 0 | 100 |  | 0
271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 |  | 0 | 0 | 3400 | 2d | 0 | 0 | 0 | 3400 | 0% | Not Started | 0 | 3400 | 100 |  | 0 | 100 |  | 0
272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 12400 | 100 |  | 0 | 100 |  | 0
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 |  | 0 | 0 | 5836 | 4d | 0 | 0 | 0 | 5836 | 0% | Not Started | 0 | 5836 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2009-10-31 17:00 |  | TP Name | 31/10, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 390d | [5 empty] | 2376488 |  | 95.31% |  | 2014584.9789 | 2113684
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 380d | 152000 | 18000 | 45d | 0 | 0 | 152000 | 18000 | 89.41% | Started | 119096.4714 | 133200 | 100 | 114.1141 | 89.4118 | 100 | 114.1141 | 89.4118
2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 100% | Finished | 24800 | 24800 | 100 | 100 | 100 | 100 | 100 | 100
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 350d | 99000 | 7200 | 45d | 12000 | 0 | 111000 | 7200 | 88.61% | Started | 86240.5075 | 91800 | 100 | 114.7541 | 88.6076 | 100 | 120.915 | 88.6076
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 100% |  | 8 | 8
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 386d | [5 empty] | 2081240 |  | 95.72% |  | 1777000 | 1856436
19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 286d | [5 empty] | 415040 |  | 100% |  | 400000 | 400000
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 100% | Finished | 88510 | 88510 | 100 | 100 | 100 | 100 | 100 | 100
21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 3300 | 3300 | 100 | 100 | 100 | 100 | 100 | 100
22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 100% | Finished | 79442 | 79442 | 100 | 100 | 100 | 100 | 100 | 100
23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1440 | 1440 | 100 | 100 | 100 | 100 | 100 | 100
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 100% | Finished | 4980 | 4980 | 100 | 100 | 100 | 100 | 100 | 100
27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 100% | Finished | 42880 | 42880 | 100 | 100 | 100 | 100 | 137.3134 | 100
28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 100% | Finished | 2440 | 2440 | 100 | 100 | 100 | 100 | 100 | 100
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 100% | Finished | 103030 | 103030 | 100 | 90.9091 | 100 | 100 | 99.0682 | 100
31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 100% | Finished | 21440 | 21440 | 100 | 100 | 100 | 100 | 100 | 100
32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 100% | Finished | 4160 | 4160 | 100 | 100 | 100 | 100 | 100 | 100
33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 100% | Finished | 10217 | 10217 | 100 | 100 | 100 | 100 | 100 | 100
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 100% | Finished | 7523 | 7523 | 100 | 100 | 100 | 100 | 100 | 100
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 176d | [5 empty] | 4 |  | 100% |  | 4 | 4
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 160d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 103.2258 | 100 | 100 | 100 | 100
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 32d | [5 empty] | 111400 |  | 100% |  | 100000 | 100000
44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-05 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 11200 | 11200 | 100 | 200 | 100 | 100 | 110.7143 | 100
45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-03 08:00 | 1d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2008-12-01 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 22400 | 22400 | 100 | 50 | 100 | 100 | 116.9643 | 100
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2008-12-10 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2008-12-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-12 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-15 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2008-12-17 08:00 | 2d | 12400 | 0 | 0 | 10000 | 0 | 22400 | 0 | 100% | Finished | 13600 | 13600 | 100 | 66.6667 | 100 | 100 | 164.7059 | 100
57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-01-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 15d | [5 empty] | 113800 |  | 100% |  | 100000 | 100000
60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-15 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-01-20 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-01-21 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-01-26 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-01-30 08:00 | 1d | 11200 | 0 | 0 | 11000 | 0 | 22200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 163.2353 | 100
73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-04 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 115800 |  | 100% |  | 100000 | 100000
76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-12 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-02-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-02-13 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-17 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-02-19 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-02 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-03-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-03-18 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-19 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-23 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-31 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-02 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-03 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-07 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-04-08 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-04-10 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-04-23 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-27 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-27 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-29 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-01 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-05 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-05-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-12 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-13 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-05-14 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-15 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-19 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-19 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-25 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-27 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-08 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-09 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-06-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-06-17 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-22 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 51d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-29 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-07-01 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-01 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-03 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-07-07 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-08-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 25d | [5 empty] | 120000 |  | 100% |  | 100000 | 100000
204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-08-06 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-08-07 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-08-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-13 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-08-18 08:00 | 3d | 13600 | 0 | 0 | 10000 | 0 | 23600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 173.5294 | 100
217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-07 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 123000 |  | 100% |  | 100000 | 100000
220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-08 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-09 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-09-10 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-09-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-09-15 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-17 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-09-21 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-25 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 16d | [5 empty] | 121800 |  | 100% |  | 98800 | 98800
236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-29 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 | 2009-09-30 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 21200 | 21200 | 100 | 100 | 100 | 100 | 123.5849 | 100
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-10-01 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-10-02 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-08 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-07 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-09 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-10-13 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-10-19 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 9d | [5 empty] | 93200 |  | 77.27% |  | 78200 | 101200
252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-10-20 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-10-21 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-10-22 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-10-23 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-10-27 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-27 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 | 2009-10-29 08:00 | 2d | 4400 | 2400 | 2d | 5000 | 0 | 9400 | 2400 | 50% | Started | 4400 | 6800 | 100 | 50 | 50 | 100 | 138.2353 | 50
264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 |  | 0 | 0 | 13600 | 3d | 0 | 0 | 0 | 13600 | 0% | Not Started | 0 | 13600 | 100 |  | 0 | 100 |  | 0
265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 |  | 0 | 0 | 3200 | 1d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200 | 100 |  | 0 | 100 |  | 0
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 |  | 0 | 0 | 3800 | 1d | 0 | 0 | 0 | 3800 | 0% | Not Started | 0 | 3800 | 100 |  | 0 | 100 |  | 0
267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 56436
268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 |  | 0 | 0 | 11200 | 1d | 0 | 0 | 0 | 11200 | 0% | Not Started | 0 | 11200 | 100 |  | 0 | 100 |  | 0
270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 12400 | 100 |  | 0 | 100 |  | 0
271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 |  | 0 | 0 | 3400 | 2d | 0 | 0 | 0 | 3400 | 0% | Not Started | 0 | 3400 | 100 |  | 0 | 100 |  | 0
272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 12400 | 100 |  | 0 | 100 |  | 0
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 |  | 0 | 0 | 5836 | 4d | 0 | 0 | 0 | 5836 | 0% | Not Started | 0 | 5836 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2009-11-30 17:00 |  | TP Name | 30/11, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 411d | [5 empty] | 2460488 |  | 98.09% |  | 2073286.7746 | 2113684
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 400d | 160000 | 18000 | 45d | 5000 | 0 | 165000 | 18000 | 89.89% | Started | 119730.3403 | 133200 | 100 | 120.1201 | 89.8876 | 100 | 123.8739 | 89.8876
2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 100% | Finished | 24800 | 24800 | 100 | 100 | 100 | 100 | 100 | 100
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 370d | 102200 | 7200 | 45d | 12000 | 0 | 114200 | 7200 | 89.16% | Started | 86508.4343 | 91800 | 100 | 121.3115 | 89.1566 | 100 | 124.4009 | 89.1566
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 100% |  | 8 | 8
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 407d | [5 empty] | 2149040 |  | 98.83% |  | 1834800 | 1856436
19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 286d | [5 empty] | 415040 |  | 100% |  | 400000 | 400000
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 100% | Finished | 88510 | 88510 | 100 | 100 | 100 | 100 | 100 | 100
21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 3300 | 3300 | 100 | 100 | 100 | 100 | 100 | 100
22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 100% | Finished | 79442 | 79442 | 100 | 100 | 100 | 100 | 100 | 100
23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1440 | 1440 | 100 | 100 | 100 | 100 | 100 | 100
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 100% | Finished | 4980 | 4980 | 100 | 100 | 100 | 100 | 100 | 100
27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 100% | Finished | 42880 | 42880 | 100 | 100 | 100 | 100 | 137.3134 | 100
28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 100% | Finished | 2440 | 2440 | 100 | 100 | 100 | 100 | 100 | 100
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 100% | Finished | 103030 | 103030 | 100 | 90.9091 | 100 | 100 | 99.0682 | 100
31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 100% | Finished | 21440 | 21440 | 100 | 100 | 100 | 100 | 100 | 100
32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 100% | Finished | 4160 | 4160 | 100 | 100 | 100 | 100 | 100 | 100
33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 100% | Finished | 10217 | 10217 | 100 | 100 | 100 | 100 | 100 | 100
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 100% | Finished | 7523 | 7523 | 100 | 100 | 100 | 100 | 100 | 100
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 176d | [5 empty] | 4 |  | 100% |  | 4 | 4
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 160d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 103.2258 | 100 | 100 | 100 | 100
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 32d | [5 empty] | 111400 |  | 100% |  | 100000 | 100000
44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-05 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 11200 | 11200 | 100 | 200 | 100 | 100 | 110.7143 | 100
45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-03 08:00 | 1d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2008-12-01 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 22400 | 22400 | 100 | 50 | 100 | 100 | 116.9643 | 100
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2008-12-10 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2008-12-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-12 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-15 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2008-12-17 08:00 | 2d | 12400 | 0 | 0 | 10000 | 0 | 22400 | 0 | 100% | Finished | 13600 | 13600 | 100 | 66.6667 | 100 | 100 | 164.7059 | 100
57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-01-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 15d | [5 empty] | 113800 |  | 100% |  | 100000 | 100000
60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-15 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-01-20 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-01-21 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-01-26 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-01-30 08:00 | 1d | 11200 | 0 | 0 | 11000 | 0 | 22200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 163.2353 | 100
73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-04 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 115800 |  | 100% |  | 100000 | 100000
76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-12 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-02-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-02-13 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-17 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-02-19 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-02 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-03-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-03-18 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-19 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-23 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-31 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-02 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-03 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-07 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-04-08 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-04-10 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-04-23 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-27 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-27 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-29 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-01 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-05 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-05-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-12 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-13 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-05-14 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-15 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-19 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-19 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-25 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-27 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-08 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-09 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-06-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-06-17 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-22 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 51d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-29 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-07-01 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-01 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-03 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-07-07 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-08-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 25d | [5 empty] | 120000 |  | 100% |  | 100000 | 100000
204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-08-06 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-08-07 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-08-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-13 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-08-18 08:00 | 3d | 13600 | 0 | 0 | 10000 | 0 | 23600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 173.5294 | 100
217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-07 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 123000 |  | 100% |  | 100000 | 100000
220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-08 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-09 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-09-10 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-09-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-09-15 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-17 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-09-21 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-25 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 16d | [5 empty] | 121800 |  | 100% |  | 98800 | 98800
236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-29 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 | 2009-09-30 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 21200 | 21200 | 100 | 100 | 100 | 100 | 123.5849 | 100
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-10-01 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-10-02 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-08 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-07 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-09 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-10-13 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-10-19 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 18d | [5 empty] | 116200 |  | 100% |  | 101200 | 101200
252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-10-20 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-10-21 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-10-22 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-10-23 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-10-27 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-27 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 | 2009-10-29 08:00 | 4d | 6800 | 0 | 0 | 5000 | 0 | 11800 | 0 | 100% | Finished | 6800 | 6800 | 100 | 100 | 100 | 100 | 173.5294 | 100
264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-11-04 08:00 | 3d | 13600 | 0 | 0 | 0 | 0 | 13600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 100 | 100
265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-11-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-11-12 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 11d | [5 empty] | 44800 |  | 61.66% |  | 34800 | 56436
268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-11-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-11-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 | 2009-11-19 08:00 | 2d | 12400 | 0 | 0 | 5000 | 0 | 17400 | 0 | 100% | Finished | 12400 | 12400 | 100 | 100 | 100 | 100 | 140.3226 | 100
271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 |  | 0 | 0 | 3400 | 2d | 0 | 0 | 0 | 3400 | 0% | Not Started | 0 | 3400 | 100 |  | 0 | 100 |  | 0
272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 |  | 0 | 0 | 12400 | 2d | 0 | 0 | 0 | 12400 | 0% | Not Started | 0 | 12400 | 100 |  | 0 | 100 |  | 0
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 |  | 0 | 0 | 5836 | 4d | 0 | 0 | 0 | 5836 | 0% | Not Started | 0 | 5836 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2009-12-31 17:00 |  | TP Name | 31/12, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 434d | [5 empty] | 2490288 |  | 99.33% |  | 2099509.676 | 2113684
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 425d | 170000 | 8000 | 20d | 5000 | 0 | 175000 | 8000 | 95.51% | Started | 127213.4846 | 133200 | 100 | 127.6276 | 95.5056 | 100 | 131.3814 | 95.5056
2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 100% | Finished | 24800 | 24800 | 100 | 100 | 100 | 100 | 100 | 100
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 395d | 106200 | 3200 | 20d | 12000 | 0 | 118200 | 3200 | 95.18% | Started | 89448.1914 | 91800 | 100 | 129.5082 | 95.1807 | 100 | 128.7582 | 95.1807
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 100% |  | 8 | 8
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 430d | [5 empty] | 2164840 |  | 99.69% |  | 1850600 | 1856436
19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 286d | [5 empty] | 415040 |  | 100% |  | 400000 | 400000
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 100% | Finished | 88510 | 88510 | 100 | 100 | 100 | 100 | 100 | 100
21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 3300 | 3300 | 100 | 100 | 100 | 100 | 100 | 100
22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 100% | Finished | 79442 | 79442 | 100 | 100 | 100 | 100 | 100 | 100
23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1440 | 1440 | 100 | 100 | 100 | 100 | 100 | 100
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 100% | Finished | 4980 | 4980 | 100 | 100 | 100 | 100 | 100 | 100
27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 100% | Finished | 42880 | 42880 | 100 | 100 | 100 | 100 | 137.3134 | 100
28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 100% | Finished | 2440 | 2440 | 100 | 100 | 100 | 100 | 100 | 100
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 100% | Finished | 103030 | 103030 | 100 | 90.9091 | 100 | 100 | 99.0682 | 100
31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 100% | Finished | 21440 | 21440 | 100 | 100 | 100 | 100 | 100 | 100
32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 100% | Finished | 4160 | 4160 | 100 | 100 | 100 | 100 | 100 | 100
33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 100% | Finished | 10217 | 10217 | 100 | 100 | 100 | 100 | 100 | 100
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 100% | Finished | 7523 | 7523 | 100 | 100 | 100 | 100 | 100 | 100
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 176d | [5 empty] | 4 |  | 100% |  | 4 | 4
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 160d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 103.2258 | 100 | 100 | 100 | 100
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 32d | [5 empty] | 111400 |  | 100% |  | 100000 | 100000
44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-05 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 11200 | 11200 | 100 | 200 | 100 | 100 | 110.7143 | 100
45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-03 08:00 | 1d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2008-12-01 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 22400 | 22400 | 100 | 50 | 100 | 100 | 116.9643 | 100
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2008-12-10 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2008-12-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-12 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-15 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2008-12-17 08:00 | 2d | 12400 | 0 | 0 | 10000 | 0 | 22400 | 0 | 100% | Finished | 13600 | 13600 | 100 | 66.6667 | 100 | 100 | 164.7059 | 100
57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-01-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 15d | [5 empty] | 113800 |  | 100% |  | 100000 | 100000
60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-15 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-01-20 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-01-21 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-01-26 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-01-30 08:00 | 1d | 11200 | 0 | 0 | 11000 | 0 | 22200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 163.2353 | 100
73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-04 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 115800 |  | 100% |  | 100000 | 100000
76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-12 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-02-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-02-13 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-17 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-02-19 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-02 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-03-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-03-18 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-19 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-23 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-31 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-02 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-03 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-07 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-04-08 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-04-10 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-04-23 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-27 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-27 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-29 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-01 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-05 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-05-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-12 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-13 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-05-14 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-15 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-19 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-19 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-25 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-27 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-08 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-09 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-06-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-06-17 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-22 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 51d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-29 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-07-01 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-01 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-03 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-07-07 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-08-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 25d | [5 empty] | 120000 |  | 100% |  | 100000 | 100000
204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-08-06 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-08-07 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-08-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-13 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-08-18 08:00 | 3d | 13600 | 0 | 0 | 10000 | 0 | 23600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 173.5294 | 100
217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-07 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 123000 |  | 100% |  | 100000 | 100000
220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-08 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-09 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-09-10 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-09-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-09-15 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-17 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-09-21 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-25 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 16d | [5 empty] | 121800 |  | 100% |  | 98800 | 98800
236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-29 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 | 2009-09-30 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 21200 | 21200 | 100 | 100 | 100 | 100 | 123.5849 | 100
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-10-01 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-10-02 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-08 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-07 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-09 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-10-13 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-10-19 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 18d | [5 empty] | 116200 |  | 100% |  | 101200 | 101200
252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-10-20 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-10-21 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-10-22 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-10-23 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-10-27 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-27 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 | 2009-10-29 08:00 | 4d | 6800 | 0 | 0 | 5000 | 0 | 11800 | 0 | 100% | Finished | 6800 | 6800 | 100 | 100 | 100 | 100 | 173.5294 | 100
264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-11-04 08:00 | 3d | 13600 | 0 | 0 | 0 | 0 | 13600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 100 | 100
265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-11-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-11-12 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 34d | [5 empty] | 60600 |  | 89.66% |  | 50600 | 56436
268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-11-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-11-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 | 2009-11-19 08:00 | 2d | 12400 | 0 | 0 | 5000 | 0 | 17400 | 0 | 100% | Finished | 12400 | 12400 | 100 | 100 | 100 | 100 | 140.3226 | 100
271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 | 2009-12-01 08:00 | 2d | 3400 | 0 | 0 | 0 | 0 | 3400 | 0 | 100% | Finished | 3400 | 3400 | 100 | 100 | 100 | 100 | 100 | 100
272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 | 2009-12-07 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 12400 | 12400 | 100 | 100 | 100 | 100 | 100 | 100
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 |  | 0 | 0 | 5836 | 4d | 0 | 0 | 0 | 5836 | 0% | Not Started | 0 | 5836 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2010-01-27 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Kitchen Tower Anderlecht | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  |  | 1448084 |  |  | 2113684 |  | 453d | [5 empty] | 2512524 |  | 100% |  | 2113684 | 2113684
1 | KEUKENTOREN IN WERKDAGEN (ADMIN BEDIENDEN) | 2008-05-05 08:00 | 2009-08-12 17:00 | 333d |  | 0 | 0 | 50 | 133200 | 133200 | 2008-05-05 08:00 | 445d | 178000 | 0 | 0 | 5000 | 0 | 183000 | 0 | 100% | Finished | 133200 | 133200 | 100 | 133.6336 | 100 | 100 | 137.3874 | 100
2 | UITZETTEN HOOFDASSEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 0 | 30 | 240 | 240 | 2008-05-05 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
3 | AFGRAVEN TEELAARDE | 2008-05-06 08:00 | 2008-05-09 17:00 | 4d |  | 0 | 0 | 150 | 4800 | 4800 | 2008-05-05 08:00 | 4d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
4 | AANLEGGEN RIOLERING EN WERFWEG | 2008-05-13 08:00 | 2008-05-16 17:00 | 4d |  | 0 | 20000 | 150 | 4800 | 24800 | 2008-05-05 08:00 | 4d | 24800 | 0 | 0 | 0 | 0 | 24800 | 0 | 100% | Finished | 24800 | 24800 | 100 | 100 | 100 | 100 | 100 | 100
5 | WERFINRICHTING EN ELEKTR. AANSLUITING | 2008-05-19 08:00 | 2008-05-23 17:00 | 5d |  | 0 | 0 | 60 | 2400 | 2400 | 2008-05-05 08:00 | 5d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
6 | INSTALLATIE SNELOPBOUWKRAAN/TORENKRAAN/WERFLIFT | 2008-06-12 08:00 | 2009-08-12 17:00 | 305d |  | 0 | 43000 | 20 | 48800 | 91800 | 2008-06-05 08:00 | 410d | 108600 | 0 | 0 | 12000 | 0 | 120600 | 0 | 100% | Finished | 91800 | 91800 | 100 | 134.4262 | 100 | 100 | 131.3725 | 100
9 | TE ONTVANGEN PLANNEN GOED VOOR UITVOERING: $ | 2008-05-05 08:00 | 2009-02-09 17:00 | 201d |  |  | 8 |  |  | 8 |  | 80d | [5 empty] | 8 |  | 100% |  | 8 | 8
10 | AANGEPASTE PLANNEN UITSPARINGEN VOOR TECHNIEKEN (coördinatie studie) | 2008-05-05 08:00 | 2008-05-09 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
11 | BETON EN WAPENING WANDEN KOKERS A tot F | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-22 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
12 | BETON EN WAPENING PREFABTRAPPEN | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-08-08 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | BETON EN WAPENING FUNDERINGSZOLEN EN PLATEN + WACHTSTAVEN WANDEN | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-07-11 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
14 | BETON EN WAPENING KELDER WANDEN + PLAAT BOVEN KELDER | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-23 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
15 | BETON EN WAPENING PLAAT BOVEN GLVL , +1 ,+2, +3, +4 | 2008-07-04 08:00 | 2008-07-04 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
16 | BETON EN WAPENING PLAAT BOVEN GLVL , +5 ,+6, +7, +8 | 2008-10-14 08:00 | 2008-10-14 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
17 | BETON EN WAPENING PLAAT BOVEN GLVL , +9 ,+10, +11, +12, +13 , DAKPLAN | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-30 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
18 | RUWBOUW BETONWERKEN $$ | 2008-05-19 08:00 | 2009-08-12 17:00 | 323d |  |  | 1385076 |  |  | 1856436 |  | 449d | [5 empty] | 2176676 |  | 100% |  | 1856436 | 1856436
19 | BETON KELDER | 2008-05-19 08:00 | 2009-01-27 17:00 | 182d |  |  | 329440 |  |  | 400000 |  | 286d | [5 empty] | 415040 |  | 100% |  | 400000 | 400000
20 | BOREN SCHROEFPALEN GEBOUW + KRAANSOKKEL | 2008-05-19 08:00 | 2008-05-27 17:00 | 7d |  | 0 | 88510 | 0 | 0 | 88510 | 2008-05-09 08:00 | 7d | 88510 | 0 | 0 | 0 | 0 | 88510 | 0 | 100% | Finished | 88510 | 88510 | 100 | 100 | 100 | 100 | 100 | 100
21 | INSTALLATIE BEMALING BOUWPUT | 2008-05-28 08:00 | 2008-05-29 17:00 | 2d |  | 0 | 3300 | 0 | 0 | 3300 | 2008-05-21 08:00 | 2d | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 3300 | 3300 | 100 | 100 | 100 | 100 | 100 | 100
22 | BEMALING | 2008-05-30 08:00 | 2008-07-24 17:00 | 40d |  | 0 | 50642 | 90 | 28800 | 79442 | 2008-05-23 08:00 | 40d | 79442 | 0 | 0 | 0 | 0 | 79442 | 0 | 100% | Finished | 79442 | 79442 | 100 | 100 | 100 | 100 | 100 | 100
23 | UITGRAVING KELDER EN ZOLEN | 2008-06-06 08:00 | 2008-06-10 17:00 | 3d |  | 0 | 0 | 150 | 3600 | 3600 | 2008-06-02 08:00 | 3d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZUIVERHEIDSBETON | 2008-06-11 08:00 | 2008-06-11 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-09 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
25 | AFSCHIETEN PAALKOPPEN | 2008-06-16 08:00 | 2008-06-18 17:00 | 3d |  | 0 | 0 | 60 | 1440 | 1440 | 2008-06-13 08:00 | 3d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1440 | 1440 | 100 | 100 | 100 | 100 | 100 | 100
26 | BEKISTEN FUNDERINGSPLAAT KELDER + WATERKEERPLATEN | 2008-06-19 08:00 | 2008-06-24 17:00 | 4d |  | 0 | 180 | 150 | 4800 | 4980 | 2008-06-18 08:00 | 4d | 4980 | 0 | 0 | 0 | 0 | 4980 | 0 | 100% | Finished | 4980 | 4980 | 100 | 100 | 100 | 100 | 100 | 100
27 | WAPENING FUNDERINGSPLAAT KELDER | 2008-06-24 08:00 | 2008-06-26 17:00 | 3d |  | 0 | 40000 | 120 | 2880 | 42880 | 2008-06-24 08:00 | 3d | 42880 | 0 | 0 | 16000 | 0 | 58880 | 0 | 100% | Finished | 42880 | 42880 | 100 | 100 | 100 | 100 | 137.3134 | 100
28 | RIOLERING IN FUNDERINGSPLAAT | 2008-06-25 08:00 | 2008-06-26 17:00 | 2d |  | 0 | 1000 | 90 | 1440 | 2440 | 2008-06-25 08:00 | 2d | 2440 | 0 | 0 | 0 | 0 | 2440 | 0 | 100% | Finished | 2440 | 2440 | 100 | 100 | 100 | 100 | 100 | 100
29 | BETON FUNDERINGSPLAAT KELDER te vlinderen | 2008-06-27 08:00 | 2008-06-27 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-06-27 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
30 | BETON KELDERWANDEN | 2008-07-01 08:00 | 2008-07-15 17:00 | 11d |  | 0 | 92470 | 120 | 10560 | 103030 | 2008-07-01 08:00 | 10d | 102070 | 0 | 0 | 0 | 0 | 102070 | 0 | 100% | Finished | 103030 | 103030 | 100 | 90.9091 | 100 | 100 | 99.0682 | 100
31 | WATERDICHTE ROK OP KELDERWANDEN | 2008-08-06 08:00 | 2008-08-08 17:00 | 3d |  | 0 | 20000 | 60 | 1440 | 21440 | 2008-08-08 08:00 | 3d | 21440 | 0 | 0 | 0 | 0 | 21440 | 0 | 100% | Finished | 21440 | 21440 | 100 | 100 | 100 | 100 | 100 | 100
32 | AANVULLING KELDER | 2008-08-14 08:00 | 2008-08-18 17:00 | 3d |  | 0 | 2000 | 90 | 2160 | 4160 | 2008-08-21 08:00 | 3d | 4160 | 0 | 0 | 0 | 0 | 4160 | 0 | 100% | Finished | 4160 | 4160 | 100 | 100 | 100 | 100 | 100 | 100
33 | BETON BORDES KOKER A | 2008-08-06 08:00 | 2008-08-06 17:00 | 1d |  | 0 | 3800 | 120 | 960 | 4760 | 2008-08-08 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 4760 | 4760 | 100 | 100 | 100 | 100 | 100 | 100
34 | ZUIVERHEIDSBETON PLATEN EN ZOOL GLVL | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-26 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
35 | BEKISTEN PLATEN EN ZOOL BOVEN KELDER+RIOLERINGSBUIZEN IN ZOOL | 2008-08-06 08:00 | 2008-08-12 17:00 | 5d |  | 0 | 5417 | 120 | 4800 | 10217 | 2008-08-08 08:00 | 5d | 10217 | 0 | 0 | 0 | 0 | 10217 | 0 | 100% | Finished | 10217 | 10217 | 100 | 100 | 100 | 100 | 100 | 100
36 | WAPENING PLATEN EN ZOOL BOVEN KELDER | 2008-08-11 08:00 | 2008-08-14 17:00 | 4d |  | 0 | 3683 | 120 | 3840 | 7523 | 2008-08-18 08:00 | 4d | 7523 | 0 | 0 | 0 | 0 | 7523 | 0 | 100% | Finished | 7523 | 7523 | 100 | 100 | 100 | 100 | 100 | 100
37 | BETON PLATEN EN ZOOL BOVEN KELDER | 2008-08-18 08:00 | 2008-08-18 17:00 | 1d |  | 0 | 5417 | 120 | 960 | 6377 | 2008-08-22 08:00 | 1d | 6377 | 0 | 0 | 0 | 0 | 6377 | 0 | 100% | Finished | 6377 | 6377 | 100 | 100 | 100 | 100 | 100 | 100
38 | PREFABBETON KOKERWANDEN | 2008-06-04 08:00 | 2009-01-27 17:00 | 170d |  |  | 4 |  |  | 4 |  | 176d | [5 empty] | 4 |  | 100% |  | 4 | 4
39 | STUDIE EN PLANNEN VOORLEGGEN + VOORLEGGEN STALEN IN GETINTE BETON | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-10 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
40 | PRODUCTIE DEUVELKOPPELPLATEN | 2008-06-04 08:00 | 2008-06-10 17:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2008-10-24 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
41 | PRODUCTIE PREFABWANDEN 11 dagen per verdiep (incl hydrofoberen) | 2008-06-25 08:00 | 2009-01-27 17:00 | 155d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 160d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 103.2258 | 100 | 100 | 100 | 100
42 | KEURING EERSTE ELEMENTEN -WIT-ZWART-GRIJS | 2008-07-11 08:00 | 2008-07-11 17:00 | 1d |  | 0 | 1 | 0 | 0 | 1 | 2008-11-03 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
43 | BETON GELIJKVLOERS | 2008-08-20 08:00 | 2008-09-08 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 32d | [5 empty] | 111400 |  | 100% |  | 100000 | 100000
44 | WANDEN KOKER A | 2008-08-20 08:00 | 2008-08-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-05 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 11200 | 11200 | 100 | 200 | 100 | 100 | 110.7143 | 100
45 | WANDEN KOKER F | 2008-08-21 08:00 | 2008-08-21 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2008-12-03 08:00 | 1d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
46 | WANDEN KOKER B tot E | 2008-08-22 08:00 | 2008-08-25 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2008-12-01 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 22400 | 22400 | 100 | 50 | 100 | 100 | 116.9643 | 100
47 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
48 | BEKISTEN TUSSENBORDES KOKER F | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
49 | PL. WERKVLOEREN KOKERS B tot E | 2008-08-26 08:00 | 2008-08-26 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
50 | BETON DRAAGWAND KOKER A en F | 2008-08-25 08:00 | 2008-08-26 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2008-12-10 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
51 | BETON DRAAGWAND KOKER B tot E | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2008-12-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
52 | BEKISTEN PLAAT KOKER A (zwart) | 2008-08-27 08:00 | 2008-08-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
53 | BEKISTEN PLAAT KOKER F | 2008-08-28 08:00 | 2008-08-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
54 | BEKISTEN RANDBALK PLAAT | 2008-08-27 08:00 | 2008-08-29 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-12 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
55 | BEKISTEN PLAAT (met tafels) | 2008-08-29 08:00 | 2008-09-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2008-12-15 08:00 | 2d | 4400 | 0 | 0 | 0 | 0 | 4400 | 0 | 100% | Finished | 5600 | 5600 | 100 | 66.6667 | 100 | 100 | 78.5714 | 100
56 | WAPENING VLOERPLATEN | 2008-09-02 08:00 | 2008-09-04 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2008-12-17 08:00 | 2d | 12400 | 0 | 0 | 10000 | 0 | 22400 | 0 | 100% | Finished | 13600 | 13600 | 100 | 66.6667 | 100 | 100 | 164.7059 | 100
57 | BETON VLOERPLATEN ( grof vlinderen) | 2008-09-05 08:00 | 2008-09-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2008-12-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
58 | PLAATSEN PREFABTRAPPEN + veiligheid $ | 2008-09-08 08:00 | 2008-09-08 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-01-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
59 | BETON EERSTE VERDIEPING | 2008-09-09 08:00 | 2008-09-26 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 15d | [5 empty] | 113800 |  | 100% |  | 100000 | 100000
60 | WANDEN KOKER A | 2008-09-09 08:00 | 2008-09-09 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-15 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
61 | WANDEN KOKER F | 2008-09-10 08:00 | 2008-09-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-01-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
62 | WANDEN KOKER B tot E | 2008-09-11 08:00 | 2008-09-12 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-01-20 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
63 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
64 | BEKISTEN TUSSENBORDES KOKER F | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
65 | PL. WERKVLOEREN KOKERS B tot E | 2008-09-15 08:00 | 2008-09-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
66 | BETON DRAAGWAND KOKER A en F | 2008-09-12 08:00 | 2008-09-15 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-01-21 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
67 | BETON DRAAGWAND KOKER B tot E | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-01-26 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
68 | BEKISTEN PLAAT KOKER A (zwart) | 2008-09-16 08:00 | 2008-09-16 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
69 | BEKISTEN PLAAT KOKER F | 2008-09-17 08:00 | 2008-09-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-01-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
70 | BEKISTEN RANDBALK PLAAT | 2008-09-16 08:00 | 2008-09-18 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
71 | BEKISTEN PLAAT (met tafels) | 2008-09-18 08:00 | 2008-09-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-01-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
72 | WAPENING VLOERPLATEN | 2008-09-22 08:00 | 2008-09-24 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-01-30 08:00 | 1d | 11200 | 0 | 0 | 11000 | 0 | 22200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 163.2353 | 100
73 | BETON VLOERPLATEN (grof vlinderen) | 2008-09-25 08:00 | 2008-09-25 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
74 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-09-26 08:00 | 2008-09-26 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-04 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
75 | BETON TWEEDE VERDIEPING | 2008-09-29 08:00 | 2008-10-16 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 115800 |  | 100% |  | 100000 | 100000
76 | WANDEN KOKER A | 2008-09-29 08:00 | 2008-09-29 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
77 | WANDEN KOKER F | 2008-09-30 08:00 | 2008-09-30 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
78 | WANDEN KOKER B tot E | 2008-10-01 08:00 | 2008-10-02 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-12 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
79 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
80 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
81 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-03 08:00 | 2008-10-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
82 | BETON DRAAGWAND KOKER A en F | 2008-10-02 08:00 | 2008-10-03 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-02-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
83 | BETON DRAAGWAND KOKER B tot E | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-02-13 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
84 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-06 08:00 | 2008-10-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
85 | BEKISTEN PLAAT KOKER F | 2008-10-07 08:00 | 2008-10-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
86 | BEKISTEN RANDBALK PLAAT | 2008-10-06 08:00 | 2008-10-08 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-13 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
87 | BEKISTEN PLAAT (met tafels) | 2008-10-08 08:00 | 2008-10-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-02-17 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
88 | WAPENING VLOERPLATEN | 2008-10-10 08:00 | 2008-10-14 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-02-19 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
89 | BETON VLOERPLATEN (grof vlinderen) | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-02-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
90 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-02-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
91 | BETON DERDE VERDIEPING | 2008-10-17 08:00 | 2008-11-06 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
92 | WANDEN KOKER A | 2008-10-17 08:00 | 2008-10-17 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
93 | WANDEN KOKER F | 2008-10-20 08:00 | 2008-10-20 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-02-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
94 | WANDEN KOKER B tot E | 2008-10-21 08:00 | 2008-10-22 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-02-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
95 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
96 | BEKISTEN TUSSENBORDES KOKER F | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
97 | PL. WERKVLOEREN KOKERS B tot E | 2008-10-23 08:00 | 2008-10-23 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
98 | BETON DRAAGWAND KOKER A en F | 2008-10-22 08:00 | 2008-10-23 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-02 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
99 | BETON DRAAGWAND KOKER B tot E | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-03 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
100 | BEKISTEN PLAAT KOKER A (zwart) | 2008-10-24 08:00 | 2008-10-24 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
101 | BEKISTEN PLAAT KOKER F | 2008-10-27 08:00 | 2008-10-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
102 | BEKISTEN RANDBALK PLAAT | 2008-10-24 08:00 | 2008-10-28 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-03 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
103 | BEKISTEN PLAAT (met tafels) | 2008-10-28 08:00 | 2008-10-30 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
104 | WAPENING VLOERPLATEN | 2008-10-30 08:00 | 2008-11-03 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
105 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
106 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-03-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
107 | BETON VIERDE VERDIEPING | 2008-11-07 08:00 | 2008-11-28 17:00 | 16d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
108 | WANDEN KOKER A | 2008-11-07 08:00 | 2008-11-07 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
109 | WANDEN KOKER F | 2008-11-12 08:00 | 2008-11-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-03-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
110 | WANDEN KOKER B tot E | 2008-11-13 08:00 | 2008-11-14 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-03-18 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
111 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
112 | BEKISTEN TUSSENBORDES KOKER F | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
113 | PL. WERKVLOEREN KOKERS B tot E | 2008-11-17 08:00 | 2008-11-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
114 | BETON DRAAGWAND KOKER A en F | 2008-11-14 08:00 | 2008-11-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-03-19 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
115 | BETON DRAAGWAND KOKER B tot E | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-03-23 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
116 | BEKISTEN PLAAT KOKER A (zwart) | 2008-11-18 08:00 | 2008-11-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
117 | BEKISTEN PLAAT KOKER F | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-03-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
118 | BEKISTEN RANDBALK PLAAT | 2008-11-18 08:00 | 2008-11-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-23 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
119 | BEKISTEN PLAAT (met tafels) | 2008-11-20 08:00 | 2008-11-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-03-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
120 | WAPENING VLOERPLATEN | 2008-11-24 08:00 | 2008-11-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-03-31 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
121 | BETON VLOERPLATEN (grof vlinderen) | 2008-11-27 08:00 | 2008-11-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
122 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-11-28 08:00 | 2008-11-28 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-02 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
123 | BETON VIJFDE VERDIEPING | 2008-12-01 08:00 | 2008-12-18 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
124 | WANDEN KOKER A | 2008-12-01 08:00 | 2008-12-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-03 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
125 | WANDEN KOKER F | 2008-12-02 08:00 | 2008-12-02 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-06 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
126 | WANDEN KOKER B tot E | 2008-12-03 08:00 | 2008-12-04 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-07 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
127 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
128 | BEKISTEN TUSSENBORDES KOKER F | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
129 | PL. WERKVLOEREN KOKERS B tot E | 2008-12-05 08:00 | 2008-12-05 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-09 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
130 | BETON DRAAGWAND KOKER A en F | 2008-12-04 08:00 | 2008-12-05 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-04-08 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
131 | BETON DRAAGWAND KOKER B tot E | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-04-10 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
132 | BEKISTEN PLAAT KOKER A (zwart) | 2008-12-08 08:00 | 2008-12-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
133 | BEKISTEN PLAAT KOKER F | 2008-12-09 08:00 | 2008-12-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
134 | BEKISTEN RANDBALK PLAAT | 2008-12-08 08:00 | 2008-12-10 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
135 | BEKISTEN PLAAT (met tafels) | 2008-12-10 08:00 | 2008-12-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-04-21 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
136 | WAPENING VLOERPLATEN | 2008-12-12 08:00 | 2008-12-16 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-04-23 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
137 | BETON VLOERPLATEN (grof vlinderen) | 2008-12-17 08:00 | 2008-12-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-04-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
138 | PLAATSEN PREFABTRAPPEN + veiligheid | 2008-12-18 08:00 | 2008-12-18 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-04-27 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
139 | BETON ZESDE VERDIEPING | 2008-12-19 08:00 | 2009-01-21 17:00 | 24d |  |  | 72400 |  |  | 100000 |  | 13d | [5 empty] | 120800 |  | 100% |  | 100000 | 100000
140 | WANDEN KOKER A | 2008-12-19 08:00 | 2008-12-19 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-27 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
141 | WANDEN KOKER F | 2009-01-05 08:00 | 2009-01-05 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-04-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
142 | WANDEN KOKER B tot E | 2009-01-06 08:00 | 2009-01-07 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-04-29 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
143 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
144 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
145 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-08 08:00 | 2009-01-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
146 | BETON DRAAGWAND KOKER A en F | 2009-01-07 08:00 | 2009-01-08 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-01 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
147 | BETON DRAAGWAND KOKER B tot E | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-05 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
148 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-09 08:00 | 2009-01-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
149 | BEKISTEN PLAAT KOKER F | 2009-01-12 08:00 | 2009-01-12 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-06 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
150 | BEKISTEN RANDBALK PLAAT | 2009-01-09 08:00 | 2009-01-13 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-05 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
151 | BEKISTEN PLAAT (met tafels) | 2009-01-13 08:00 | 2009-01-15 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 5600 | 5600 | 100 | 33.3333 | 100 | 100 | 57.1429 | 100
152 | WAPENING VLOERPLATEN | 2009-01-15 08:00 | 2009-01-19 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-11 08:00 | 1d | 11200 | 0 | 0 | 13000 | 0 | 24200 | 0 | 100% | Finished | 13600 | 13600 | 100 | 33.3333 | 100 | 100 | 177.9412 | 100
153 | BETON VLOERPLATEN (grof vlinderen) | 2009-01-20 08:00 | 2009-01-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
154 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-01-21 08:00 | 2009-01-21 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-05-13 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
155 | BETON ZEVENDE VERDIEPING | 2009-01-22 08:00 | 2009-02-10 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 17d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
156 | WANDEN KOKER A | 2009-01-22 08:00 | 2009-01-22 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-12 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
157 | WANDEN KOKER F | 2009-01-23 08:00 | 2009-01-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-13 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
158 | WANDEN KOKER B tot E | 2009-01-26 08:00 | 2009-01-27 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-05-14 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
159 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
160 | BEKISTEN TUSSENBORDES KOKER F | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
161 | PL. WERKVLOEREN KOKERS B tot E | 2009-01-28 08:00 | 2009-01-28 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-18 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
162 | BETON DRAAGWAND KOKER A en F | 2009-01-27 08:00 | 2009-01-28 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-05-15 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
163 | BETON DRAAGWAND KOKER B tot E | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-05-19 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
164 | BEKISTEN PLAAT KOKER A (zwart) | 2009-01-29 08:00 | 2009-01-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-19 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
165 | BEKISTEN PLAAT KOKER F | 2009-01-30 08:00 | 2009-01-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-05-20 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
166 | BEKISTEN RANDBALK PLAAT | 2009-01-29 08:00 | 2009-02-02 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-19 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
167 | BEKISTEN PLAAT (met tafels) | 2009-02-02 08:00 | 2009-02-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-05-25 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
168 | WAPENING VLOERPLATEN | 2009-02-04 08:00 | 2009-02-06 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-05-27 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
169 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-09 08:00 | 2009-02-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
170 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-02-10 08:00 | 2009-02-10 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
171 | BETON ACHTSTE VERDIEPING | 2009-02-11 08:00 | 2009-03-02 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
172 | WANDEN KOKER A | 2009-02-11 08:00 | 2009-02-11 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
173 | WANDEN KOKER F | 2009-02-12 08:00 | 2009-02-12 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
174 | WANDEN KOKER B tot E | 2009-02-13 08:00 | 2009-02-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-08 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
175 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
176 | BEKISTEN TUSSENBORDES KOKER F | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
177 | PL. WERKVLOEREN KOKERS B tot E | 2009-02-17 08:00 | 2009-02-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
178 | BETON DRAAGWAND KOKER A en F | 2009-02-16 08:00 | 2009-02-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-09 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
179 | BETON DRAAGWAND KOKER B tot E | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-06-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
180 | BEKISTEN PLAAT KOKER A (zwart) | 2009-02-18 08:00 | 2009-02-18 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
181 | BEKISTEN PLAAT KOKER F | 2009-02-19 08:00 | 2009-02-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
182 | BEKISTEN RANDBALK PLAAT | 2009-02-18 08:00 | 2009-02-20 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
183 | BEKISTEN PLAAT (met tafels) | 2009-02-20 08:00 | 2009-02-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-06-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
184 | WAPENING VLOERPLATEN | 2009-02-24 08:00 | 2009-02-26 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-06-17 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
185 | BETON VLOERPLATEN (grof vlinderen) | 2009-02-27 08:00 | 2009-02-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-22 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
186 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-02 08:00 | 2009-03-02 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-06-23 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
187 | BETON NEGENDE VERDIEPING | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 51d | [5 empty] | 128000 |  | 100% |  | 100000 | 100000
188 | WANDEN KOKER A | 2009-03-03 08:00 | 2009-03-03 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-06-24 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
189 | WANDEN KOKER F | 2009-03-04 08:00 | 2009-03-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-05-25 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
190 | WANDEN KOKER B tot E | 2009-03-05 08:00 | 2009-03-06 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-06-26 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
191 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
192 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
193 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-09 08:00 | 2009-03-09 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-06-30 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
194 | BETON DRAAGWAND KOKER A en F | 2009-03-06 08:00 | 2009-03-09 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-06-29 08:00 | 2d | 4300 | 0 | 0 | 5000 | 0 | 9300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 216.2791 | 100
195 | BETON DRAAGWAND KOKER B tot E | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-07-01 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
196 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-10 08:00 | 2009-03-10 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
197 | BEKISTEN PLAAT KOKER F | 2009-03-11 08:00 | 2009-03-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
198 | BEKISTEN RANDBALK PLAAT | 2009-03-10 08:00 | 2009-03-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-01 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
199 | BEKISTEN PLAAT (met tafels) | 2009-03-12 08:00 | 2009-03-16 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-07-03 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
200 | WAPENING VLOERPLATEN | 2009-03-16 08:00 | 2009-03-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-07-07 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
201 | BETON VLOERPLATEN (grof vlinderen) | 2009-03-19 08:00 | 2009-03-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-07-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
202 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-03-20 08:00 | 2009-03-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-08-03 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
203 | BETON TIENDE VERDIEPING | 2009-03-23 08:00 | 2009-04-09 17:00 | 14d |  |  | 72400 |  |  | 100000 |  | 25d | [5 empty] | 120000 |  | 100% |  | 100000 | 100000
204 | WANDEN KOKER A | 2009-03-23 08:00 | 2009-03-23 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-04 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
205 | WANDEN KOKER F | 2009-03-24 08:00 | 2009-03-24 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-08-05 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
206 | WANDEN KOKER B tot E | 2009-03-25 08:00 | 2009-03-26 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-08-06 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
207 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
208 | BEKISTEN TUSSENBORDES KOKER F | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
209 | PL. WERKVLOEREN KOKERS B tot E | 2009-03-27 08:00 | 2009-03-27 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
210 | BETON DRAAGWAND KOKER A en F | 2009-03-26 08:00 | 2009-03-27 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-08-07 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
211 | BETON DRAAGWAND KOKER B tot E | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-08-11 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
212 | BEKISTEN PLAAT KOKER A (zwart) | 2009-03-30 08:00 | 2009-03-30 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-11 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
213 | BEKISTEN PLAAT KOKER F | 2009-03-31 08:00 | 2009-03-31 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-08-12 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
214 | BEKISTEN RANDBALK PLAAT | 2009-03-30 08:00 | 2009-04-01 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-11 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
215 | BEKISTEN PLAAT (met tafels) | 2009-04-01 08:00 | 2009-04-03 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-08-13 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
216 | WAPENING VLOERPLATEN | 2009-04-03 08:00 | 2009-04-07 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-08-18 08:00 | 3d | 13600 | 0 | 0 | 10000 | 0 | 23600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 173.5294 | 100
217 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-08 08:00 | 2009-04-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-04 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
218 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-09 08:00 | 2009-04-09 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-07 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
219 | BETON ELFDE VERDIEPING | 2009-04-10 08:00 | 2009-04-30 17:00 | 15d |  |  | 72400 |  |  | 100000 |  | 14d | [5 empty] | 123000 |  | 100% |  | 100000 | 100000
220 | WANDEN KOKER A | 2009-04-10 08:00 | 2009-04-10 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-08 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
221 | WANDEN KOKER F | 2009-04-14 08:00 | 2009-04-14 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-09 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
222 | WANDEN KOKER B tot E | 2009-04-15 08:00 | 2009-04-16 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-09-10 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
223 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
224 | BEKISTEN TUSSENBORDES KOKER F | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
225 | PL. WERKVLOEREN KOKERS B tot E | 2009-04-17 08:00 | 2009-04-17 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-14 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
226 | BETON DRAAGWAND KOKER A en F | 2009-04-16 08:00 | 2009-04-17 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-09-11 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
227 | BETON DRAAGWAND KOKER B tot E | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-09-15 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
228 | BEKISTEN PLAAT KOKER A (zwart) | 2009-04-20 08:00 | 2009-04-20 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-15 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
229 | BEKISTEN PLAAT KOKER F | 2009-04-21 08:00 | 2009-04-21 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
230 | BEKISTEN RANDBALK PLAAT | 2009-04-20 08:00 | 2009-04-22 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-15 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
231 | BEKISTEN PLAAT (met tafels) | 2009-04-22 08:00 | 2009-04-24 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-09-17 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
232 | WAPENING VLOERPLATEN | 2009-04-24 08:00 | 2009-04-28 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-09-21 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
233 | BETON VLOERPLATEN (grof vlinderen) | 2009-04-29 08:00 | 2009-04-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-09-24 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
234 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-04-30 08:00 | 2009-04-30 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-09-25 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
235 | BETON TWAALFDE VERDIEPING | 2009-05-01 08:00 | 2009-05-20 17:00 | 14d |  |  | 72400 |  |  | 98800 |  | 16d | [5 empty] | 121800 |  | 100% |  | 98800 | 98800
236 | WANDEN KOKER A | 2009-05-01 08:00 | 2009-05-01 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-28 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
237 | WANDEN KOKER F | 2009-05-04 08:00 | 2009-05-04 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-09-29 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
238 | WANDEN KOKER B tot E | 2009-05-05 08:00 | 2009-05-05 17:00 | 1d |  | 0 | 20000 | 150 | 1200 | 21200 | 2009-09-30 08:00 | 1d | 21200 | 0 | 0 | 5000 | 0 | 26200 | 0 | 100% | Finished | 21200 | 21200 | 100 | 100 | 100 | 100 | 123.5849 | 100
239 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
240 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-02 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
241 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-06 08:00 | 2009-05-06 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-01 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
242 | BETON DRAAGWAND KOKER A en F | 2009-05-06 08:00 | 2009-05-07 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-10-01 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
243 | BETON DRAAGWAND KOKER B tot E | 2009-05-07 08:00 | 2009-05-07 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-10-02 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
244 | BEKISTEN PLAAT KOKER A (zwart) | 2009-05-08 08:00 | 2009-05-08 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-07 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
245 | BEKISTEN PLAAT KOKER F | 2009-05-11 08:00 | 2009-05-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-08 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
246 | BEKISTEN RANDBALK PLAAT | 2009-05-08 08:00 | 2009-05-12 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-07 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
247 | BEKISTEN PLAAT (met tafels) | 2009-05-12 08:00 | 2009-05-14 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-09 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
248 | WAPENING VLOERPLATEN | 2009-05-14 08:00 | 2009-05-18 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-10-13 08:00 | 3d | 13600 | 0 | 0 | 13000 | 0 | 26600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 195.5882 | 100
249 | BETON VLOERPLATEN (grof vlinderen) | 2009-05-19 08:00 | 2009-05-19 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-16 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
250 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-05-20 08:00 | 2009-05-20 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-10-19 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
251 | BETON DERTIENDE VERDIEPING | 2009-05-25 08:00 | 2009-06-12 17:00 | 15d |  |  | 72400 |  |  | 101200 |  | 18d | [5 empty] | 116200 |  | 100% |  | 101200 | 101200
252 | WANDEN KOKER A | 2009-05-25 08:00 | 2009-05-25 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-10-20 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
253 | WANDEN KOKER F | 2009-05-26 08:00 | 2009-05-26 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-10-21 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
254 | WANDEN KOKER B tot E | 2009-05-27 08:00 | 2009-05-28 17:00 | 2d |  | 0 | 20000 | 150 | 2400 | 22400 | 2009-10-22 08:00 | 2d | 22400 | 0 | 0 | 5000 | 0 | 27400 | 0 | 100% | Finished | 22400 | 22400 | 100 | 100 | 100 | 100 | 122.3214 | 100
255 | BEKISTEN TUSSENBORDES KOKER A (zwart) | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
256 | BEKISTEN TUSSENBORDES KOKER F | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
257 | PL. WERKVLOEREN KOKERS B tot E | 2009-05-29 08:00 | 2009-05-29 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-26 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
258 | BETON DRAAGWAND KOKER A en F | 2009-05-28 08:00 | 2009-05-29 17:00 | 2d |  | 0 | 1900 | 150 | 2400 | 4300 | 2009-10-23 08:00 | 2d | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 100 | 100
259 | BETON DRAAGWAND KOKER B tot E | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 1900 | 150 | 1200 | 3100 | 2009-10-27 08:00 | 1d | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 100% | Finished | 3100 | 3100 | 100 | 100 | 100 | 100 | 100 | 100
260 | BEKISTEN PLAAT KOKER A (zwart) | 2009-06-02 08:00 | 2009-06-02 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-27 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
261 | BEKISTEN PLAAT KOKER F | 2009-06-03 08:00 | 2009-06-03 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-10-28 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
262 | BEKISTEN RANDBALK PLAAT | 2009-06-02 08:00 | 2009-06-04 17:00 | 3d |  | 0 | 2000 | 150 | 3600 | 5600 | 2009-10-27 08:00 | 3d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 5600 | 5600 | 100 | 100 | 100 | 100 | 100 | 100
263 | BEKISTEN PLAAT (met tafels) deels met stelling 8m hoog | 2009-06-04 08:00 | 2009-06-09 17:00 | 4d |  | 0 | 2000 | 150 | 4800 | 6800 | 2009-10-29 08:00 | 4d | 6800 | 0 | 0 | 5000 | 0 | 11800 | 0 | 100% | Finished | 6800 | 6800 | 100 | 100 | 100 | 100 | 173.5294 | 100
264 | WAPENING VLOERPLATEN | 2009-06-08 08:00 | 2009-06-10 17:00 | 3d |  | 0 | 10000 | 150 | 3600 | 13600 | 2009-11-04 08:00 | 3d | 13600 | 0 | 0 | 0 | 0 | 13600 | 0 | 100% | Finished | 13600 | 13600 | 100 | 100 | 100 | 100 | 100 | 100
265 | BETON VLOERPLATEN (grof vlinderen) | 2009-06-11 08:00 | 2009-06-11 17:00 | 1d |  | 0 | 2000 | 150 | 1200 | 3200 | 2009-11-10 08:00 | 1d | 3200 | 0 | 0 | 0 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200 | 100 | 100 | 100 | 100 | 100 | 100
266 | PLAATSEN PREFABTRAPPEN + veiligheid | 2009-06-12 08:00 | 2009-06-12 17:00 | 1d |  | 0 | 2600 | 150 | 1200 | 3800 | 2009-11-12 08:00 | 1d | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 3800 | 3800 | 100 | 100 | 100 | 100 | 100 | 100
267 | BETON VEERTIENDE DAKVERDIEPING | 2009-06-15 08:00 | 2009-08-12 17:00 | 43d |  |  | 42036 |  |  | 56436 |  | 53d | [5 empty] | 72436 |  | 100% |  | 56436 | 56436
268 | WANDEN KOKER A | 2009-06-15 08:00 | 2009-06-15 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-11-16 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
269 | WANDEN KOKER F | 2009-06-16 08:00 | 2009-06-16 17:00 | 1d |  | 0 | 10000 | 150 | 1200 | 11200 | 2009-11-17 08:00 | 1d | 11200 | 0 | 0 | 2500 | 0 | 13700 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 122.3214 | 100
270 | BETON DRAAGWAND KOKER F | 2009-06-18 08:00 | 2009-06-19 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 | 2009-11-19 08:00 | 2d | 12400 | 0 | 0 | 5000 | 0 | 17400 | 0 | 100% | Finished | 12400 | 12400 | 100 | 100 | 100 | 100 | 140.3226 | 100
271 | BEKISTEN DAKPLAAT KOKER F | 2009-06-23 08:00 | 2009-06-24 17:00 | 2d |  | 0 | 1000 | 150 | 2400 | 3400 | 2009-12-01 08:00 | 2d | 3400 | 0 | 0 | 0 | 0 | 3400 | 0 | 100% | Finished | 3400 | 3400 | 100 | 100 | 100 | 100 | 100 | 100
272 | HELLINGSBETON DAK enkel boven kokers | 2009-06-25 08:00 | 2009-06-26 17:00 | 2d |  | 0 | 10000 | 150 | 2400 | 12400 | 2009-12-07 08:00 | 2d | 12400 | 0 | 0 | 0 | 0 | 12400 | 0 | 100% | Finished | 12400 | 12400 | 100 | 100 | 100 | 100 | 100 | 100
273 | ONTKISTEN PLATEN 13de EN 14de VERDIEPING | 2009-08-07 08:00 | 2009-08-12 17:00 | 4d |  | 0 | 1036 | 150 | 4800 | 5836 | 2010-01-22 08:00 | 4d | 5836 | 0 | 0 | 6000 | 0 | 11836 | 0 | 100% | Finished | 5836 | 5836 | 100 | 100 | 100 | 100 | 202.8101 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
30/10, 2008 | 2008-05-05 08:00 | 2008-10-30 17:00 | 933607 | 539567.7653 | 559006 | 2008-08-21 17:00 | -394039.2347 | 57.79% | -19438.2347 | 96.52% | -50d | 61.24% | 95.83% | 2009-11-09 09:00 | 2010-07-20 09:00 | 2010-08-17 17:00 | 2009-10-28 12:00 | 2010-07-20 09:00 | 2010-08-11 10:00 | 2009-10-21 17:00 | 2010-06-03 15:00 | 2010-06-24 15:00 | 2133122.2347 | 2189830.6648 | 3282678.5953 | 3129398.3327 | 3380800.4451 | 3221998.1741 | 2332119.6927 | 2318458.8924 | 0.6124 | 0.96523 | 0.57794 | 0.95831 | -50 | 0.96523 | 1 | 0.6124 | 1
31/12, 2008 | 2008-10-30 17:00 | 2008-12-31 17:00 | 1178847 | 635769.7653 | 678368 | 2008-09-09 17:00 | -543077.2347 | 53.93% | -42598.2347 | 93.72% | -81d | 53.18% | 97.63% | 2009-12-10 12:00 | 2010-09-15 12:00 | 2010-11-11 16:00 | 2009-12-02 15:00 | 2010-09-15 12:00 | 2010-10-27 10:00 | 2009-12-03 17:00 | 2010-09-28 09:00 | 2010-11-09 12:00 | 2156282.2347 | 2255306.3484 | 3418722.8534 | 3457489.3327 | 3602333.7856 | 3643697.7203 | 2401628.2301 | 2404656.7914 | 0.53179 | 0.9372 | 0.53931 | 0.97632 | -81 | 0.9372 | 1 | 0.53179 | 1
31/01, 2009 | 2008-12-31 17:00 | 2009-01-31 17:00 | 1352567 | 732773.6016 | 800488 | 2008-09-26 17:00 | -619793.3984 | 54.18% | -67714.3984 | 91.54% | -90d | 53.85% | 99.04% | 2009-12-28 14:00 | 2010-09-10 14:00 | 2010-11-30 12:00 | 2009-12-16 11:00 | 2010-09-10 14:00 | 2010-11-04 11:00 | 2009-12-16 17:00 | 2010-09-16 11:00 | 2010-11-10 12:00 | 2181398.3984 | 2309006.0478 | 3349397.8279 | 3365035.8827 | 3584938.3758 | 3602021.5173 | 2443099.407 | 2444391.3953 | 0.53846 | 0.91541 | 0.54177 | 0.99041 | -90 | 0.91541 | 1 | 0.53846 | 1
28/02, 2009 | 2009-01-31 17:00 | 2009-02-28 17:00 | 1487368 | 891713.5339 | 989288 | 2008-10-22 17:00 | -595654.4661 | 59.95% | -97574.4661 | 90.14% | -92d | 57.21% | 99.65% | 2009-12-22 16:00 | 2010-06-21 12:00 | 2010-09-14 10:00 | 2009-12-11 09:00 | 2010-06-21 12:00 | 2010-08-11 15:00 | 2009-12-18 17:00 | 2010-07-28 09:00 | 2010-09-22 10:00 | 2211258.4661 | 2344970.8203 | 3027520.7948 | 3125252.6359 | 3250551.4759 | 3358977.4827 | 2442284.8215 | 2451825.7355 | 0.57209 | 0.90137 | 0.59952 | 0.99651 | -92 | 0.90137 | 1 | 0.57209 | 1
30/04, 2009 | 2009-02-28 17:00 | 2009-04-30 17:00 | 1815808 | 1220536.7429 | 1393688 | 2009-01-07 17:00 | -595271.2571 | 67.22% | -173151.2571 | 87.58% | -81d | 68.73% | 99.72% | 2009-12-22 15:00 | 2010-03-29 11:00 | 2010-07-05 15:00 | 2009-12-09 16:00 | 2010-03-29 11:00 | 2010-05-13 17:00 | 2009-12-03 17:00 | 2010-03-12 12:00 | 2010-04-27 12:00 | 2286835.2571 | 2413541.4552 | 2722434.5077 | 2693267.4359 | 2910936.9264 | 2877632.0725 | 2463270.5206 | 2459419.817 | 0.68726 | 0.87576 | 0.67217 | 0.99721 | -81 | 0.87576 | 1 | 0.68726 | 1
30/06, 2009 | 2009-04-30 17:00 | 2009-06-30 17:00 | 2090488 | 1556958.9339 | 1816788 | 2009-03-09 17:00 | -533529.0661 | 74.48% | -259829.0661 | 85.7% | -81d | 73.18% | 100% | 2009-12-08 17:00 | 2010-01-20 09:00 | 2010-05-04 15:00 | 2009-11-30 09:00 | 2010-01-20 09:00 | 2010-02-23 11:00 | 2009-12-03 17:00 | 2010-01-29 17:00 | 2010-03-08 14:00 | 2373513.0661 | 2466420.6893 | 2564288.1714 | 2577561.6197 | 2689032.8048 | 2704521.3583 | 2483888.9091 | 2485972.8464 | 0.73179 | 0.85698 | 0.74478 | 1 | -81 | 0.85698 | 1 | 0.73179 | 1
30/09, 2009 | 2009-06-30 17:00 | 2009-09-30 17:00 | 2113684 | 1870261.0751 | 2198088 | 2009-05-06 17:00 | -243422.9249 | 88.48% | -327826.9249 | 85.09% | -105d | 71.47% | 99.66% | 2009-10-06 11:00 | 2009-10-13 11:00 | 2010-01-13 10:00 | 2009-11-30 11:00 | 2009-12-07 16:00 | 2009-12-18 10:00 | 2010-01-06 17:00 | 2010-02-15 17:00 | 2010-03-11 09:00 | 2441510.9249 | 2484179.0796 | 2473193.5178 | 2538694.9824 | 2521415.1256 | 2598397.9517 | 2481912.335 | 2493640.0039 | 0.71467 | 0.85086 | 0.88483 | 0.99663 | -105 | 0.85086 | 1 | 0.71467 | 1
31/10, 2009 | 2009-09-30 17:00 | 2009-10-31 17:00 | 2113684 | 2014584.9789 | 2376488 | 2009-06-05 17:00 | -99099.0211 | 95.31% | -361903.0211 | 84.77% | -105d | 73.08% | 100% | 2009-09-03 14:00 | 2009-09-04 11:00 | 2009-12-02 09:00 | 2009-11-26 10:00 | 2009-11-27 09:00 | 2009-12-02 14:00 | 2010-01-06 17:00 | 2010-02-01 14:00 | 2010-02-17 12:00 | 2475587.0211 | 2493389.3156 | 2480461.7799 | 2512097.1867 | 2499139.7833 | 2536458.2213 | 2490552.8741 | 2496706.2403 | 0.73077 | 0.84772 | 0.95312 | 1 | -105 | 0.84772 | 1 | 0.73077 | 1
30/11, 2009 | 2009-10-31 17:00 | 2009-11-30 17:00 | 2113684 | 2073286.7746 | 2460488 | 2009-06-23 12:00 | -40397.2254 | 98.09% | -387201.2254 | 84.26% | -114d 4h | 72.14% | 99.92% | 2009-08-21 11:00 | 2009-08-21 12:00 | 2009-11-18 16:00 | 2009-12-10 16:00 | 2009-12-10 17:00 | 2009-12-14 12:00 | 2010-01-20 12:00 | 2010-02-09 14:00 | 2010-02-22 17:00 | 2500885.2254 | 2508429.698 | 2501672.3504 | 2516485.503 | 2509363.8242 | 2526943.4397 | 2506906.4702 | 2509849.9405 | 0.72141 | 0.84263 | 0.98089 | 0.99923 | -114.5 | 0.84263 | 1 | 0.72141 | 1
31/12, 2009 | 2009-11-30 17:00 | 2009-12-31 17:00 | 2113684 | 2099509.676 | 2490288 | 2009-07-22 17:00 | -14174.324 | 99.33% | -390778.324 | 84.31% | -116d | 73.27% | 100% | 2009-08-17 10:00 | 2009-08-17 10:00 | 2009-11-11 14:00 | 2010-01-05 16:00 | 2010-01-05 16:00 | 2010-01-06 12:00 | 2010-01-21 17:00 | 2010-01-29 12:00 | 2010-02-04 10:00 | 2504462.324 | 2507100.5679 | 2504558.0185 | 2509632.8322 | 2507214.0738 | 2513233.4543 | 2506522.0694 | 2507552.5587 | 0.73272 | 0.84308 | 0.99329 | 1 | -116 | 0.84308 | 1 | 0.73272 | 1
Actual Schedule | 2009-12-31 17:00 | 2010-01-27 17:00 | 2113684 | 2113684 | 2512524 | 2009-08-12 17:00 | 0 | 100% | -398840 | 84.13% | -120d | 73.51% | 100% | 2009-08-12 17:00 | 2009-08-12 17:00 | 2009-11-09 16:00 | 2010-01-27 17:00 | 2010-01-27 17:00 | 2010-01-27 17:00 | 2010-01-27 17:00 | 2010-01-27 17:00 | 2010-01-27 17:00 | 2512524 | 2512524 | 2512524 | 2512524 | 2512524 | 2512524 | 2512524 | 2512524 | 0.7351 | 0.84126 | 1 | 1 | -120 | 0.84126 | 1 | 0.7351 | 1