## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Family Residence | 1 |  |  | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 | 286.375
62 | Voorafgaande activiteiten | 1.1 |  | FS61 | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 0.375
61 | Werfinrichting | 1.2 | 62FS | FS2 | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 0.375
1 | Ruwbouw | 1.3 |  |  | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 | 70.375
2 | Fundering | 1.3.1 | 61FS | FS3;FS58 | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 9.375
3 | Metselwerken | 1.3.2 | 2FS | SS5;FS4;FS7;SS10;FS11 | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 49.375
4 | Dorpels | 1.3.3 | 3FS | FS18;FS21 | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 | 0.375
5 | Parement levering | 1.3.4 | 3SS |  | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 0.375
6 | Voegwerken | 1.4 |  |  | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 | 64.375
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 1.4.1 | 3FS |  | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 | 0.375
8 | Volledige ruwbouw | 1.4.2 | 15FS |  | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 | 1.375
9 | Kapconstructie | 1.5 |  |  | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 | 30.375
10 | Koppels | 1.5.1 | 3SS |  | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 | 0.375
11 | Volledige kapconstructie | 1.5.2 | 3FS | FS13;FS18;FS21 | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 | 7.375
12 | Dakwerken | 1.6 |  |  | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 | 21.375
13 | Zinkwerken | 1.6.1 | 11FS | FS14 | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 | 1.375
14 | Onderdak | 1.6.2 | 13FS | FS15;FS23 | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 | 0.375
15 | Plaatsing pannen | 1.6.3 | 14FS | FS8;FS27 | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 | 2.375
16 | Buitenschrijnwerk | 1.7 |  |  | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 | 69.375
17 | Schrijnwerk | 1.7.1 |  |  | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 | 69.375
18 | Opmeting schrijnwerk | 1.7.1.1 | 4FS;11FS | FS19 | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 | 0.375
19 | Plaatsing schrijnwerk | 1.7.1.2 | 18FS | FS28 | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 | 1.375
20 | Poort | 1.7.2 |  |  | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 | 68.375
21 | Opmeting poort | 1.7.2.1 | 4FS;11FS | FS22 | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 0.375
22 | Plaatsing poort | 1.7.2.2 | 21FS | FS39 | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 0.375
23 | Ruwbouw sanitair en cv | 1.8 | 14FS | FS25;FS26 | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 | 5.375
25 | Ruwbouw elektriciteit | 1.9 | 23FS | FS27 | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 | 5.375
26 | Ruwbouw ventilatie | 1.10 | 23FS |  | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 | 0.375
27 | Dakisolatie | 1.11 | 15FS;25FS | FS28 | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 | 1.375
28 | Pleisterwerken | 1.12 | 27FS;19FS | FS33;SS30;FS31;FS34 | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 | 25.375
29 | Spuitplamuur | 1.13 |  |  | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 | 35.375
30 | Opstop voegen | 1.13.1 | 28SS | FS31 | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 0.375
31 | 1-ste laag | 1.13.2 | 30FS;28FS | FS32 | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 0.375
32 | 2-de laag | 1.13.3 | 31FS | FS36 | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 0.375
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 1.14 | 28FS | FS34 | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 | 0.375
63 | Verdichting inloopdouche plaatsen | 1.15 | 34FS | FS36 | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 | 0.375
34 | Chape | 1.16 | 28FS;33FS | FS63;FS36 | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 | 0.375
35 | Bevloering en faiences | 1.17 |  |  | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 | 21.375
36 | Bevloering beneden+badkamer boven-wc boven | 1.17.1 | 32FS;34FS;63FS | FS37;FS39;FS43;FS46;FS49;FS52 | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 | 14.375
37 | Faiences boven | 1.17.2 | 36FS | FS55 | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 | 6.375
38 | Elektriciteit afwerking | 1.18 |  |  | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 | 30.375
39 | Afwerking elektriciteit | 1.18.1 | 36FS;22FS | FS40;FS41 | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 | 2.375
40 | Keuring | 1.18.2 | 39FS | FS59 | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 | 0.375
41 | Afwerking ventilatie | 1.18.3 | 39FS;59FS |  | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 | 0.375
42 | Binnenschrijnwerk | 1.19 |  |  | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 | 24.375
43 | Opmeting binnenschrijnwerk | 1.19.1 | 36FS | FS44 | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 | 0.375
44 | Plaatsing binnenschrijnwerk | 1.19.2 | 43FS |  | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 | 2.375
45 | Trap gelijkvl. - 1°verdiep | 1.20 |  |  | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 | 29.375
46 | Opmeting trap | 1.20.1 | 36FS | FS47 | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 | 0.375
47 | Plaatsing trap | 1.20.2 | 46FS |  | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 | 0.375
48 | MAP-trap | 1.21 |  |  | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 | 22.375
49 | Opmeting zoldertrap | 1.21.1 | 36FS | FS50 | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 | 0.375
50 | Plaatsing zoldertrap | 1.21.2 | 49FS |  | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 | 0.375
51 | Keukenmeubilair | 1.22 |  |  | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 | 58.375
52 | Opmeting keukenmeubilair | 1.22.1 | 36FS | FS53 | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 | 0.375
53 | Plaatsing keukenmeubilair | 1.22.2 | 52FS | FS60 | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 | 2.375
54 | Badmeubel | 1.23 |  |  | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 | 29.375
55 | Opmeting badmeubel | 1.23.1 | 37FS | FS56 | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 | 0.375
56 | Plaatsing badmeubel | 1.23.2 | 55FS |  | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 | 0.375
57 | Nutsleidingen | 1.24 |  |  | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 | 221.375
58 | Aanvraag offertes | 1.24.1 | 2FS |  | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 0.375
59 | Uitvoering aansluitingen | 1.24.2 | 40FS | FS60;FS41 | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 0.375
60 | Afwerking sanitair en cv | 1.25 | 59FS;53FS |  | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 | 2.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Family Residence | 1360h |  |  |  |  | 99 | 100 | 101
62 | Voorafgaande activiteiten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Werfinrichting | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
1 | Ruwbouw | 368h |  |  |  |  | 99 | 100 | 101
2 | Fundering | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Metselwerken | 256h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Dorpels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Parement levering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Voegwerken | 240h |  |  |  |  | 99 | 100 | 101
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Volledige ruwbouw | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Kapconstructie | 160h |  |  |  |  | 99 | 100 | 101
10 | Koppels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Volledige kapconstructie | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Dakwerken | 128h |  |  |  |  | 99 | 100 | 101
13 | Zinkwerken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Onderdak | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Plaatsing pannen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Buitenschrijnwerk | 264h |  |  |  |  | 99 | 100 | 101
17 | Schrijnwerk | 264h |  |  |  |  | 99 | 100 | 101
18 | Opmeting schrijnwerk | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Plaatsing schrijnwerk | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Poort | 256h |  |  |  |  | 99 | 100 | 101
21 | Opmeting poort | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Plaatsing poort | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Ruwbouw sanitair en cv | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Ruwbouw elektriciteit | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Ruwbouw ventilatie | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Dakisolatie | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Pleisterwerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Spuitplamuur | 208h |  |  |  |  | 99 | 100 | 101
30 | Opstop voegen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | 1-ste laag | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | 2-de laag | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Verdichting inloopdouche plaatsen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Chape | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Bevloering en faiences | 104h |  |  |  |  | 99 | 100 | 101
36 | Bevloering beneden+badkamer boven-wc boven | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Faiences boven | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Elektriciteit afwerking | 184h |  |  |  |  | 99 | 100 | 101
39 | Afwerking elektriciteit | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Keuring | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Afwerking ventilatie | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Binnenschrijnwerk | 152h |  |  |  |  | 99 | 100 | 101
43 | Opmeting binnenschrijnwerk | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Plaatsing binnenschrijnwerk | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Trap gelijkvl. - 1°verdiep | 176h |  |  |  |  | 99 | 100 | 101
46 | Opmeting trap | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Plaatsing trap | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | MAP-trap | 136h |  |  |  |  | 99 | 100 | 101
49 | Opmeting zoldertrap | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Plaatsing zoldertrap | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Keukenmeubilair | 264h |  |  |  |  | 99 | 100 | 101
52 | Opmeting keukenmeubilair | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Plaatsing keukenmeubilair | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Badmeubel | 176h |  |  |  |  | 99 | 100 | 101
55 | Opmeting badmeubel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Plaatsing badmeubel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Nutsleidingen | 1080h |  |  |  |  | 99 | 100 | 101
58 | Aanvraag offertes | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Uitvoering aansluitingen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Afwerking sanitair en cv | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2006-04-30 17:00 |  | TP Name | 30/04, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 7d | [5 empty] | 13130.7102 |  | 7.881% |  | 14223.0502 | 70717.3802
62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 100% | Finished | 1359.3101 | 1359.3101 | 100 | 100 | 100 | 100 | 63.9626 | 100
61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 100% | Finished | 214.62 | 214.62 | 100 | 100 | 100 | 100 | 177.579 | 100
1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 5d | [5 empty] | 11880.1401 |  | 17.88% |  | 12649.1201 | 69143.4502
2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 5d | 12649.1201 | 0 | 2d | -768.98 | 0 | 11880.1401 | 0 | 71.43% | Started | 12649.1201 | 12649.1201 | 100 | 71.4286 | 71.4286 | 100 | 93.9207 | 71.4286
3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 |  | 0 | 0 | 50655.3203 | 32d | 0 | 0 | 0 | 50655.3203 | 0% | Not Started | 0 | 50655.3203 | 100 |  | 0 | 100 |  | 0
4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 |  | 0 | 0 | 1582.98 | 1d | 0 | 0 | 0 | 1582.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 |  | 0 | 0 | 5839.0098 | 1d | 0 | 0 | 0 | 5839.0098 | 0% | Not Started | 0 | 5839.0098 | 100 |  | 0 | 100 |  | 0
6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 |  | 0 | 0 | 558.86 | 1d | 0 | 0 | 0 | 558.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 |  | 0 | 0 | 1117.71 | 2d | 0 | 0 | 0 | 1117.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 |  | 0 | 0 | 970.24 | 1d | 0 | 0 | 0 | 970.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 |  | 0 | 0 | 5821.4199 | 6d | 0 | 0 | 0 | 5821.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 |  | 0 | 0 | 2313.3 | 2d | 0 | 0 | 0 | 2313.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 |  | 0 | 0 | 1156.65 | 1d | 0 | 0 | 0 | 1156.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 |  | 0 | 0 | 3469.96 | 3d | 0 | 0 | 0 | 3469.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 |  | 0 | 0 | 5524.2998 | 1d | 0 | 0 | 0 | 5524.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 |  | 0 | 0 | 11048.5898 | 2d | 0 | 0 | 0 | 11048.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 |  | 0 | 0 | 1298.9301 | 1d | 0 | 0 | 0 | 1298.9301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 |  | 0 | 0 | 1298.9301 | 1d | 0 | 0 | 0 | 1298.9301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 |  | 0 | 0 | 11733.46 | 4d | 0 | 0 | 0 | 11733.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 |  | 0 | 0 | 3594.54 | 4d | 0 | 0 | 0 | 3594.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 |  | 0 | 0 | 1014.92 | 2d | 0 | 0 | 0 | 1014.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 |  | 0 | 0 | 8332.7402 | 20d | 0 | 0 | 0 | 8332.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 |  | 0 | 0 | 29.93 | 1d | 0 | 0 | 0 | 29.93 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 |  | 0 | 0 | 14.43 | 1d | 0 | 0 | 0 | 14.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 |  | 0 | 0 | 1598.6899 | 1d | 0 | 0 | 0 | 1598.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 |  | 0 | 0 | 6829.4302 | 8d | 0 | 0 | 0 | 6829.4302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 |  | 0 | 0 | 4268.3999 | 5d | 0 | 0 | 0 | 4268.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 |  | 0 | 0 | 2695.8999 | 3d | 0 | 0 | 0 | 2695.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 |  | 0 | 0 | 898.63 | 1d | 0 | 0 | 0 | 898.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 |  | 0 | 0 | 1194.5 | 1d | 0 | 0 | 0 | 1194.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 |  | 0 | 0 | 3583.5 | 3d | 0 | 0 | 0 | 3583.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 |  | 0 | 0 | 2957.3799 | 1d | 0 | 0 | 0 | 2957.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 |  | 0 | 0 | 8872.1504 | 3d | 0 | 0 | 0 | 8872.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 |  | 0 | 0 | 27 | 1d | 0 | 0 | 0 | 27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 |  | 0 | 0 | 27 | 1d | 0 | 0 | 0 | 27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 |  | 0 | 0 | 8574.7402 | 3d | 0 | 0 | 0 | 8574.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2006-05-31 17:00 |  | TP Name | 31/05, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 27d | [5 empty] | 66109.1602 |  | 39.2% |  | 70744.3802 | 71714.6202
62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 100% | Finished | 1359.3101 | 1359.3101 | 100 | 100 | 100 | 100 | 63.9626 | 100
61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 100% | Finished | 214.62 | 214.62 | 100 | 100 | 100 | 100 | 177.579 | 100
1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 25d | [5 empty] | 64858.5901 |  | 97.76% |  | 69143.4502 | 69143.4502
2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 7d | 12649.1201 | 0 | 0 | -768.98 | 0 | 11880.1401 | 0 | 100% | Finished | 12649.1201 | 12649.1201 | 100 | 100 | 100 | 100 | 93.9207 | 100
3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 2006-05-12 08:00 | 12d | 50655.3203 | 0 | 24d | -3515.3501 | 0 | 47139.9702 | 0 | 33.33% | Started | 50655.3203 | 50655.3203 | 100 | 37.5 | 33.3333 | 100 | 93.0603 | 33.3333
4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 |  | 0 | 0 | 1582.98 | 1d | 0 | 0 | 0 | 1582.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 2006-05-12 08:00 | 1d | 5839.0098 | 0 | 0 | -0.53 | 0 | 5838.4798 | 0 | 100% | Finished | 5839.0098 | 5839.0098 | 100 | 100 | 100 | 100 | 99.9909 | 100
6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 |  | 0 | 0 | 558.86 | 1d | 0 | 0 | 0 | 558.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 |  | 0 | 0 | 1117.71 | 2d | 0 | 0 | 0 | 1117.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 970.24
10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 |  | 0 | 0 | 970.24 | 1d | 0 | 0 | 0 | 970.24 | 0% | Not Started | 0 | 970.24 | 100 |  | 0 | 100 |  | 0
11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 |  | 0 | 0 | 5821.4199 | 6d | 0 | 0 | 0 | 5821.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 |  | 0 | 0 | 2313.3 | 2d | 0 | 0 | 0 | 2313.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 |  | 0 | 0 | 1156.65 | 1d | 0 | 0 | 0 | 1156.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 |  | 0 | 0 | 3469.96 | 3d | 0 | 0 | 0 | 3469.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 |  | 0 | 0 | 5524.2998 | 1d | 0 | 0 | 0 | 5524.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 |  | 0 | 0 | 11048.5898 | 2d | 0 | 0 | 0 | 11048.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 |  | 0 | 0 | 1298.9301 | 1d | 0 | 0 | 0 | 1298.9301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 |  | 0 | 0 | 1298.9301 | 1d | 0 | 0 | 0 | 1298.9301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 |  | 0 | 0 | 11733.46 | 4d | 0 | 0 | 0 | 11733.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 |  | 0 | 0 | 3594.54 | 4d | 0 | 0 | 0 | 3594.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 |  | 0 | 0 | 1014.92 | 2d | 0 | 0 | 0 | 1014.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 |  | 0 | 0 | 8332.7402 | 20d | 0 | 0 | 0 | 8332.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 |  | 0 | 0 | 29.93 | 1d | 0 | 0 | 0 | 29.93 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 |  | 0 | 0 | 14.43 | 1d | 0 | 0 | 0 | 14.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 |  | 0 | 0 | 1598.6899 | 1d | 0 | 0 | 0 | 1598.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 |  | 0 | 0 | 6829.4302 | 8d | 0 | 0 | 0 | 6829.4302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 |  | 0 | 0 | 4268.3999 | 5d | 0 | 0 | 0 | 4268.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 |  | 0 | 0 | 2695.8999 | 3d | 0 | 0 | 0 | 2695.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 |  | 0 | 0 | 898.63 | 1d | 0 | 0 | 0 | 898.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 |  | 0 | 0 | 1194.5 | 1d | 0 | 0 | 0 | 1194.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 |  | 0 | 0 | 3583.5 | 3d | 0 | 0 | 0 | 3583.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 |  | 0 | 0 | 2957.3799 | 1d | 0 | 0 | 0 | 2957.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 |  | 0 | 0 | 8872.1504 | 3d | 0 | 0 | 0 | 8872.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 7d | [5 empty] | 0 |  | 50% |  | 27 | 27
58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2006-05-19 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 |  | 0 | 0 | 27 | 1d | 0 | 0 | 0 | 27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 |  | 0 | 0 | 8574.7402 | 3d | 0 | 0 | 0 | 8574.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2006-06-30 17:00 |  | TP Name | 30/06, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 48d | [5 empty] | 66893.9902 |  | 39.74% |  | 71714.6202 | 88814.41
62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 100% | Finished | 1359.3101 | 1359.3101 | 100 | 100 | 100 | 100 | 63.9626 | 100
61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 100% | Finished | 214.62 | 214.62 | 100 | 100 | 100 | 100 | 177.579 | 100
1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 46d | [5 empty] | 64858.5901 |  | 97.76% |  | 69143.4502 | 70726.4302
2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 7d | 12649.1201 | 0 | 0 | -768.98 | 0 | 11880.1401 | 0 | 100% | Finished | 12649.1201 | 12649.1201 | 100 | 100 | 100 | 100 | 93.9207 | 100
3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 2006-05-12 08:00 | 33d | 50655.3203 | 0 | 3d | -3515.3501 | 0 | 47139.9702 | 0 | 91.67% | Started | 50655.3203 | 50655.3203 | 100 | 103.125 | 91.6667 | 100 | 93.0603 | 91.6667
4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 |  | 0 | 0 | 1582.98 | 1d | 0 | 0 | 0 | 1582.98 | 0% | Not Started | 0 | 1582.98 | 100 |  | 0 | 100 |  | 0
5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 2006-05-12 08:00 | 1d | 5839.0098 | 0 | 0 | -0.53 | 0 | 5838.4798 | 0 | 100% | Finished | 5839.0098 | 5839.0098 | 100 | 100 | 100 | 100 | 99.9909 | 100
6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 558.86
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 |  | 0 | 0 | 558.86 | 1d | 0 | 0 | 0 | 558.86 | 0% | Not Started | 0 | 558.86 | 100 |  | 0 | 100 |  | 0
8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 |  | 0 | 0 | 1117.71 | 2d | 0 | 0 | 0 | 1117.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 4d | [5 empty] | 784.83 |  | 14.29% |  | 970.24 | 6791.6599
10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 | 2006-06-27 08:00 | 1d | 970.24 | 0 | 0 | -185.41 | 0 | 784.83 | 0 | 100% | Finished | 970.24 | 970.24 | 100 | 100 | 100 | 100 | 80.8903 | 100
11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 |  | 0 | 0 | 5821.4199 | 6d | 0 | 0 | 0 | 5821.4199 | 0% | Not Started | 0 | 5821.4199 | 100 |  | 0 | 100 |  | 0
12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2313.3
13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 |  | 0 | 0 | 2313.3 | 2d | 0 | 0 | 0 | 2313.3 | 0% | Not Started | 0 | 2313.3 | 100 |  | 0 | 100 |  | 0
14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 |  | 0 | 0 | 1156.65 | 1d | 0 | 0 | 0 | 1156.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 |  | 0 | 0 | 3469.96 | 3d | 0 | 0 | 0 | 3469.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6823.2299
17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 5524.2998
18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 |  | 0 | 0 | 5524.2998 | 1d | 0 | 0 | 0 | 5524.2998 | 0% | Not Started | 0 | 5524.2998 | 100 |  | 0 | 100 |  | 0
19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 |  | 0 | 0 | 11048.5898 | 2d | 0 | 0 | 0 | 11048.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1298.9301
21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 |  | 0 | 0 | 1298.9301 | 1d | 0 | 0 | 0 | 1298.9301 | 0% | Not Started | 0 | 1298.9301 | 100 |  | 0 | 100 |  | 0
22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 |  | 0 | 0 | 1298.9301 | 1d | 0 | 0 | 0 | 1298.9301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 |  | 0 | 0 | 11733.46 | 4d | 0 | 0 | 0 | 11733.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 |  | 0 | 0 | 3594.54 | 4d | 0 | 0 | 0 | 3594.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 |  | 0 | 0 | 1014.92 | 2d | 0 | 0 | 0 | 1014.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 |  | 0 | 0 | 8332.7402 | 20d | 0 | 0 | 0 | 8332.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 |  | 0 | 0 | 29.93 | 1d | 0 | 0 | 0 | 29.93 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 |  | 0 | 0 | 14.43 | 1d | 0 | 0 | 0 | 14.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 |  | 0 | 0 | 1598.6899 | 1d | 0 | 0 | 0 | 1598.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 |  | 0 | 0 | 6829.4302 | 8d | 0 | 0 | 0 | 6829.4302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 |  | 0 | 0 | 4268.3999 | 5d | 0 | 0 | 0 | 4268.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 |  | 0 | 0 | 2695.8999 | 3d | 0 | 0 | 0 | 2695.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 |  | 0 | 0 | 898.63 | 1d | 0 | 0 | 0 | 898.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 |  | 0 | 0 | 1194.5 | 1d | 0 | 0 | 0 | 1194.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 |  | 0 | 0 | 3583.5 | 3d | 0 | 0 | 0 | 3583.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 |  | 0 | 0 | 2957.3799 | 1d | 0 | 0 | 0 | 2957.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 |  | 0 | 0 | 8872.1504 | 3d | 0 | 0 | 0 | 8872.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 28d | [5 empty] | 0 |  | 50% |  | 27 | 27
58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2006-05-19 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 |  | 0 | 0 | 27 | 1d | 0 | 0 | 0 | 27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 |  | 0 | 0 | 8574.7402 | 3d | 0 | 0 | 0 | 8574.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2006-07-31 17:00 |  | TP Name | 31/07, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 63d | [5 empty] | 88759.39 |  | 52.39% |  | 94558.73 | 93441.02
62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 100% | Finished | 1359.3101 | 1359.3101 | 100 | 100 | 100 | 100 | 63.9626 | 100
61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 100% | Finished | 214.62 | 214.62 | 100 | 100 | 100 | 100 | 177.579 | 100
1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 50d | [5 empty] | 66331.7201 |  | 100% |  | 70726.4302 | 70726.4302
2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 7d | 12649.1201 | 0 | 0 | -768.98 | 0 | 11880.1401 | 0 | 100% | Finished | 12649.1201 | 12649.1201 | 100 | 100 | 100 | 100 | 93.9207 | 100
3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 2006-05-12 08:00 | 36d | 50655.3203 | 0 | 0 | -3515.3501 | 0 | 47139.9702 | 0 | 100% | Finished | 50655.3203 | 50655.3203 | 100 | 112.5 | 100 | 100 | 93.0603 | 100
4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 | 2006-07-06 08:00 | 1d | 1582.98 | 0 | 0 | -109.85 | 0 | 1473.13 | 0 | 100% | Finished | 1582.98 | 1582.98 | 100 | 100 | 100 | 100 | 93.0606 | 100
5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 2006-05-12 08:00 | 1d | 5839.0098 | 0 | 0 | -0.53 | 0 | 5838.4798 | 0 | 100% | Finished | 5839.0098 | 5839.0098 | 100 | 100 | 100 | 100 | 99.9909 | 100
6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 10d | [5 empty] | 2236 |  | 100% |  | 1676.5699 | 558.86
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 | 2006-07-10 08:00 | 1d | 558.86 | 0 | 0 | 186.48 | 0 | 745.34 | 0 | 100% | Finished | 558.86 | 558.86 | 100 | 100 | 100 | 100 | 133.3679 | 100
8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 | 2006-07-20 08:00 | 2d | 1117.71 | 0 | 0 | 372.95 | 0 | 1490.66 | 0 | 100% | Finished | 1117.71 | 0 | 100 | 100 | 100 | 100 | 133.3673 | 100
9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 11d | [5 empty] | 5493.7799 |  | 100% |  | 6791.6599 | 6791.6599
10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 | 2006-06-27 08:00 | 1d | 970.24 | 0 | 0 | -185.41 | 0 | 784.83 | 0 | 100% | Finished | 970.24 | 970.24 | 100 | 100 | 100 | 100 | 80.8903 | 100
11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 | 2006-07-06 08:00 | 4d | 5821.4199 | 0 | 0 | -1112.47 | 0 | 4708.95 | 0 | 100% | Finished | 5821.4199 | 5821.4199 | 100 | 66.6667 | 100 | 100 | 80.8901 | 100
12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 4d | [5 empty] | 6475.53 |  | 100% |  | 6939.91 | 6939.91
13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 | 2006-07-12 08:00 | 1d | 2313.3 | 0 | 0 | -154.79 | 0 | 2158.5101 | 0 | 100% | Finished | 2313.3 | 2313.3 | 100 | 50 | 100 | 100 | 93.3087 | 100
14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 | 2006-07-13 08:00 | 1d | 1156.65 | 0 | 0 | -77.4 | 0 | 1079.25 | 0 | 100% | Finished | 1156.65 | 1156.65 | 100 | 100 | 100 | 100 | 93.3083 | 100
15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 | 2006-07-14 08:00 | 2d | 3469.96 | 0 | 0 | -232.19 | 0 | 3237.77 | 0 | 100% | Finished | 3469.96 | 3469.96 | 100 | 66.6667 | 100 | 100 | 93.3086 | 100
16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 8d | [5 empty] | 6971.7899 |  | 35.59% |  | 6823.2299 | 6823.2299
17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 8d | [5 empty] | 5809.9498 |  | 33.33% |  | 5524.2998 | 5524.2998
18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 | 2006-07-12 08:00 | 1d | 5524.2998 | 0 | 0 | 285.65 | 0 | 5809.9498 | 0 | 100% | Finished | 5524.2998 | 5524.2998 | 100 | 100 | 100 | 100 | 105.1708 | 100
19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 |  | 0 | 0 | 11048.5898 | 2d | 0 | 0 | 0 | 11048.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 6d | [5 empty] | 1161.8401 |  | 50% |  | 1298.9301 | 1298.9301
21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-07-14 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 |  | 0 | 0 | 1298.9301 | 1d | 0 | 0 | 0 | 1298.9301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 |  | 0 | 0 | 11733.46 | 4d | 0 | 0 | 0 | 11733.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 |  | 0 | 0 | 3594.54 | 4d | 0 | 0 | 0 | 3594.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 |  | 0 | 0 | 1014.92 | 2d | 0 | 0 | 0 | 1014.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 |  | 0 | 0 | 8332.7402 | 20d | 0 | 0 | 0 | 8332.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 |  | 0 | 0 | 29.93 | 1d | 0 | 0 | 0 | 29.93 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 |  | 0 | 0 | 14.43 | 1d | 0 | 0 | 0 | 14.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 |  | 0 | 0 | 1598.6899 | 1d | 0 | 0 | 0 | 1598.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 |  | 0 | 0 | 6829.4302 | 8d | 0 | 0 | 0 | 6829.4302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 |  | 0 | 0 | 4268.3999 | 5d | 0 | 0 | 0 | 4268.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 |  | 0 | 0 | 2695.8999 | 3d | 0 | 0 | 0 | 2695.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 |  | 0 | 0 | 898.63 | 1d | 0 | 0 | 0 | 898.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 |  | 0 | 0 | 1194.5 | 1d | 0 | 0 | 0 | 1194.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 |  | 0 | 0 | 3583.5 | 3d | 0 | 0 | 0 | 3583.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 |  | 0 | 0 | 2957.3799 | 1d | 0 | 0 | 0 | 2957.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 |  | 0 | 0 | 8872.1504 | 3d | 0 | 0 | 0 | 8872.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 43d | [5 empty] | 0 |  | 50% |  | 27 | 27
58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2006-05-19 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 |  | 0 | 0 | 27 | 1d | 0 | 0 | 0 | 27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 |  | 0 | 0 | 8574.7402 | 3d | 0 | 0 | 0 | 8574.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2006-08-31 17:00 |  | TP Name | 31/08, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 75d | [5 empty] | 99985.5099 |  | 58.9% |  | 106292.1899 | 111571.04
62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 100% | Finished | 1359.3101 | 1359.3101 | 100 | 100 | 100 | 100 | 63.9626 | 100
61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 100% | Finished | 214.62 | 214.62 | 100 | 100 | 100 | 100 | 177.579 | 100
1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 50d | [5 empty] | 66331.7201 |  | 100% |  | 70726.4302 | 70726.4302
2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 7d | 12649.1201 | 0 | 0 | -768.98 | 0 | 11880.1401 | 0 | 100% | Finished | 12649.1201 | 12649.1201 | 100 | 100 | 100 | 100 | 93.9207 | 100
3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 2006-05-12 08:00 | 36d | 50655.3203 | 0 | 0 | -3515.3501 | 0 | 47139.9702 | 0 | 100% | Finished | 50655.3203 | 50655.3203 | 100 | 112.5 | 100 | 100 | 93.0603 | 100
4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 | 2006-07-06 08:00 | 1d | 1582.98 | 0 | 0 | -109.85 | 0 | 1473.13 | 0 | 100% | Finished | 1582.98 | 1582.98 | 100 | 100 | 100 | 100 | 93.0606 | 100
5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 2006-05-12 08:00 | 1d | 5839.0098 | 0 | 0 | -0.53 | 0 | 5838.4798 | 0 | 100% | Finished | 5839.0098 | 5839.0098 | 100 | 100 | 100 | 100 | 99.9909 | 100
6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 10d | [5 empty] | 2236 |  | 100% |  | 1676.5699 | 1676.5699
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 | 2006-07-10 08:00 | 1d | 558.86 | 0 | 0 | 186.48 | 0 | 745.34 | 0 | 100% | Finished | 558.86 | 558.86 | 100 | 100 | 100 | 100 | 133.3679 | 100
8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 | 2006-07-20 08:00 | 2d | 1117.71 | 0 | 0 | 372.95 | 0 | 1490.66 | 0 | 100% | Finished | 1117.71 | 1117.71 | 100 | 100 | 100 | 100 | 133.3673 | 100
9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 11d | [5 empty] | 5493.7799 |  | 100% |  | 6791.6599 | 6791.6599
10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 | 2006-06-27 08:00 | 1d | 970.24 | 0 | 0 | -185.41 | 0 | 784.83 | 0 | 100% | Finished | 970.24 | 970.24 | 100 | 100 | 100 | 100 | 80.8903 | 100
11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 | 2006-07-06 08:00 | 4d | 5821.4199 | 0 | 0 | -1112.47 | 0 | 4708.95 | 0 | 100% | Finished | 5821.4199 | 5821.4199 | 100 | 66.6667 | 100 | 100 | 80.8901 | 100
12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 4d | [5 empty] | 6475.53 |  | 100% |  | 6939.91 | 6939.91
13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 | 2006-07-12 08:00 | 1d | 2313.3 | 0 | 0 | -154.79 | 0 | 2158.5101 | 0 | 100% | Finished | 2313.3 | 2313.3 | 100 | 50 | 100 | 100 | 93.3087 | 100
14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 | 2006-07-13 08:00 | 1d | 1156.65 | 0 | 0 | -77.4 | 0 | 1079.25 | 0 | 100% | Finished | 1156.65 | 1156.65 | 100 | 100 | 100 | 100 | 93.3083 | 100
15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 | 2006-07-14 08:00 | 2d | 3469.96 | 0 | 0 | -232.19 | 0 | 3237.77 | 0 | 100% | Finished | 3469.96 | 3469.96 | 100 | 66.6667 | 100 | 100 | 93.3086 | 100
16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 20d | [5 empty] | 6971.7899 |  | 35.59% |  | 6823.2299 | 6823.2299
17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 20d | [5 empty] | 5809.9498 |  | 33.33% |  | 5524.2998 | 5524.2998
18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 | 2006-07-12 08:00 | 1d | 5524.2998 | 0 | 0 | 285.65 | 0 | 5809.9498 | 0 | 100% | Finished | 5524.2998 | 5524.2998 | 100 | 100 | 100 | 100 | 105.1708 | 100
19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 |  | 0 | 0 | 11048.5898 | 2d | 0 | 0 | 0 | 11048.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 18d | [5 empty] | 1161.8401 |  | 50% |  | 1298.9301 | 1298.9301
21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-07-14 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 |  | 0 | 0 | 1298.9301 | 1d | 0 | 0 | 0 | 1298.9301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 | 2006-08-25 08:00 | 4d | 11733.46 | 0 | 0 | -507.34 | 0 | 11226.12 | 0 | 100% | Finished | 11733.46 | 11733.46 | 100 | 100 | 100 | 100 | 95.6761 | 100
25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 |  | 0 | 0 | 3594.54 | 4d | 0 | 0 | 0 | 3594.54 | 0% | Not Started | 0 | 3594.54 | 100 |  | 0 | 100 |  | 0
26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 1684.3101 | 100 |  | 0 | 100 |  | 0
27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 |  | 0 | 0 | 1014.92 | 2d | 0 | 0 | 0 | 1014.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 |  | 0 | 0 | 8332.7402 | 20d | 0 | 0 | 0 | 8332.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 |  | 0 | 0 | 29.93 | 1d | 0 | 0 | 0 | 29.93 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 |  | 0 | 0 | 14.43 | 1d | 0 | 0 | 0 | 14.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 |  | 0 | 0 | 1598.6899 | 1d | 0 | 0 | 0 | 1598.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 |  | 0 | 0 | 6829.4302 | 8d | 0 | 0 | 0 | 6829.4302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 |  | 0 | 0 | 4268.3999 | 5d | 0 | 0 | 0 | 4268.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 |  | 0 | 0 | 2695.8999 | 3d | 0 | 0 | 0 | 2695.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 |  | 0 | 0 | 898.63 | 1d | 0 | 0 | 0 | 898.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 |  | 0 | 0 | 1194.5 | 1d | 0 | 0 | 0 | 1194.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 |  | 0 | 0 | 3583.5 | 3d | 0 | 0 | 0 | 3583.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 |  | 0 | 0 | 2957.3799 | 1d | 0 | 0 | 0 | 2957.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 |  | 0 | 0 | 8872.1504 | 3d | 0 | 0 | 0 | 8872.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 55d | [5 empty] | 0 |  | 50% |  | 27 | 27
58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2006-05-19 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 |  | 0 | 0 | 27 | 1d | 0 | 0 | 0 | 27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 |  | 0 | 0 | 8574.7402 | 3d | 0 | 0 | 0 | 8574.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2006-09-30 17:00 |  | TP Name | 30/09, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 96d | [5 empty] | 127768.2101 |  | 73.94% |  | 133445.1402 | 133445.1402
62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 100% | Finished | 1359.3101 | 1359.3101 | 100 | 100 | 100 | 100 | 63.9626 | 100
61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 100% | Finished | 214.62 | 214.62 | 100 | 100 | 100 | 100 | 177.579 | 100
1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 50d | [5 empty] | 66331.7201 |  | 100% |  | 70726.4302 | 70726.4302
2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 7d | 12649.1201 | 0 | 0 | -768.98 | 0 | 11880.1401 | 0 | 100% | Finished | 12649.1201 | 12649.1201 | 100 | 100 | 100 | 100 | 93.9207 | 100
3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 2006-05-12 08:00 | 36d | 50655.3203 | 0 | 0 | -3515.3501 | 0 | 47139.9702 | 0 | 100% | Finished | 50655.3203 | 50655.3203 | 100 | 112.5 | 100 | 100 | 93.0603 | 100
4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 | 2006-07-06 08:00 | 1d | 1582.98 | 0 | 0 | -109.85 | 0 | 1473.13 | 0 | 100% | Finished | 1582.98 | 1582.98 | 100 | 100 | 100 | 100 | 93.0606 | 100
5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 2006-05-12 08:00 | 1d | 5839.0098 | 0 | 0 | -0.53 | 0 | 5838.4798 | 0 | 100% | Finished | 5839.0098 | 5839.0098 | 100 | 100 | 100 | 100 | 99.9909 | 100
6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 10d | [5 empty] | 2236 |  | 100% |  | 1676.5699 | 1676.5699
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 | 2006-07-10 08:00 | 1d | 558.86 | 0 | 0 | 186.48 | 0 | 745.34 | 0 | 100% | Finished | 558.86 | 558.86 | 100 | 100 | 100 | 100 | 133.3679 | 100
8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 | 2006-07-20 08:00 | 2d | 1117.71 | 0 | 0 | 372.95 | 0 | 1490.66 | 0 | 100% | Finished | 1117.71 | 1117.71 | 100 | 100 | 100 | 100 | 133.3673 | 100
9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 11d | [5 empty] | 5493.7799 |  | 100% |  | 6791.6599 | 6791.6599
10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 | 2006-06-27 08:00 | 1d | 970.24 | 0 | 0 | -185.41 | 0 | 784.83 | 0 | 100% | Finished | 970.24 | 970.24 | 100 | 100 | 100 | 100 | 80.8903 | 100
11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 | 2006-07-06 08:00 | 4d | 5821.4199 | 0 | 0 | -1112.47 | 0 | 4708.95 | 0 | 100% | Finished | 5821.4199 | 5821.4199 | 100 | 66.6667 | 100 | 100 | 80.8901 | 100
12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 4d | [5 empty] | 6475.53 |  | 100% |  | 6939.91 | 6939.91
13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 | 2006-07-12 08:00 | 1d | 2313.3 | 0 | 0 | -154.79 | 0 | 2158.5101 | 0 | 100% | Finished | 2313.3 | 2313.3 | 100 | 50 | 100 | 100 | 93.3087 | 100
14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 | 2006-07-13 08:00 | 1d | 1156.65 | 0 | 0 | -77.4 | 0 | 1079.25 | 0 | 100% | Finished | 1156.65 | 1156.65 | 100 | 100 | 100 | 100 | 93.3083 | 100
15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 | 2006-07-14 08:00 | 2d | 3469.96 | 0 | 0 | -232.19 | 0 | 3237.77 | 0 | 100% | Finished | 3469.96 | 3469.96 | 100 | 66.6667 | 100 | 100 | 93.3086 | 100
16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 36d | [5 empty] | 19753.5097 |  | 100% |  | 19170.7498 | 19170.7498
17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 30d | [5 empty] | 17429.8296 |  | 100% |  | 16572.8896 | 16572.8896
18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 | 2006-07-12 08:00 | 1d | 5524.2998 | 0 | 0 | 285.65 | 0 | 5809.9498 | 0 | 100% | Finished | 5524.2998 | 5524.2998 | 100 | 100 | 100 | 100 | 105.1708 | 100
19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 | 2006-09-13 08:00 | 2d | 11048.5898 | 0 | 0 | 571.29 | 0 | 11619.8798 | 0 | 100% | Finished | 11048.5898 | 11048.5898 | 100 | 100 | 100 | 100 | 105.1707 | 100
20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 34d | [5 empty] | 2323.6801 |  | 100% |  | 2597.8601 | 2597.8601
21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-07-14 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-09-22 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 | 2006-08-25 08:00 | 4d | 11733.46 | 0 | 0 | -507.34 | 0 | 11226.12 | 0 | 100% | Finished | 11733.46 | 11733.46 | 100 | 100 | 100 | 100 | 95.6761 | 100
25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 | 2006-09-05 08:00 | 4d | 3594.54 | 0 | 0 | 322.35 | 0 | 3916.89 | 0 | 100% | Finished | 3594.54 | 3594.54 | 100 | 100 | 100 | 100 | 108.9678 | 100
26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 | 2006-09-01 08:00 | 1d | 1684.3101 | 0 | 0 | -188.45 | 0 | 1495.8601 | 0 | 100% | Finished | 1684.3101 | 1684.3101 | 100 | 100 | 100 | 100 | 88.8114 | 100
27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 | 2006-09-13 08:00 | 2d | 1014.92 | 0 | 0 | 173.08 | 0 | 1188 | 0 | 100% | Finished | 1014.92 | 1014.92 | 100 | 100 | 100 | 100 | 117.0536 | 100
28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 | 2006-09-27 08:00 | 3d | 8332.7402 | 0 | 19d | -87.65 | 0 | 8245.0902 | 0 | 13.64% | Started | 8332.7402 | 8332.7402 | 100 | 15 | 13.6364 | 100 | 98.9481 | 13.6364
29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 1d | [5 empty] | 155.14 |  | 33.33% |  | 178.92 | 178.92
30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-09-29 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 |  | 0 | 0 | 29.93 | 1d | 0 | 0 | 0 | 29.93 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 |  | 0 | 0 | 14.43 | 1d | 0 | 0 | 0 | 14.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 |  | 0 | 0 | 1598.6899 | 1d | 0 | 0 | 0 | 1598.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 |  | 0 | 0 | 6829.4302 | 8d | 0 | 0 | 0 | 6829.4302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 |  | 0 | 0 | 4268.3999 | 5d | 0 | 0 | 0 | 4268.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 |  | 0 | 0 | 2695.8999 | 3d | 0 | 0 | 0 | 2695.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 |  | 0 | 0 | 898.63 | 1d | 0 | 0 | 0 | 898.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 |  | 0 | 0 | 1194.5 | 1d | 0 | 0 | 0 | 1194.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 |  | 0 | 0 | 3583.5 | 3d | 0 | 0 | 0 | 3583.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 |  | 0 | 0 | 2957.3799 | 1d | 0 | 0 | 0 | 2957.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 |  | 0 | 0 | 8872.1504 | 3d | 0 | 0 | 0 | 8872.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 76d | [5 empty] | 0 |  | 50% |  | 27 | 27
58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2006-05-19 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 |  | 0 | 0 | 27 | 1d | 0 | 0 | 0 | 27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 |  | 0 | 0 | 8574.7402 | 3d | 0 | 0 | 0 | 8574.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2006-10-31 17:00 |  | TP Name | 31/10, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 118d | [5 empty] | 127793.0001 |  | 73.96% |  | 133475.0702 | 142275.4603
62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 100% | Finished | 1359.3101 | 1359.3101 | 100 | 100 | 100 | 100 | 63.9626 | 100
61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 100% | Finished | 214.62 | 214.62 | 100 | 100 | 100 | 100 | 177.579 | 100
1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 50d | [5 empty] | 66331.7201 |  | 100% |  | 70726.4302 | 70726.4302
2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 7d | 12649.1201 | 0 | 0 | -768.98 | 0 | 11880.1401 | 0 | 100% | Finished | 12649.1201 | 12649.1201 | 100 | 100 | 100 | 100 | 93.9207 | 100
3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 2006-05-12 08:00 | 36d | 50655.3203 | 0 | 0 | -3515.3501 | 0 | 47139.9702 | 0 | 100% | Finished | 50655.3203 | 50655.3203 | 100 | 112.5 | 100 | 100 | 93.0603 | 100
4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 | 2006-07-06 08:00 | 1d | 1582.98 | 0 | 0 | -109.85 | 0 | 1473.13 | 0 | 100% | Finished | 1582.98 | 1582.98 | 100 | 100 | 100 | 100 | 93.0606 | 100
5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 2006-05-12 08:00 | 1d | 5839.0098 | 0 | 0 | -0.53 | 0 | 5838.4798 | 0 | 100% | Finished | 5839.0098 | 5839.0098 | 100 | 100 | 100 | 100 | 99.9909 | 100
6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 10d | [5 empty] | 2236 |  | 100% |  | 1676.5699 | 1676.5699
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 | 2006-07-10 08:00 | 1d | 558.86 | 0 | 0 | 186.48 | 0 | 745.34 | 0 | 100% | Finished | 558.86 | 558.86 | 100 | 100 | 100 | 100 | 133.3679 | 100
8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 | 2006-07-20 08:00 | 2d | 1117.71 | 0 | 0 | 372.95 | 0 | 1490.66 | 0 | 100% | Finished | 1117.71 | 1117.71 | 100 | 100 | 100 | 100 | 133.3673 | 100
9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 11d | [5 empty] | 5493.7799 |  | 100% |  | 6791.6599 | 6791.6599
10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 | 2006-06-27 08:00 | 1d | 970.24 | 0 | 0 | -185.41 | 0 | 784.83 | 0 | 100% | Finished | 970.24 | 970.24 | 100 | 100 | 100 | 100 | 80.8903 | 100
11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 | 2006-07-06 08:00 | 4d | 5821.4199 | 0 | 0 | -1112.47 | 0 | 4708.95 | 0 | 100% | Finished | 5821.4199 | 5821.4199 | 100 | 66.6667 | 100 | 100 | 80.8901 | 100
12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 4d | [5 empty] | 6475.53 |  | 100% |  | 6939.91 | 6939.91
13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 | 2006-07-12 08:00 | 1d | 2313.3 | 0 | 0 | -154.79 | 0 | 2158.5101 | 0 | 100% | Finished | 2313.3 | 2313.3 | 100 | 50 | 100 | 100 | 93.3087 | 100
14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 | 2006-07-13 08:00 | 1d | 1156.65 | 0 | 0 | -77.4 | 0 | 1079.25 | 0 | 100% | Finished | 1156.65 | 1156.65 | 100 | 100 | 100 | 100 | 93.3083 | 100
15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 | 2006-07-14 08:00 | 2d | 3469.96 | 0 | 0 | -232.19 | 0 | 3237.77 | 0 | 100% | Finished | 3469.96 | 3469.96 | 100 | 66.6667 | 100 | 100 | 93.3086 | 100
16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 36d | [5 empty] | 19753.5097 |  | 100% |  | 19170.7498 | 19170.7498
17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 30d | [5 empty] | 17429.8296 |  | 100% |  | 16572.8896 | 16572.8896
18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 | 2006-07-12 08:00 | 1d | 5524.2998 | 0 | 0 | 285.65 | 0 | 5809.9498 | 0 | 100% | Finished | 5524.2998 | 5524.2998 | 100 | 100 | 100 | 100 | 105.1708 | 100
19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 | 2006-09-13 08:00 | 2d | 11048.5898 | 0 | 0 | 571.29 | 0 | 11619.8798 | 0 | 100% | Finished | 11048.5898 | 11048.5898 | 100 | 100 | 100 | 100 | 105.1707 | 100
20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 34d | [5 empty] | 2323.6801 |  | 100% |  | 2597.8601 | 2597.8601
21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-07-14 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-09-22 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 | 2006-08-25 08:00 | 4d | 11733.46 | 0 | 0 | -507.34 | 0 | 11226.12 | 0 | 100% | Finished | 11733.46 | 11733.46 | 100 | 100 | 100 | 100 | 95.6761 | 100
25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 | 2006-09-05 08:00 | 4d | 3594.54 | 0 | 0 | 322.35 | 0 | 3916.89 | 0 | 100% | Finished | 3594.54 | 3594.54 | 100 | 100 | 100 | 100 | 108.9678 | 100
26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 | 2006-09-01 08:00 | 1d | 1684.3101 | 0 | 0 | -188.45 | 0 | 1495.8601 | 0 | 100% | Finished | 1684.3101 | 1684.3101 | 100 | 100 | 100 | 100 | 88.8114 | 100
27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 | 2006-09-13 08:00 | 2d | 1014.92 | 0 | 0 | 173.08 | 0 | 1188 | 0 | 100% | Finished | 1014.92 | 1014.92 | 100 | 100 | 100 | 100 | 117.0536 | 100
28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 | 2006-09-27 08:00 | 22d | 8332.7402 | 0 | 0 | -87.65 | 0 | 8245.0902 | 0 | 100% | Finished | 8332.7402 | 8332.7402 | 100 | 110 | 100 | 100 | 98.9481 | 100
29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 23d | [5 empty] | 155.14 |  | 33.33% |  | 178.92 | 536.76
30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-09-29 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 178.92 | 100 |  | 0 | 100 |  | 0
32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 |  | 0 | 0 | 178.92 | 1d | 0 | 0 | 0 | 178.92 | 0% | Not Started | 0 | 178.92 | 100 |  | 0 | 100 |  | 0
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 | 2006-10-30 08:00 | 1d | 29.93 | 0 | 0 | -5.14 | 0 | 24.79 | 0 | 100% | Finished | 29.93 | 29.93 | 100 | 100 | 100 | 100 | 82.8266 | 100
63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 |  | 0 | 0 | 14.43 | 1d | 0 | 0 | 0 | 14.43 | 0% | Not Started | 0 | 14.43 | 100 |  | 0 | 100 |  | 0
34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 |  | 0 | 0 | 1598.6899 | 1d | 0 | 0 | 0 | 1598.6899 | 0% | Not Started | 0 | 1598.6899 | 100 |  | 0 | 100 |  | 0
35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6829.4302
36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 |  | 0 | 0 | 6829.4302 | 8d | 0 | 0 | 0 | 6829.4302 | 0% | Not Started | 0 | 6829.4302 | 100 |  | 0 | 100 |  | 0
37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 |  | 0 | 0 | 4268.3999 | 5d | 0 | 0 | 0 | 4268.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 |  | 0 | 0 | 2695.8999 | 3d | 0 | 0 | 0 | 2695.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 |  | 0 | 0 | 898.63 | 1d | 0 | 0 | 0 | 898.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 |  | 0 | 0 | 1194.5 | 1d | 0 | 0 | 0 | 1194.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 |  | 0 | 0 | 3583.5 | 3d | 0 | 0 | 0 | 3583.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 |  | 0 | 0 | 2957.3799 | 1d | 0 | 0 | 0 | 2957.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 |  | 0 | 0 | 8872.1504 | 3d | 0 | 0 | 0 | 8872.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 98d | [5 empty] | 0 |  | 50% |  | 27 | 27
58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2006-05-19 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 |  | 0 | 0 | 27 | 1d | 0 | 0 | 0 | 27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 |  | 0 | 0 | 8574.7402 | 3d | 0 | 0 | 0 | 8574.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2006-11-30 17:00 |  | TP Name | 30/11, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 137d | [5 empty] | 139630.7701 |  | 80.5% |  | 145276.1301 | 155113.8899
62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 100% | Finished | 1359.3101 | 1359.3101 | 100 | 100 | 100 | 100 | 63.9626 | 100
61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 100% | Finished | 214.62 | 214.62 | 100 | 100 | 100 | 100 | 177.579 | 100
1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 50d | [5 empty] | 66331.7201 |  | 100% |  | 70726.4302 | 70726.4302
2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 7d | 12649.1201 | 0 | 0 | -768.98 | 0 | 11880.1401 | 0 | 100% | Finished | 12649.1201 | 12649.1201 | 100 | 100 | 100 | 100 | 93.9207 | 100
3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 2006-05-12 08:00 | 36d | 50655.3203 | 0 | 0 | -3515.3501 | 0 | 47139.9702 | 0 | 100% | Finished | 50655.3203 | 50655.3203 | 100 | 112.5 | 100 | 100 | 93.0603 | 100
4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 | 2006-07-06 08:00 | 1d | 1582.98 | 0 | 0 | -109.85 | 0 | 1473.13 | 0 | 100% | Finished | 1582.98 | 1582.98 | 100 | 100 | 100 | 100 | 93.0606 | 100
5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 2006-05-12 08:00 | 1d | 5839.0098 | 0 | 0 | -0.53 | 0 | 5838.4798 | 0 | 100% | Finished | 5839.0098 | 5839.0098 | 100 | 100 | 100 | 100 | 99.9909 | 100
6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 10d | [5 empty] | 2236 |  | 100% |  | 1676.5699 | 1676.5699
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 | 2006-07-10 08:00 | 1d | 558.86 | 0 | 0 | 186.48 | 0 | 745.34 | 0 | 100% | Finished | 558.86 | 558.86 | 100 | 100 | 100 | 100 | 133.3679 | 100
8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 | 2006-07-20 08:00 | 2d | 1117.71 | 0 | 0 | 372.95 | 0 | 1490.66 | 0 | 100% | Finished | 1117.71 | 1117.71 | 100 | 100 | 100 | 100 | 133.3673 | 100
9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 11d | [5 empty] | 5493.7799 |  | 100% |  | 6791.6599 | 6791.6599
10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 | 2006-06-27 08:00 | 1d | 970.24 | 0 | 0 | -185.41 | 0 | 784.83 | 0 | 100% | Finished | 970.24 | 970.24 | 100 | 100 | 100 | 100 | 80.8903 | 100
11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 | 2006-07-06 08:00 | 4d | 5821.4199 | 0 | 0 | -1112.47 | 0 | 4708.95 | 0 | 100% | Finished | 5821.4199 | 5821.4199 | 100 | 66.6667 | 100 | 100 | 80.8901 | 100
12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 4d | [5 empty] | 6475.53 |  | 100% |  | 6939.91 | 6939.91
13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 | 2006-07-12 08:00 | 1d | 2313.3 | 0 | 0 | -154.79 | 0 | 2158.5101 | 0 | 100% | Finished | 2313.3 | 2313.3 | 100 | 50 | 100 | 100 | 93.3087 | 100
14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 | 2006-07-13 08:00 | 1d | 1156.65 | 0 | 0 | -77.4 | 0 | 1079.25 | 0 | 100% | Finished | 1156.65 | 1156.65 | 100 | 100 | 100 | 100 | 93.3083 | 100
15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 | 2006-07-14 08:00 | 2d | 3469.96 | 0 | 0 | -232.19 | 0 | 3237.77 | 0 | 100% | Finished | 3469.96 | 3469.96 | 100 | 66.6667 | 100 | 100 | 93.3086 | 100
16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 36d | [5 empty] | 19753.5097 |  | 100% |  | 19170.7498 | 19170.7498
17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 30d | [5 empty] | 17429.8296 |  | 100% |  | 16572.8896 | 16572.8896
18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 | 2006-07-12 08:00 | 1d | 5524.2998 | 0 | 0 | 285.65 | 0 | 5809.9498 | 0 | 100% | Finished | 5524.2998 | 5524.2998 | 100 | 100 | 100 | 100 | 105.1708 | 100
19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 | 2006-09-13 08:00 | 2d | 11048.5898 | 0 | 0 | 571.29 | 0 | 11619.8798 | 0 | 100% | Finished | 11048.5898 | 11048.5898 | 100 | 100 | 100 | 100 | 105.1707 | 100
20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 34d | [5 empty] | 2323.6801 |  | 100% |  | 2597.8601 | 2597.8601
21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-07-14 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-09-22 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 | 2006-08-25 08:00 | 4d | 11733.46 | 0 | 0 | -507.34 | 0 | 11226.12 | 0 | 100% | Finished | 11733.46 | 11733.46 | 100 | 100 | 100 | 100 | 95.6761 | 100
25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 | 2006-09-05 08:00 | 4d | 3594.54 | 0 | 0 | 322.35 | 0 | 3916.89 | 0 | 100% | Finished | 3594.54 | 3594.54 | 100 | 100 | 100 | 100 | 108.9678 | 100
26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 | 2006-09-01 08:00 | 1d | 1684.3101 | 0 | 0 | -188.45 | 0 | 1495.8601 | 0 | 100% | Finished | 1684.3101 | 1684.3101 | 100 | 100 | 100 | 100 | 88.8114 | 100
27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 | 2006-09-13 08:00 | 2d | 1014.92 | 0 | 0 | 173.08 | 0 | 1188 | 0 | 100% | Finished | 1014.92 | 1014.92 | 100 | 100 | 100 | 100 | 117.0536 | 100
28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 | 2006-09-27 08:00 | 22d | 8332.7402 | 0 | 0 | -87.65 | 0 | 8245.0902 | 0 | 100% | Finished | 8332.7402 | 8332.7402 | 100 | 110 | 100 | 100 | 98.9481 | 100
29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 28d | [5 empty] | 465.42 |  | 100% |  | 536.76 | 536.76
30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-09-29 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-11-06 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-11-10 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 | 2006-10-30 08:00 | 1d | 29.93 | 0 | 0 | -5.14 | 0 | 24.79 | 0 | 100% | Finished | 29.93 | 29.93 | 100 | 100 | 100 | 100 | 82.8266 | 100
63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 | 2006-11-21 08:00 | 1d | 14.43 | 0 | 0 | 0 | 0 | 14.43 | 0 | 100% | Finished | 14.43 | 14.43 | 100 | 100 | 100 | 100 | 100 | 100
34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 | 2006-11-07 08:00 | 1d | 1598.6899 | 0 | 0 | -6.89 | 0 | 1591.7999 | 0 | 100% | Finished | 1598.6899 | 1598.6899 | 100 | 100 | 100 | 100 | 99.569 | 100
35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 7d | [5 empty] | 6899.1302 |  | 61.54% |  | 6829.4302 | 11097.8301
36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 | 2006-11-22 08:00 | 7d | 6829.4302 | 0 | 1d | 69.7 | 0 | 6899.1302 | 0 | 87.5% | Started | 6829.4302 | 6829.4302 | 100 | 87.5 | 87.5 | 100 | 101.0206 | 87.5
37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 |  | 0 | 0 | 4268.3999 | 5d | 0 | 0 | 0 | 4268.3999 | 0% | Not Started | 0 | 4268.3999 | 100 |  | 0 | 100 |  | 0
38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2695.8999
39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 |  | 0 | 0 | 2695.8999 | 3d | 0 | 0 | 0 | 2695.8999 | 0% | Not Started | 0 | 2695.8999 | 100 |  | 0 | 100 |  | 0
40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 |  | 0 | 0 | 898.63 | 1d | 0 | 0 | 0 | 898.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1194.5
43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 |  | 0 | 0 | 1194.5 | 1d | 0 | 0 | 0 | 1194.5 | 0% | Not Started | 0 | 1194.5 | 100 |  | 0 | 100 |  | 0
44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 |  | 0 | 0 | 3583.5 | 3d | 0 | 0 | 0 | 3583.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1514.46
46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 1514.46 | 100 |  | 0 | 100 |  | 0
47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164.5
49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 164.5 | 100 |  | 0 | 100 |  | 0
50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 19d | [5 empty] | 2978.8399 |  | 25% |  | 2957.3799 | 2957.3799
52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 | 2006-11-06 08:00 | 1d | 2957.3799 | 0 | 0 | 21.46 | 0 | 2978.8399 | 0 | 100% | Finished | 2957.3799 | 2957.3799 | 100 | 100 | 100 | 100 | 100.7256 | 100
53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 |  | 0 | 0 | 8872.1504 | 3d | 0 | 0 | 0 | 8872.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 19d | [5 empty] | 43.29 |  | 50% |  | 43.29 | 43.29
55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 | 2006-11-06 08:00 | 1d | 43.29 | 0 | 0 | 0 | 0 | 43.29 | 0 | 100% | Finished | 43.29 | 43.29 | 100 | 100 | 100 | 100 | 100 | 100
56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 117d | [5 empty] | 0 |  | 50% |  | 27 | 27
58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2006-05-19 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 |  | 0 | 0 | 27 | 1d | 0 | 0 | 0 | 27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 |  | 0 | 0 | 8574.7402 | 3d | 0 | 0 | 0 | 8574.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2006-12-31 17:00 |  | TP Name | 31/12, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 153d | [5 empty] | 149832.7499 |  | 85.95% |  | 155113.8899 | 163029.5799
62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 100% | Finished | 1359.3101 | 1359.3101 | 100 | 100 | 100 | 100 | 63.9626 | 100
61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 100% | Finished | 214.62 | 214.62 | 100 | 100 | 100 | 100 | 177.579 | 100
1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 50d | [5 empty] | 66331.7201 |  | 100% |  | 70726.4302 | 70726.4302
2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 7d | 12649.1201 | 0 | 0 | -768.98 | 0 | 11880.1401 | 0 | 100% | Finished | 12649.1201 | 12649.1201 | 100 | 100 | 100 | 100 | 93.9207 | 100
3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 2006-05-12 08:00 | 36d | 50655.3203 | 0 | 0 | -3515.3501 | 0 | 47139.9702 | 0 | 100% | Finished | 50655.3203 | 50655.3203 | 100 | 112.5 | 100 | 100 | 93.0603 | 100
4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 | 2006-07-06 08:00 | 1d | 1582.98 | 0 | 0 | -109.85 | 0 | 1473.13 | 0 | 100% | Finished | 1582.98 | 1582.98 | 100 | 100 | 100 | 100 | 93.0606 | 100
5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 2006-05-12 08:00 | 1d | 5839.0098 | 0 | 0 | -0.53 | 0 | 5838.4798 | 0 | 100% | Finished | 5839.0098 | 5839.0098 | 100 | 100 | 100 | 100 | 99.9909 | 100
6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 10d | [5 empty] | 2236 |  | 100% |  | 1676.5699 | 1676.5699
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 | 2006-07-10 08:00 | 1d | 558.86 | 0 | 0 | 186.48 | 0 | 745.34 | 0 | 100% | Finished | 558.86 | 558.86 | 100 | 100 | 100 | 100 | 133.3679 | 100
8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 | 2006-07-20 08:00 | 2d | 1117.71 | 0 | 0 | 372.95 | 0 | 1490.66 | 0 | 100% | Finished | 1117.71 | 1117.71 | 100 | 100 | 100 | 100 | 133.3673 | 100
9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 11d | [5 empty] | 5493.7799 |  | 100% |  | 6791.6599 | 6791.6599
10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 | 2006-06-27 08:00 | 1d | 970.24 | 0 | 0 | -185.41 | 0 | 784.83 | 0 | 100% | Finished | 970.24 | 970.24 | 100 | 100 | 100 | 100 | 80.8903 | 100
11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 | 2006-07-06 08:00 | 4d | 5821.4199 | 0 | 0 | -1112.47 | 0 | 4708.95 | 0 | 100% | Finished | 5821.4199 | 5821.4199 | 100 | 66.6667 | 100 | 100 | 80.8901 | 100
12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 4d | [5 empty] | 6475.53 |  | 100% |  | 6939.91 | 6939.91
13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 | 2006-07-12 08:00 | 1d | 2313.3 | 0 | 0 | -154.79 | 0 | 2158.5101 | 0 | 100% | Finished | 2313.3 | 2313.3 | 100 | 50 | 100 | 100 | 93.3087 | 100
14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 | 2006-07-13 08:00 | 1d | 1156.65 | 0 | 0 | -77.4 | 0 | 1079.25 | 0 | 100% | Finished | 1156.65 | 1156.65 | 100 | 100 | 100 | 100 | 93.3083 | 100
15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 | 2006-07-14 08:00 | 2d | 3469.96 | 0 | 0 | -232.19 | 0 | 3237.77 | 0 | 100% | Finished | 3469.96 | 3469.96 | 100 | 66.6667 | 100 | 100 | 93.3086 | 100
16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 36d | [5 empty] | 19753.5097 |  | 100% |  | 19170.7498 | 19170.7498
17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 30d | [5 empty] | 17429.8296 |  | 100% |  | 16572.8896 | 16572.8896
18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 | 2006-07-12 08:00 | 1d | 5524.2998 | 0 | 0 | 285.65 | 0 | 5809.9498 | 0 | 100% | Finished | 5524.2998 | 5524.2998 | 100 | 100 | 100 | 100 | 105.1708 | 100
19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 | 2006-09-13 08:00 | 2d | 11048.5898 | 0 | 0 | 571.29 | 0 | 11619.8798 | 0 | 100% | Finished | 11048.5898 | 11048.5898 | 100 | 100 | 100 | 100 | 105.1707 | 100
20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 34d | [5 empty] | 2323.6801 |  | 100% |  | 2597.8601 | 2597.8601
21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-07-14 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-09-22 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 | 2006-08-25 08:00 | 4d | 11733.46 | 0 | 0 | -507.34 | 0 | 11226.12 | 0 | 100% | Finished | 11733.46 | 11733.46 | 100 | 100 | 100 | 100 | 95.6761 | 100
25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 | 2006-09-05 08:00 | 4d | 3594.54 | 0 | 0 | 322.35 | 0 | 3916.89 | 0 | 100% | Finished | 3594.54 | 3594.54 | 100 | 100 | 100 | 100 | 108.9678 | 100
26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 | 2006-09-01 08:00 | 1d | 1684.3101 | 0 | 0 | -188.45 | 0 | 1495.8601 | 0 | 100% | Finished | 1684.3101 | 1684.3101 | 100 | 100 | 100 | 100 | 88.8114 | 100
27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 | 2006-09-13 08:00 | 2d | 1014.92 | 0 | 0 | 173.08 | 0 | 1188 | 0 | 100% | Finished | 1014.92 | 1014.92 | 100 | 100 | 100 | 100 | 117.0536 | 100
28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 | 2006-09-27 08:00 | 22d | 8332.7402 | 0 | 0 | -87.65 | 0 | 8245.0902 | 0 | 100% | Finished | 8332.7402 | 8332.7402 | 100 | 110 | 100 | 100 | 98.9481 | 100
29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 28d | [5 empty] | 465.42 |  | 100% |  | 536.76 | 536.76
30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-09-29 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-11-06 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-11-10 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 | 2006-10-30 08:00 | 1d | 29.93 | 0 | 0 | -5.14 | 0 | 24.79 | 0 | 100% | Finished | 29.93 | 29.93 | 100 | 100 | 100 | 100 | 82.8266 | 100
63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 | 2006-11-21 08:00 | 1d | 14.43 | 0 | 0 | 0 | 0 | 14.43 | 0 | 100% | Finished | 14.43 | 14.43 | 100 | 100 | 100 | 100 | 100 | 100
34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 | 2006-11-07 08:00 | 1d | 1598.6899 | 0 | 0 | -6.89 | 0 | 1591.7999 | 0 | 100% | Finished | 1598.6899 | 1598.6899 | 100 | 100 | 100 | 100 | 99.569 | 100
35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 19d | [5 empty] | 11211.1001 |  | 100% |  | 11097.8301 | 11097.8301
36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 | 2006-11-22 08:00 | 8d | 6829.4302 | 0 | 0 | 69.7 | 0 | 6899.1302 | 0 | 100% | Finished | 6829.4302 | 6829.4302 | 100 | 100 | 100 | 100 | 101.0206 | 100
37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 | 2006-12-06 08:00 | 9d | 4268.3999 | 0 | 0 | 43.57 | 0 | 4311.9699 | 0 | 100% | Finished | 4268.3999 | 4268.3999 | 100 | 180 | 100 | 100 | 101.0208 | 100
38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 6d | [5 empty] | 2937.6599 |  | 51.07% |  | 2695.8999 | 5278.84
39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 | 2006-12-15 08:00 | 3d | 2695.8999 | 0 | 0 | 241.76 | 0 | 2937.6599 | 0 | 100% | Finished | 2695.8999 | 2695.8999 | 100 | 100 | 100 | 100 | 108.9677 | 100
40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 |  | 0 | 0 | 898.63 | 1d | 0 | 0 | 0 | 898.63 | 0% | Not Started | 0 | 898.63 | 100 |  | 0 | 100 |  | 0
41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 1684.3101 | 100 |  | 0 | 100 |  | 0
42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 7d | [5 empty] | 1302 |  | 25% |  | 1194.5 | 4778
43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 | 2006-12-14 08:00 | 1d | 1194.5 | 0 | 0 | 107.5 | 0 | 1302 | 0 | 100% | Finished | 1194.5 | 1194.5 | 100 | 100 | 100 | 100 | 108.9996 | 100
44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 |  | 0 | 0 | 3583.5 | 3d | 0 | 0 | 0 | 3583.5 | 0% | Not Started | 0 | 3583.5 | 100 |  | 0 | 100 |  | 0
45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 7d | [5 empty] | 1477.55 |  | 50% |  | 1514.46 | 3028.9199
46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 | 2006-12-14 08:00 | 1d | 1514.46 | 0 | 0 | -36.91 | 0 | 1477.55 | 0 | 100% | Finished | 1514.46 | 1514.46 | 100 | 100 | 100 | 100 | 97.5628 | 100
47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 1514.46 | 100 |  | 0 | 100 |  | 0
48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 7d | [5 empty] | 172.8 |  | 50% |  | 164.5 | 329
49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 | 2006-12-14 08:00 | 1d | 164.5 | 0 | 0 | 8.3 | 0 | 172.8 | 0 | 100% | Finished | 164.5 | 164.5 | 100 | 100 | 100 | 100 | 105.0456 | 100
50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 |  | 0 | 0 | 164.5 | 1d | 0 | 0 | 0 | 164.5 | 0% | Not Started | 0 | 164.5 | 100 |  | 0 | 100 |  | 0
51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 35d | [5 empty] | 2978.8399 |  | 25% |  | 2957.3799 | 2957.3799
52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 | 2006-11-06 08:00 | 1d | 2957.3799 | 0 | 0 | 21.46 | 0 | 2978.8399 | 0 | 100% | Finished | 2957.3799 | 2957.3799 | 100 | 100 | 100 | 100 | 100.7256 | 100
53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 |  | 0 | 0 | 8872.1504 | 3d | 0 | 0 | 0 | 8872.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 35d | [5 empty] | 43.29 |  | 50% |  | 43.29 | 86.58
55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 | 2006-11-06 08:00 | 1d | 43.29 | 0 | 0 | 0 | 0 | 43.29 | 0 | 100% | Finished | 43.29 | 43.29 | 100 | 100 | 100 | 100 | 100 | 100
56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 |  | 0 | 0 | 43.29 | 1d | 0 | 0 | 0 | 43.29 | 0% | Not Started | 0 | 43.29 | 100 |  | 0 | 100 |  | 0
57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 133d | [5 empty] | 0 |  | 50% |  | 27 | 54
58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2006-05-19 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 |  | 0 | 0 | 27 | 1d | 0 | 0 | 0 | 27 | 0% | Not Started | 0 | 27 | 100 |  | 0 | 100 |  | 0
60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 |  | 0 | 0 | 8574.7402 | 3d | 0 | 0 | 0 | 8574.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2007-01-31 17:00 |  | TP Name | 31/01, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 171d | [5 empty] | 163870.6103 |  | 93.48% |  | 168702.9603 | 180476.4706
62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 100% | Finished | 1359.3101 | 1359.3101 | 100 | 100 | 100 | 100 | 63.9626 | 100
61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 100% | Finished | 214.62 | 214.62 | 100 | 100 | 100 | 100 | 177.579 | 100
1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 50d | [5 empty] | 66331.7201 |  | 100% |  | 70726.4302 | 70726.4302
2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 7d | 12649.1201 | 0 | 0 | -768.98 | 0 | 11880.1401 | 0 | 100% | Finished | 12649.1201 | 12649.1201 | 100 | 100 | 100 | 100 | 93.9207 | 100
3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 2006-05-12 08:00 | 36d | 50655.3203 | 0 | 0 | -3515.3501 | 0 | 47139.9702 | 0 | 100% | Finished | 50655.3203 | 50655.3203 | 100 | 112.5 | 100 | 100 | 93.0603 | 100
4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 | 2006-07-06 08:00 | 1d | 1582.98 | 0 | 0 | -109.85 | 0 | 1473.13 | 0 | 100% | Finished | 1582.98 | 1582.98 | 100 | 100 | 100 | 100 | 93.0606 | 100
5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 2006-05-12 08:00 | 1d | 5839.0098 | 0 | 0 | -0.53 | 0 | 5838.4798 | 0 | 100% | Finished | 5839.0098 | 5839.0098 | 100 | 100 | 100 | 100 | 99.9909 | 100
6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 10d | [5 empty] | 2236 |  | 100% |  | 1676.5699 | 1676.5699
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 | 2006-07-10 08:00 | 1d | 558.86 | 0 | 0 | 186.48 | 0 | 745.34 | 0 | 100% | Finished | 558.86 | 558.86 | 100 | 100 | 100 | 100 | 133.3679 | 100
8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 | 2006-07-20 08:00 | 2d | 1117.71 | 0 | 0 | 372.95 | 0 | 1490.66 | 0 | 100% | Finished | 1117.71 | 1117.71 | 100 | 100 | 100 | 100 | 133.3673 | 100
9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 11d | [5 empty] | 5493.7799 |  | 100% |  | 6791.6599 | 6791.6599
10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 | 2006-06-27 08:00 | 1d | 970.24 | 0 | 0 | -185.41 | 0 | 784.83 | 0 | 100% | Finished | 970.24 | 970.24 | 100 | 100 | 100 | 100 | 80.8903 | 100
11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 | 2006-07-06 08:00 | 4d | 5821.4199 | 0 | 0 | -1112.47 | 0 | 4708.95 | 0 | 100% | Finished | 5821.4199 | 5821.4199 | 100 | 66.6667 | 100 | 100 | 80.8901 | 100
12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 4d | [5 empty] | 6475.53 |  | 100% |  | 6939.91 | 6939.91
13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 | 2006-07-12 08:00 | 1d | 2313.3 | 0 | 0 | -154.79 | 0 | 2158.5101 | 0 | 100% | Finished | 2313.3 | 2313.3 | 100 | 50 | 100 | 100 | 93.3087 | 100
14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 | 2006-07-13 08:00 | 1d | 1156.65 | 0 | 0 | -77.4 | 0 | 1079.25 | 0 | 100% | Finished | 1156.65 | 1156.65 | 100 | 100 | 100 | 100 | 93.3083 | 100
15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 | 2006-07-14 08:00 | 2d | 3469.96 | 0 | 0 | -232.19 | 0 | 3237.77 | 0 | 100% | Finished | 3469.96 | 3469.96 | 100 | 66.6667 | 100 | 100 | 93.3086 | 100
16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 36d | [5 empty] | 19753.5097 |  | 100% |  | 19170.7498 | 19170.7498
17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 30d | [5 empty] | 17429.8296 |  | 100% |  | 16572.8896 | 16572.8896
18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 | 2006-07-12 08:00 | 1d | 5524.2998 | 0 | 0 | 285.65 | 0 | 5809.9498 | 0 | 100% | Finished | 5524.2998 | 5524.2998 | 100 | 100 | 100 | 100 | 105.1708 | 100
19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 | 2006-09-13 08:00 | 2d | 11048.5898 | 0 | 0 | 571.29 | 0 | 11619.8798 | 0 | 100% | Finished | 11048.5898 | 11048.5898 | 100 | 100 | 100 | 100 | 105.1707 | 100
20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 34d | [5 empty] | 2323.6801 |  | 100% |  | 2597.8601 | 2597.8601
21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-07-14 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-09-22 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 | 2006-08-25 08:00 | 4d | 11733.46 | 0 | 0 | -507.34 | 0 | 11226.12 | 0 | 100% | Finished | 11733.46 | 11733.46 | 100 | 100 | 100 | 100 | 95.6761 | 100
25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 | 2006-09-05 08:00 | 4d | 3594.54 | 0 | 0 | 322.35 | 0 | 3916.89 | 0 | 100% | Finished | 3594.54 | 3594.54 | 100 | 100 | 100 | 100 | 108.9678 | 100
26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 | 2006-09-01 08:00 | 1d | 1684.3101 | 0 | 0 | -188.45 | 0 | 1495.8601 | 0 | 100% | Finished | 1684.3101 | 1684.3101 | 100 | 100 | 100 | 100 | 88.8114 | 100
27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 | 2006-09-13 08:00 | 2d | 1014.92 | 0 | 0 | 173.08 | 0 | 1188 | 0 | 100% | Finished | 1014.92 | 1014.92 | 100 | 100 | 100 | 100 | 117.0536 | 100
28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 | 2006-09-27 08:00 | 22d | 8332.7402 | 0 | 0 | -87.65 | 0 | 8245.0902 | 0 | 100% | Finished | 8332.7402 | 8332.7402 | 100 | 110 | 100 | 100 | 98.9481 | 100
29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 28d | [5 empty] | 465.42 |  | 100% |  | 536.76 | 536.76
30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-09-29 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-11-06 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-11-10 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 | 2006-10-30 08:00 | 1d | 29.93 | 0 | 0 | -5.14 | 0 | 24.79 | 0 | 100% | Finished | 29.93 | 29.93 | 100 | 100 | 100 | 100 | 82.8266 | 100
63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 | 2006-11-21 08:00 | 1d | 14.43 | 0 | 0 | 0 | 0 | 14.43 | 0 | 100% | Finished | 14.43 | 14.43 | 100 | 100 | 100 | 100 | 100 | 100
34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 | 2006-11-07 08:00 | 1d | 1598.6899 | 0 | 0 | -6.89 | 0 | 1591.7999 | 0 | 100% | Finished | 1598.6899 | 1598.6899 | 100 | 100 | 100 | 100 | 99.569 | 100
35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 19d | [5 empty] | 11211.1001 |  | 100% |  | 11097.8301 | 11097.8301
36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 | 2006-11-22 08:00 | 8d | 6829.4302 | 0 | 0 | 69.7 | 0 | 6899.1302 | 0 | 100% | Finished | 6829.4302 | 6829.4302 | 100 | 100 | 100 | 100 | 101.0206 | 100
37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 | 2006-12-06 08:00 | 9d | 4268.3999 | 0 | 0 | 43.57 | 0 | 4311.9699 | 0 | 100% | Finished | 4268.3999 | 4268.3999 | 100 | 180 | 100 | 100 | 101.0208 | 100
38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 24d | [5 empty] | 3916.8799 |  | 68.09% |  | 3594.5299 | 5278.84
39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 | 2006-12-15 08:00 | 3d | 2695.8999 | 0 | 0 | 241.76 | 0 | 2937.6599 | 0 | 100% | Finished | 2695.8999 | 2695.8999 | 100 | 100 | 100 | 100 | 108.9677 | 100
40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 | 2007-01-23 08:00 | 1d | 898.63 | 0 | 0 | 80.59 | 0 | 979.22 | 0 | 100% | Finished | 898.63 | 898.63 | 100 | 100 | 100 | 100 | 108.9681 | 100
41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 |  | 0 | 0 | 1684.3101 | 1d | 0 | 0 | 0 | 1684.3101 | 0% | Not Started | 0 | 1684.3101 | 100 |  | 0 | 100 |  | 0
42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 23d | [5 empty] | 5208.01 |  | 100% |  | 4778 | 4778
43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 | 2006-12-14 08:00 | 1d | 1194.5 | 0 | 0 | 107.5 | 0 | 1302 | 0 | 100% | Finished | 1194.5 | 1194.5 | 100 | 100 | 100 | 100 | 108.9996 | 100
44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 | 2007-01-25 08:00 | 3d | 3583.5 | 0 | 0 | 322.51 | 0 | 3906.01 | 0 | 100% | Finished | 3583.5 | 3583.5 | 100 | 100 | 100 | 100 | 108.9999 | 100
45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 25d | [5 empty] | 1477.55 |  | 50% |  | 1514.46 | 3028.9199
46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 | 2006-12-14 08:00 | 1d | 1514.46 | 0 | 0 | -36.91 | 0 | 1477.55 | 0 | 100% | Finished | 1514.46 | 1514.46 | 100 | 100 | 100 | 100 | 97.5628 | 100
47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 |  | 0 | 0 | 1514.46 | 1d | 0 | 0 | 0 | 1514.46 | 0% | Not Started | 0 | 1514.46 | 100 |  | 0 | 100 |  | 0
48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 21d | [5 empty] | 345.6 |  | 100% |  | 329 | 329
49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 | 2006-12-14 08:00 | 1d | 164.5 | 0 | 0 | 8.3 | 0 | 172.8 | 0 | 100% | Finished | 164.5 | 164.5 | 100 | 100 | 100 | 100 | 105.0456 | 100
50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 | 2007-01-25 08:00 | 1d | 164.5 | 0 | 0 | 8.3 | 0 | 172.8 | 0 | 100% | Finished | 164.5 | 164.5 | 100 | 100 | 100 | 100 | 105.0456 | 100
51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 46d | [5 empty] | 11915.3803 |  | 100% |  | 11829.5303 | 11829.5303
52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 | 2006-11-06 08:00 | 1d | 2957.3799 | 0 | 0 | 21.46 | 0 | 2978.8399 | 0 | 100% | Finished | 2957.3799 | 2957.3799 | 100 | 100 | 100 | 100 | 100.7256 | 100
53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 | 2007-01-16 08:00 | 5d | 8872.1504 | 0 | 0 | 64.39 | 0 | 8936.5404 | 0 | 100% | Finished | 8872.1504 | 8872.1504 | 100 | 166.6667 | 100 | 100 | 100.7258 | 100
54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 42d | [5 empty] | 86.58 |  | 100% |  | 86.58 | 86.58
55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 | 2006-11-06 08:00 | 1d | 43.29 | 0 | 0 | 0 | 0 | 43.29 | 0 | 100% | Finished | 43.29 | 43.29 | 100 | 100 | 100 | 100 | 100 | 100
56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 | 2007-01-16 08:00 | 1d | 43.29 | 0 | 0 | 0 | 0 | 43.29 | 0 | 100% | Finished | 43.29 | 43.29 | 100 | 100 | 100 | 100 | 100 | 100
57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 151d | [5 empty] | 0 |  | 100% |  | 54 | 54
58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2006-05-19 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2007-01-31 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 |  | 0 | 0 | 8574.7402 | 3d | 0 | 0 | 0 | 8574.7402 | 0% | Not Started | 0 | 8574.7402 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2007-02-28 17:00 |  | TP Name | 28/02, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence | 2006-04-06 08:00 | 2007-01-17 17:00 | 170d |  |  | 180476.4706 |  |  | 180476.4706 |  | 174d | [5 empty] | 175030.6505 |  | 100% |  | 180476.4706 | 180476.4706
62 | Voorafgaande activiteiten | 2006-04-06 08:00 | 2006-04-06 17:00 | 1d |  | 0 | 1359.3101 | 0 | 0 | 1359.3101 | 2006-04-20 08:00 | 1d | 1359.3101 | 0 | 0 | -489.86 | 0 | 869.4501 | 0 | 100% | Finished | 1359.3101 | 1359.3101 | 100 | 100 | 100 | 100 | 63.9626 | 100
61 | Werfinrichting | 2006-04-07 08:00 | 2006-04-07 17:00 | 1d |  | 0 | 214.62 | 0 | 0 | 214.62 | 2006-04-21 08:00 | 1d | 214.62 | 0 | 0 | 166.5 | 0 | 381.12 | 0 | 100% | Finished | 214.62 | 214.62 | 100 | 100 | 100 | 100 | 177.579 | 100
1 | Ruwbouw | 2006-04-10 08:00 | 2006-06-19 17:00 | 46d |  |  | 70726.4302 |  |  | 70726.4302 |  | 50d | [5 empty] | 66331.7201 |  | 100% |  | 70726.4302 | 70726.4302
2 | Fundering | 2006-04-10 08:00 | 2006-04-19 17:00 | 7d |  | 0 | 12649.1201 | 0 | 0 | 12649.1201 | 2006-04-24 08:00 | 7d | 12649.1201 | 0 | 0 | -768.98 | 0 | 11880.1401 | 0 | 100% | Finished | 12649.1201 | 12649.1201 | 100 | 100 | 100 | 100 | 93.9207 | 100
3 | Metselwerken | 2006-04-21 08:00 | 2006-06-09 17:00 | 32d |  | 0 | 50655.3203 | 0 | 0 | 50655.3203 | 2006-05-12 08:00 | 36d | 50655.3203 | 0 | 0 | -3515.3501 | 0 | 47139.9702 | 0 | 100% | Finished | 50655.3203 | 50655.3203 | 100 | 112.5 | 100 | 100 | 93.0603 | 100
4 | Dorpels | 2006-06-19 08:00 | 2006-06-19 17:00 | 1d |  | 0 | 1582.98 | 0 | 0 | 1582.98 | 2006-07-06 08:00 | 1d | 1582.98 | 0 | 0 | -109.85 | 0 | 1473.13 | 0 | 100% | Finished | 1582.98 | 1582.98 | 100 | 100 | 100 | 100 | 93.0606 | 100
5 | Parement levering | 2006-04-21 08:00 | 2006-04-21 17:00 | 1d |  | 0 | 5839.0098 | 0 | 0 | 5839.0098 | 2006-05-12 08:00 | 1d | 5839.0098 | 0 | 0 | -0.53 | 0 | 5838.4798 | 0 | 100% | Finished | 5839.0098 | 5839.0098 | 100 | 100 | 100 | 100 | 99.9909 | 100
6 | Voegwerken | 2006-06-14 08:00 | 2006-08-17 17:00 | 30d |  |  | 1676.5699 |  |  | 1676.5699 |  | 10d | [5 empty] | 2236 |  | 100% |  | 1676.5699 | 1676.5699
7 | Voegen schoorsteen-niet aanwezig + eggen schrijnwerk | 2006-06-14 08:00 | 2006-06-14 17:00 | 1d |  | 0 | 558.86 | 0 | 0 | 558.86 | 2006-07-10 08:00 | 1d | 558.86 | 0 | 0 | 186.48 | 0 | 745.34 | 0 | 100% | Finished | 558.86 | 558.86 | 100 | 100 | 100 | 100 | 133.3679 | 100
8 | Volledige ruwbouw | 2006-08-16 08:00 | 2006-08-17 17:00 | 2d |  | 0 | 1117.71 | 0 | 0 | 1117.71 | 2006-07-20 08:00 | 2d | 1117.71 | 0 | 0 | 372.95 | 0 | 1490.66 | 0 | 100% | Finished | 1117.71 | 1117.71 | 100 | 100 | 100 | 100 | 133.3673 | 100
9 | Kapconstructie | 2006-05-24 08:00 | 2006-06-23 17:00 | 20d |  |  | 6791.6599 |  |  | 6791.6599 |  | 11d | [5 empty] | 5493.7799 |  | 100% |  | 6791.6599 | 6791.6599
10 | Koppels | 2006-05-24 08:00 | 2006-05-24 17:00 | 1d |  | 0 | 970.24 | 0 | 0 | 970.24 | 2006-06-27 08:00 | 1d | 970.24 | 0 | 0 | -185.41 | 0 | 784.83 | 0 | 100% | Finished | 970.24 | 970.24 | 100 | 100 | 100 | 100 | 80.8903 | 100
11 | Volledige kapconstructie | 2006-06-16 08:00 | 2006-06-23 17:00 | 6d |  | 0 | 5821.4199 | 0 | 0 | 5821.4199 | 2006-07-06 08:00 | 4d | 5821.4199 | 0 | 0 | -1112.47 | 0 | 4708.95 | 0 | 100% | Finished | 5821.4199 | 5821.4199 | 100 | 66.6667 | 100 | 100 | 80.8901 | 100
12 | Dakwerken | 2006-06-28 08:00 | 2006-07-19 17:00 | 16d |  |  | 6939.91 |  |  | 6939.91 |  | 4d | [5 empty] | 6475.53 |  | 100% |  | 6939.91 | 6939.91
13 | Zinkwerken | 2006-06-28 08:00 | 2006-06-29 17:00 | 2d |  | 0 | 2313.3 | 0 | 0 | 2313.3 | 2006-07-12 08:00 | 1d | 2313.3 | 0 | 0 | -154.79 | 0 | 2158.5101 | 0 | 100% | Finished | 2313.3 | 2313.3 | 100 | 50 | 100 | 100 | 93.3087 | 100
14 | Onderdak | 2006-07-03 08:00 | 2006-07-03 17:00 | 1d |  | 0 | 1156.65 | 0 | 0 | 1156.65 | 2006-07-13 08:00 | 1d | 1156.65 | 0 | 0 | -77.4 | 0 | 1079.25 | 0 | 100% | Finished | 1156.65 | 1156.65 | 100 | 100 | 100 | 100 | 93.3083 | 100
15 | Plaatsing pannen | 2006-07-17 08:00 | 2006-07-19 17:00 | 3d |  | 0 | 3469.96 | 0 | 0 | 3469.96 | 2006-07-14 08:00 | 2d | 3469.96 | 0 | 0 | -232.19 | 0 | 3237.77 | 0 | 100% | Finished | 3469.96 | 3469.96 | 100 | 66.6667 | 100 | 100 | 93.3086 | 100
16 | Buitenschrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 19170.7498 |  |  | 19170.7498 |  | 36d | [5 empty] | 19753.5097 |  | 100% |  | 19170.7498 | 19170.7498
17 | Schrijnwerk | 2006-06-28 08:00 | 2006-09-05 17:00 | 33d |  |  | 16572.8896 |  |  | 16572.8896 |  | 30d | [5 empty] | 17429.8296 |  | 100% |  | 16572.8896 | 16572.8896
18 | Opmeting schrijnwerk | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 5524.2998 | 0 | 0 | 5524.2998 | 2006-07-12 08:00 | 1d | 5524.2998 | 0 | 0 | 285.65 | 0 | 5809.9498 | 0 | 100% | Finished | 5524.2998 | 5524.2998 | 100 | 100 | 100 | 100 | 105.1708 | 100
19 | Plaatsing schrijnwerk | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 11048.5898 | 0 | 0 | 11048.5898 | 2006-09-13 08:00 | 2d | 11048.5898 | 0 | 0 | 571.29 | 0 | 11619.8798 | 0 | 100% | Finished | 11048.5898 | 11048.5898 | 100 | 100 | 100 | 100 | 105.1707 | 100
20 | Poort | 2006-06-28 08:00 | 2006-09-04 17:00 | 32d |  |  | 2597.8601 |  |  | 2597.8601 |  | 34d | [5 empty] | 2323.6801 |  | 100% |  | 2597.8601 | 2597.8601
21 | Opmeting poort | 2006-06-28 08:00 | 2006-06-28 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-07-14 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
22 | Plaatsing poort | 2006-09-04 08:00 | 2006-09-04 17:00 | 1d |  | 0 | 1298.9301 | 0 | 0 | 1298.9301 | 2006-09-22 08:00 | 1d | 1298.9301 | 0 | 0 | -137.09 | 0 | 1161.8401 | 0 | 100% | Finished | 1298.9301 | 1298.9301 | 100 | 100 | 100 | 100 | 89.4459 | 100
23 | Ruwbouw sanitair en cv | 2006-08-16 08:00 | 2006-08-21 17:00 | 4d |  | 0 | 11733.46 | 0 | 0 | 11733.46 | 2006-08-25 08:00 | 4d | 11733.46 | 0 | 0 | -507.34 | 0 | 11226.12 | 0 | 100% | Finished | 11733.46 | 11733.46 | 100 | 100 | 100 | 100 | 95.6761 | 100
25 | Ruwbouw elektriciteit | 2006-08-25 08:00 | 2006-08-30 17:00 | 4d |  | 0 | 3594.54 | 0 | 0 | 3594.54 | 2006-09-05 08:00 | 4d | 3594.54 | 0 | 0 | 322.35 | 0 | 3916.89 | 0 | 100% | Finished | 3594.54 | 3594.54 | 100 | 100 | 100 | 100 | 108.9678 | 100
26 | Ruwbouw ventilatie | 2006-08-24 08:00 | 2006-08-24 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 | 2006-09-01 08:00 | 1d | 1684.3101 | 0 | 0 | -188.45 | 0 | 1495.8601 | 0 | 100% | Finished | 1684.3101 | 1684.3101 | 100 | 100 | 100 | 100 | 88.8114 | 100
27 | Dakisolatie | 2006-09-04 08:00 | 2006-09-05 17:00 | 2d |  | 0 | 1014.92 | 0 | 0 | 1014.92 | 2006-09-13 08:00 | 2d | 1014.92 | 0 | 0 | 173.08 | 0 | 1188 | 0 | 100% | Finished | 1014.92 | 1014.92 | 100 | 100 | 100 | 100 | 117.0536 | 100
28 | Pleisterwerken | 2006-09-18 08:00 | 2006-10-13 17:00 | 20d |  | 0 | 8332.7402 | 0 | 0 | 8332.7402 | 2006-09-27 08:00 | 22d | 8332.7402 | 0 | 0 | -87.65 | 0 | 8245.0902 | 0 | 100% | Finished | 8332.7402 | 8332.7402 | 100 | 110 | 100 | 100 | 98.9481 | 100
29 | Spuitplamuur | 2006-09-20 08:00 | 2006-10-25 17:00 | 26d |  |  | 536.76 |  |  | 536.76 |  | 28d | [5 empty] | 465.42 |  | 100% |  | 536.76 | 536.76
30 | Opstop voegen | 2006-09-20 08:00 | 2006-09-20 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-09-29 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
31 | 1-ste laag | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-11-06 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
32 | 2-de laag | 2006-10-25 08:00 | 2006-10-25 17:00 | 1d |  | 0 | 178.92 | 0 | 0 | 178.92 | 2006-11-10 08:00 | 1d | 178.92 | 0 | 0 | -23.78 | 0 | 155.14 | 0 | 100% | Finished | 178.92 | 178.92 | 100 | 100 | 100 | 100 | 86.7091 | 100
33 | Plaatsing baden / douche's (1 inloopdouche voorzien) | 2006-10-16 08:00 | 2006-10-16 17:00 | 1d |  | 0 | 29.93 | 0 | 0 | 29.93 | 2006-10-30 08:00 | 1d | 29.93 | 0 | 0 | -5.14 | 0 | 24.79 | 0 | 100% | Finished | 29.93 | 29.93 | 100 | 100 | 100 | 100 | 82.8266 | 100
63 | Verdichting inloopdouche plaatsen | 2006-10-23 08:00 | 2006-10-23 17:00 | 1d |  | 0 | 14.43 | 0 | 0 | 14.43 | 2006-11-21 08:00 | 1d | 14.43 | 0 | 0 | 0 | 0 | 14.43 | 0 | 100% | Finished | 14.43 | 14.43 | 100 | 100 | 100 | 100 | 100 | 100
34 | Chape | 2006-10-19 08:00 | 2006-10-19 17:00 | 1d |  | 0 | 1598.6899 | 0 | 0 | 1598.6899 | 2006-11-07 08:00 | 1d | 1598.6899 | 0 | 0 | -6.89 | 0 | 1591.7999 | 0 | 100% | Finished | 1598.6899 | 1598.6899 | 100 | 100 | 100 | 100 | 99.569 | 100
35 | Bevloering en faiences | 2006-10-26 08:00 | 2006-11-16 17:00 | 13d |  |  | 11097.8301 |  |  | 11097.8301 |  | 19d | [5 empty] | 11211.1001 |  | 100% |  | 11097.8301 | 11097.8301
36 | Bevloering beneden+badkamer boven-wc boven | 2006-10-26 08:00 | 2006-11-09 17:00 | 8d |  | 0 | 6829.4302 | 0 | 0 | 6829.4302 | 2006-11-22 08:00 | 8d | 6829.4302 | 0 | 0 | 69.7 | 0 | 6899.1302 | 0 | 100% | Finished | 6829.4302 | 6829.4302 | 100 | 100 | 100 | 100 | 101.0206 | 100
37 | Faiences boven | 2006-11-10 08:00 | 2006-11-16 17:00 | 5d |  | 0 | 4268.3999 | 0 | 0 | 4268.3999 | 2006-12-06 08:00 | 9d | 4268.3999 | 0 | 0 | 43.57 | 0 | 4311.9699 | 0 | 100% | Finished | 4268.3999 | 4268.3999 | 100 | 180 | 100 | 100 | 101.0208 | 100
38 | Elektriciteit afwerking | 2006-11-15 08:00 | 2006-12-15 17:00 | 23d |  |  | 5278.84 |  |  | 5278.84 |  | 27d | [5 empty] | 5412.74 |  | 100% |  | 5278.84 | 5278.84
39 | Afwerking elektriciteit | 2006-11-15 08:00 | 2006-11-17 17:00 | 3d |  | 0 | 2695.8999 | 0 | 0 | 2695.8999 | 2006-12-15 08:00 | 3d | 2695.8999 | 0 | 0 | 241.76 | 0 | 2937.6599 | 0 | 100% | Finished | 2695.8999 | 2695.8999 | 100 | 100 | 100 | 100 | 108.9677 | 100
40 | Keuring | 2006-12-04 08:00 | 2006-12-04 17:00 | 1d |  | 0 | 898.63 | 0 | 0 | 898.63 | 2007-01-23 08:00 | 1d | 898.63 | 0 | 0 | 80.59 | 0 | 979.22 | 0 | 100% | Finished | 898.63 | 898.63 | 100 | 100 | 100 | 100 | 108.9681 | 100
41 | Afwerking ventilatie | 2006-12-15 08:00 | 2006-12-15 17:00 | 1d |  | 0 | 1684.3101 | 0 | 0 | 1684.3101 | 2007-02-05 08:00 | 1d | 1684.3101 | 0 | 0 | -188.45 | 0 | 1495.8601 | 0 | 100% | Finished | 1684.3101 | 1684.3101 | 100 | 100 | 100 | 100 | 88.8114 | 100
42 | Binnenschrijnwerk | 2006-11-14 08:00 | 2006-12-08 17:00 | 19d |  |  | 4778 |  |  | 4778 |  | 23d | [5 empty] | 5208.01 |  | 100% |  | 4778 | 4778
43 | Opmeting binnenschrijnwerk | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1194.5 | 0 | 0 | 1194.5 | 2006-12-14 08:00 | 1d | 1194.5 | 0 | 0 | 107.5 | 0 | 1302 | 0 | 100% | Finished | 1194.5 | 1194.5 | 100 | 100 | 100 | 100 | 108.9996 | 100
44 | Plaatsing binnenschrijnwerk | 2006-12-06 08:00 | 2006-12-08 17:00 | 3d |  | 0 | 3583.5 | 0 | 0 | 3583.5 | 2007-01-25 08:00 | 3d | 3583.5 | 0 | 0 | 322.51 | 0 | 3906.01 | 0 | 100% | Finished | 3583.5 | 3583.5 | 100 | 100 | 100 | 100 | 108.9999 | 100
45 | Trap gelijkvl. - 1°verdiep | 2006-11-14 08:00 | 2006-12-13 17:00 | 22d |  |  | 3028.9199 |  |  | 3028.9199 |  | 26d | [5 empty] | 2955.0999 |  | 100% |  | 3028.9199 | 3028.9199
46 | Opmeting trap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 | 2006-12-14 08:00 | 1d | 1514.46 | 0 | 0 | -36.91 | 0 | 1477.55 | 0 | 100% | Finished | 1514.46 | 1514.46 | 100 | 100 | 100 | 100 | 97.5628 | 100
47 | Plaatsing trap | 2006-12-13 08:00 | 2006-12-13 17:00 | 1d |  | 0 | 1514.46 | 0 | 0 | 1514.46 | 2007-02-01 08:00 | 1d | 1514.46 | 0 | 0 | -36.91 | 0 | 1477.55 | 0 | 100% | Finished | 1514.46 | 1514.46 | 100 | 100 | 100 | 100 | 97.5628 | 100
48 | MAP-trap | 2006-11-14 08:00 | 2006-12-06 17:00 | 17d |  |  | 329 |  |  | 329 |  | 21d | [5 empty] | 345.6 |  | 100% |  | 329 | 329
49 | Opmeting zoldertrap | 2006-11-14 08:00 | 2006-11-14 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 | 2006-12-14 08:00 | 1d | 164.5 | 0 | 0 | 8.3 | 0 | 172.8 | 0 | 100% | Finished | 164.5 | 164.5 | 100 | 100 | 100 | 100 | 105.0456 | 100
50 | Plaatsing zoldertrap | 2006-12-06 08:00 | 2006-12-06 17:00 | 1d |  | 0 | 164.5 | 0 | 0 | 164.5 | 2007-01-25 08:00 | 1d | 164.5 | 0 | 0 | 8.3 | 0 | 172.8 | 0 | 100% | Finished | 164.5 | 164.5 | 100 | 100 | 100 | 100 | 105.0456 | 100
51 | Keukenmeubilair | 2006-11-15 08:00 | 2007-01-12 17:00 | 33d |  |  | 11829.5303 |  |  | 11829.5303 |  | 46d | [5 empty] | 11915.3803 |  | 100% |  | 11829.5303 | 11829.5303
52 | Opmeting keukenmeubilair | 2006-11-15 08:00 | 2006-11-15 17:00 | 1d |  | 0 | 2957.3799 | 0 | 0 | 2957.3799 | 2006-11-06 08:00 | 1d | 2957.3799 | 0 | 0 | 21.46 | 0 | 2978.8399 | 0 | 100% | Finished | 2957.3799 | 2957.3799 | 100 | 100 | 100 | 100 | 100.7256 | 100
53 | Plaatsing keukenmeubilair | 2007-01-10 08:00 | 2007-01-12 17:00 | 3d |  | 0 | 8872.1504 | 0 | 0 | 8872.1504 | 2007-01-16 08:00 | 5d | 8872.1504 | 0 | 0 | 64.39 | 0 | 8936.5404 | 0 | 100% | Finished | 8872.1504 | 8872.1504 | 100 | 166.6667 | 100 | 100 | 100.7258 | 100
54 | Badmeubel | 2006-11-21 08:00 | 2006-12-20 17:00 | 22d |  |  | 86.58 |  |  | 86.58 |  | 42d | [5 empty] | 86.58 |  | 100% |  | 86.58 | 86.58
55 | Opmeting badmeubel | 2006-11-21 08:00 | 2006-11-21 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 | 2006-11-06 08:00 | 1d | 43.29 | 0 | 0 | 0 | 0 | 43.29 | 0 | 100% | Finished | 43.29 | 43.29 | 100 | 100 | 100 | 100 | 100 | 100
56 | Plaatsing badmeubel | 2006-12-20 08:00 | 2006-12-20 17:00 | 1d |  | 0 | 43.29 | 0 | 0 | 43.29 | 2007-01-16 08:00 | 1d | 43.29 | 0 | 0 | 0 | 0 | 43.29 | 0 | 100% | Finished | 43.29 | 43.29 | 100 | 100 | 100 | 100 | 100 | 100
57 | Nutsleidingen | 2006-05-05 08:00 | 2006-12-12 17:00 | 135d |  |  | 54 |  |  | 54 |  | 151d | [5 empty] | 0 |  | 100% |  | 54 | 54
58 | Aanvraag offertes | 2006-05-05 08:00 | 2006-05-05 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2006-05-19 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
59 | Uitvoering aansluitingen | 2006-12-12 08:00 | 2006-12-12 17:00 | 1d |  | 0 | 27 | 0 | 0 | 27 | 2007-01-31 08:00 | 1d | 27 | 0 | 0 | -27 | 0 | 0 | 0 | 100% | Finished | 27 | 27 | 100 | 100 | 100 | 100 |  | 100
60 | Afwerking sanitair en cv | 2007-01-15 08:00 | 2007-01-17 17:00 | 3d |  | 0 | 8574.7402 | 0 | 0 | 8574.7402 | 2007-02-01 08:00 | 3d | 8574.7402 | 0 | 0 | -388.11 | 0 | 8186.6302 | 0 | 100% | Finished | 8574.7402 | 8574.7402 | 100 | 100 | 100 | 100 | 95.4738 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2006-04-17
1:00 - 2:00 | No | Tuesday | Yes | 2006-05-01
2:00 - 3:00 | No | Wednesday | Yes | 2006-05-25
3:00 - 4:00 | No | Thursday | Yes | 2006-05-26
4:00 - 5:00 | No | Friday | Yes | 2006-06-05
5:00 - 6:00 | No | Saturday | No | 2006-07-24
6:00 - 7:00 | No | Sunday | No | 2006-07-25
7:00 - 8:00 | No |  |  | 2006-07-26
8:00 - 9:00 | Yes |  |  | 2006-07-27
9:00 - 10:00 | Yes |  |  | 2006-07-28
10:00 - 11:00 | Yes |  |  | 2006-07-31
11:00 - 12:00 | Yes |  |  | 2006-08-01
12:00 - 13:00 | No |  |  | 2006-08-02
13:00 - 14:00 | Yes |  |  | 2006-08-03
14:00 - 15:00 | Yes |  |  | 2006-08-04
15:00 - 16:00 | Yes |  |  | 2006-08-08
16:00 - 17:00 | Yes |  |  | 2006-08-09
17:00 - 18:00 | No |  |  | 2006-08-10
18:00 - 19:00 | No |  |  | 2006-08-11
19:00 - 20:00 | No |  |  | 2006-08-07
20:00 - 21:00 | No |  |  | 2006-08-14
21:00 - 22:00 | No |  |  | 2006-08-15
22:00 - 23:00 | No |  |  | 2006-11-01
23:00 - 0:00 | No |  |  | 2006-11-02
2006-11-03
2006-12-25
Generated by PMConverter v1.1.3 |  |  |  | 2006-12-26
2006-12-27
2006-12-28
2006-12-29
2007-01-01
2007-01-02
2007-01-03
2007-01-04
2007-01-05

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
30/04, 2006 | 2006-04-06 08:00 | 2006-04-30 17:00 | 70717.3802 | 14223.0502 | 13130.7102 | 2006-04-20 17:00 | -56494.3301 | 20.11% | 1092.34 | 108.3% | -6d | 62.5% | 100% | 2007-04-03 10:00 | 2009-08-20 10:00 | 2009-05-21 11:00 | 2007-02-05 15:00 | 2009-08-20 10:00 | 2009-05-22 12:00 | 2007-01-25 17:00 | 2007-06-08 17:00 | 2007-05-14 11:00 | 179384.1306 | 166615.7544 | 839747.0974 | 279136.1828 | 776262.3944 | 258706.7809 | 196476.179 | 180800.6452 | 0.625 | 1.0832 | 0.20113 | 1 | -6 | 1.0832 | 1 | 0.625 | 1
31/05, 2006 | 2006-04-30 17:00 | 2006-05-31 17:00 | 71714.6202 | 70744.3802 | 66109.1602 | 2006-05-23 17:00 | -970.24 | 98.65% | 4635.2201 | 107% | -4d | 88.89% | 100% | 2007-01-18 16:00 | 2007-01-22 11:00 | 2006-12-21 17:00 | 2007-01-18 12:00 | 2007-01-22 11:00 | 2007-01-09 11:00 | 2007-01-23 17:00 | 2007-02-16 10:00 | 2007-02-02 09:00 | 175841.2505 | 168651.5291 | 177346.1964 | 189557.7618 | 170057.8699 | 181469.3252 | 170279.9989 | 172246.435 | 0.88889 | 1.0701 | 0.98647 | 1 | -4 | 1.0701 | 1 | 0.88889 | 1
30/06, 2006 | 2006-05-31 17:00 | 2006-06-30 17:00 | 88814.41 | 71714.6202 | 66893.9902 | 2006-06-13 17:00 | -17099.7898 | 80.75% | 4820.6301 | 107.2% | -13d | 77.19% | 100% | 2007-02-09 09:00 | 2007-03-15 12:00 | 2007-02-23 11:00 | 2007-02-01 17:00 | 2007-03-15 12:00 | 2007-03-01 10:00 | 2007-02-05 17:00 | 2007-03-29 10:00 | 2007-03-14 10:00 | 175655.8405 | 168344.9094 | 201589.2523 | 207790.0235 | 192535.0869 | 198319.0447 | 173612.7956 | 174362.251 | 0.77193 | 1.0721 | 0.80747 | 1 | -13 | 1.0721 | 1 | 0.77193 | 1
31/07, 2006 | 2006-06-30 17:00 | 2006-07-31 17:00 | 93441.02 | 94558.73 | 88759.39 | 2006-08-16 09:00 | 1117.71 | 101.2% | 5799.34 | 106.5% | 1h | 100.2% | 88.96% | 2007-01-16 17:00 | 2007-01-15 17:00 | 2006-12-18 15:00 | 2007-01-17 09:00 | 2007-01-15 17:00 | 2007-01-08 09:00 | 2007-01-17 16:00 | 2007-01-17 15:00 | 2007-01-09 15:00 | 174677.1305 | 169407.7472 | 173661.5594 | 174528.2263 | 168454.4617 | 169267.9754 | 170224.0642 | 170382.3404 | 1.0017 | 1.0653 | 1.012 | 0.88961 | 0.125 | 1.0653 | 1 | 1.0017 | 1
31/08, 2006 | 2006-07-31 17:00 | 2006-08-31 17:00 | 111571.04 | 106292.1899 | 99985.5099 | 2006-08-23 17:00 | -5278.8501 | 95.27% | 6306.68 | 106.3% | -6d | 92.86% | 100% | 2007-01-24 17:00 | 2007-01-30 12:00 | 2007-01-15 16:00 | 2007-01-23 17:00 | 2007-01-30 12:00 | 2007-01-22 16:00 | 2007-01-25 17:00 | 2007-02-06 09:00 | 2007-01-29 10:00 | 174169.7905 | 169768.1829 | 177854.0471 | 179876.2737 | 173233.8398 | 175136.0808 | 171248.1648 | 171579.8621 | 0.92857 | 1.0631 | 0.95269 | 1 | -6 | 1.0631 | 1 | 0.92857 | 1
30/09, 2006 | 2006-08-31 17:00 | 2006-09-30 17:00 | 133445.1402 | 133445.1402 | 127768.2101 | 2006-09-29 17:00 | 0 | 100% | 5676.93 | 104.4% | 0 | 100% | 100% | 2007-01-17 17:00 | 2007-01-17 17:00 | 2007-01-08 15:00 | 2007-01-17 17:00 | 2007-01-17 17:00 | 2007-01-15 10:00 | 2007-01-17 17:00 | 2007-01-17 17:00 | 2007-01-15 10:00 | 174799.5405 | 172798.7665 | 174799.5405 | 174799.5405 | 172798.7665 | 172798.7665 | 173185.186 | 173185.186 | 1 | 1.0444 | 1 | 1 | 0 | 1.0444 | 1 | 1 | 1
31/10, 2006 | 2006-09-30 17:00 | 2006-10-31 17:00 | 142275.4603 | 133475.0702 | 127793.0001 | 2006-10-18 17:00 | -8800.3901 | 93.81% | 5682.07 | 104.4% | -9d | 92.91% | 100% | 2007-01-30 10:00 | 2007-02-02 10:00 | 2007-01-23 12:00 | 2007-01-29 16:00 | 2007-02-02 10:00 | 2007-01-30 16:00 | 2007-01-30 17:00 | 2007-02-05 17:00 | 2007-02-01 14:00 | 174794.4005 | 172793.5381 | 177893.3362 | 178379.2531 | 175760.5513 | 176225.7826 | 173728.7129 | 173809.769 | 0.92913 | 1.0445 | 0.93815 | 1 | -9 | 1.0445 | 1 | 0.92913 | 1
30/11, 2006 | 2006-10-31 17:00 | 2006-11-30 17:00 | 155113.8899 | 145276.1301 | 139630.7701 | 2006-11-09 17:00 | -9837.7598 | 93.66% | 5645.36 | 104% | -15d | 89.73% | 100% | 2007-01-31 10:00 | 2007-02-02 12:00 | 2007-01-24 12:00 | 2007-01-31 10:00 | 2007-02-02 12:00 | 2007-02-01 09:00 | 2007-02-07 17:00 | 2007-02-14 12:00 | 2007-02-12 15:00 | 174831.1105 | 173463.2424 | 177214.7953 | 178861.6839 | 175754.2982 | 177337.1896 | 174152.417 | 174420.709 | 0.89726 | 1.0404 | 0.93658 | 1 | -15 | 1.0404 | 1 | 0.89726 | 1
31/12, 2006 | 2006-11-30 17:00 | 2006-12-31 17:00 | 163029.5799 | 155113.8899 | 149832.7499 | 2006-12-01 17:00 | -7915.69 | 95.14% | 5281.14 | 103.5% | -15d | 90.74% | 100% | 2007-01-29 12:00 | 2007-01-30 14:00 | 2007-01-22 14:00 | 2007-01-29 16:00 | 2007-01-30 14:00 | 2007-01-30 09:00 | 2007-02-07 17:00 | 2007-02-12 11:00 | 2007-02-09 12:00 | 175195.3305 | 174331.8144 | 176489.6203 | 177783.349 | 175582.0377 | 176831.719 | 174734.9687 | 174952.1993 | 0.90741 | 1.0352 | 0.95145 | 1 | -15 | 1.0352 | 1 | 0.90741 | 1
31/01, 2007 | 2006-12-31 17:00 | 2007-01-31 17:00 | 180476.4706 | 168702.9603 | 163870.6103 | 2007-01-09 17:00 | -11773.5103 | 93.48% | 4832.35 | 102.9% | -16d | 91.11% | 98.04% | 2007-02-02 09:00 | 2007-02-02 16:00 | 2007-01-26 14:00 | 2007-02-16 15:00 | 2007-02-19 12:00 | 2007-02-19 10:00 | 2007-02-08 17:00 | 2007-02-09 14:00 | 2007-02-09 11:00 | 175644.1205 | 175306.8785 | 176465.775 | 176792.7557 | 176104.9974 | 176422.612 | 175521.2769 | 175576.0735 | 0.91111 | 1.0295 | 0.93476 | 0.98038 | -16 | 1.0295 | 1 | 0.91111 | 1
28/02, 2007 | 2007-01-31 17:00 | 2007-02-28 17:00 | 180476.4706 | 180476.4706 | 175030.6505 | 2007-01-17 17:00 | 0 | 100% | 5445.82 | 103.1% | -30d | 85% | 100% | 2007-01-17 17:00 | 2007-01-17 17:00 | 2007-01-10 16:00 | 2007-02-28 17:00 | 2007-02-28 17:00 | 2007-02-28 17:00 | 2007-02-28 17:00 | 2007-02-28 17:00 | 2007-02-28 17:00 | 175030.6505 | 175030.6505 | 175030.6505 | 175030.6505 | 175030.6505 | 175030.6505 | 175030.6505 | 175030.6505 | 0.85 | 1.0311 | 1 | 1 | -30 | 1.0311 | 1 | 0.85 | 1