## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Office Finishing Works (3) | 1 |  |  | 2011-04-18 08:00 | 2011-12-12 17:00 | 171d |  |  | 1 |  |  | 341468.1141 | 238.375
16 | Diversen | 1.1 |  | FS10 | 2011-04-18 08:00 | 2011-08-31 17:00 | 98d |  | 0 | 0 | 2.3 | 1803.2 | 1803.2 | 135.375
10 | Opmerkingen oplevering | 1.2 | 16FS |  | 2011-09-13 08:00 | 2011-12-12 17:00 | 65d |  | 0 | 0 | 113.01 | 58765.2011 | 58765.2011 | 90.375
6 | Gipswanden | 1.3 |  | FS11;FS2;FS13 | 2011-05-16 08:00 | 2011-06-28 17:00 | 32d |  | 0 | 0 | 60.82 | 15569.9199 | 15569.9199 | 43.375
1 | Vaste plafonds (1) | 1.4 |  | FS11;FS2;FS13 | 2011-05-18 08:00 | 2011-07-01 17:00 | 33d |  | 0 | 0 | 106.8 | 28195.2008 | 28195.2008 | 44.375
9 | Plafonds + AKD | 1.5 |  | FS4;FS14;FS5 | 2011-05-18 08:00 | 2011-08-12 17:00 | 63d |  | 0 | 0 | 4.33 | 2182.32 | 2182.32 | 86.375
3 | Akoestische dammen (1) | 1.6 |  | FS8 | 2011-06-07 08:00 | 2011-06-10 17:00 | 4d |  | 0 | 0 | 106.14 | 3396.48 | 3396.48 | 3.375
8 | Schrijnwerk diversen | 1.7 | 3FS | FS12 | 2011-06-14 08:00 | 2011-06-24 17:00 | 9d |  | 0 | 0 | 190.2 | 13694.3998 | 13694.3998 | 10.375
11 | Vaste plafonds (2) | 1.8 | 1FS;6FS | FS4;FS14;FS5 | 2011-07-04 08:00 | 2011-08-12 17:00 | 30d |  | 0 | 0 | 12.32 | 2956.7999 | 2956.7999 | 39.375
2 | Metalen plafonds verdieping 3 | 1.9 | 1FS;6FS | FS4;FS14;FS5 | 2011-07-04 08:00 | 2011-08-19 17:00 | 35d |  | 0 | 0 | 209.26 | 58592.7985 | 58592.7985 | 46.375
13 | Extra ploeg metalen plafonds verdieping 2 | 1.10 | 1FS;6FS | FS4;FS14;FS5 | 2011-07-05 08:00 | 2011-07-15 17:00 | 9d |  | 0 | 0 | 121.42 | 8742.2399 | 8742.2399 | 10.375
12 | Akoestische dammen (2) | 1.11 | 8FS | FS4;FS14;FS5 | 2011-07-11 08:00 | 2011-07-15 17:00 | 5d |  | 0 | 0 | 9.78 | 391.2 | 391.2 | 4.375
4 | Verplaatsbare wanden (1) | 1.12 | 9FS;11FS;2FS;13FS;12FS | FS7;FS15 | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 609.41 | 58503.3574 | 58503.3574 | 15.375
14 | Systeemwanden | 1.13 | 9FS;11FS;2FS;13FS;12FS | FS7;FS15 | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 79.75 | 7656 | 7656 | 15.375
5 | Verplaatsbare wanden (2) | 1.14 | 9FS;11FS;2FS;13FS;12FS | FS7;FS15 | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 519.66 | 49887.3574 | 49887.3574 | 15.375
7 | Deuren | 1.15 | 4FS;14FS;5FS |  | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 405.43 | 29190.9595 | 29190.9595 | 10.375
15 | Schrijnwerk | 1.16 | 4FS;14FS;5FS |  | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 26.94 | 1939.68 | 1939.68 | 10.375
17 | MEERWERK | 1.17 |  |  | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 0.041667

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Office Finishing Works (3) | 1368h |  |  |  |  | 99 | 100 | 101
16 | Diversen | 784h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Opmerkingen oplevering | 520h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Gipswanden | 256h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
1 | Vaste plafonds (1) | 264h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Plafonds + AKD | 504h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Akoestische dammen (1) | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Schrijnwerk diversen | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Vaste plafonds (2) | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Metalen plafonds verdieping 3 | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Extra ploeg metalen plafonds verdieping 2 | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Akoestische dammen (2) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Verplaatsbare wanden (1) | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Systeemwanden | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Verplaatsbare wanden (2) | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Deuren | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Schrijnwerk | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | MEERWERK | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2011-04-30 18:00 |  | TP Name | periode 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (3) | 2011-04-18 08:00 | 2011-12-12 17:00 | 171d |  |  | 1 |  |  | 341468.1141 |  | 20d | [5 empty] | 29047.68 |  | 4.059% |  | 13861.1663 | 185
16 | Diversen | 2011-04-18 08:00 | 2011-08-31 17:00 | 98d |  | 0 | 0 | 2.3 | 1803.2 | 1803.2 |  | 0 | 0 | 1803.2 | 98d | 0 | 0 | 0 | 1803.2 | 0% | Not Started | 0 | 184 | 100 |  | 0 | 100 |  | 0
10 | Opmerkingen oplevering | 2011-09-13 08:00 | 2011-12-12 17:00 | 65d |  | 0 | 0 | 113.01 | 58765.2011 | 58765.2011 |  | 0 | 0 | 58765.2011 | 65d | 0 | 0 | 0 | 58765.2011 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Gipswanden | 2011-05-16 08:00 | 2011-06-28 17:00 | 32d |  | 0 | 0 | 60.82 | 15569.9199 | 15569.9199 | 2011-04-18 08:00 | 10d | 4865.6 | 29193.5999 | 60d | 5411.7998 | 0 | 10277.3998 | 29193.5999 | 14.29% | Started | 2224.2744 | 0 | 100 | 31.25 | 14.2857 | 100 | 66.008 | 14.2857
1 | Vaste plafonds (1) | 2011-05-18 08:00 | 2011-07-01 17:00 | 33d |  | 0 | 0 | 106.8 | 28195.2008 | 28195.2008 | 2011-04-18 08:00 | 10d | 8544.0002 | 51264.0015 | 60d | 2794.3501 | 0 | 11338.3503 | 51264.0015 | 14.29% | Started | 4027.886 | 0 | 100 | 30.303 | 14.2857 | 100 | 40.2138 | 14.2857
9 | Plafonds + AKD | 2011-05-18 08:00 | 2011-08-12 17:00 | 63d |  | 0 | 0 | 4.33 | 2182.32 | 2182.32 |  | 0 | 0 | 2182.32 | 63d | 0 | 0 | 0 | 2182.32 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Akoestische dammen (1) | 2011-06-07 08:00 | 2011-06-10 17:00 | 4d |  | 0 | 0 | 106.14 | 3396.48 | 3396.48 |  | 0 | 0 | 3396.48 | 4d | 0 | 0 | 0 | 3396.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Schrijnwerk diversen | 2011-06-14 08:00 | 2011-06-24 17:00 | 9d |  | 0 | 0 | 190.2 | 13694.3998 | 13694.3998 | 2011-04-25 08:00 | 5d | 7607.9999 | 6086.3999 | 4d | -748.32 | 0 | 6859.6799 | 6086.3999 | 55.56% | Started | 7608.006 | 0 | 100 | 55.5556 | 55.5556 | 100 | 50.0911 | 55.5556
11 | Vaste plafonds (2) | 2011-07-04 08:00 | 2011-08-12 17:00 | 30d |  | 0 | 0 | 12.32 | 2956.7999 | 2956.7999 |  | 0 | 0 | 2956.7999 | 30d | 0 | 0 | 0 | 2956.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Metalen plafonds verdieping 3 | 2011-07-04 08:00 | 2011-08-19 17:00 | 35d |  | 0 | 0 | 209.26 | 58592.7985 | 58592.7985 |  | 0 | 0 | 58592.7985 | 35d | 0 | 0 | 0 | 58592.7985 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Extra ploeg metalen plafonds verdieping 2 | 2011-07-05 08:00 | 2011-07-15 17:00 | 9d |  | 0 | 0 | 121.42 | 8742.2399 | 8742.2399 |  | 0 | 0 | 8742.2399 | 9d | 0 | 0 | 0 | 8742.2399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Akoestische dammen (2) | 2011-07-11 08:00 | 2011-07-15 17:00 | 5d |  | 0 | 0 | 9.78 | 391.2 | 391.2 |  | 0 | 0 | 391.2 | 5d | 0 | 0 | 0 | 391.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Verplaatsbare wanden (1) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 609.41 | 58503.3574 | 58503.3574 |  | 0 | 0 | 58503.3574 | 12d | 0 | 0 | 0 | 58503.3574 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Systeemwanden | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 79.75 | 7656 | 7656 |  | 0 | 0 | 7656 | 12d | 0 | 0 | 0 | 7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Verplaatsbare wanden (2) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 519.66 | 49887.3574 | 49887.3574 |  | 0 | 0 | 49887.3574 | 12d | 0 | 0 | 0 | 49887.3574 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Deuren | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 405.43 | 29190.9595 | 29190.9595 |  | 0 | 0 | 29190.9595 | 9d | 0 | 0 | 0 | 29190.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Schrijnwerk | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 26.94 | 1939.68 | 1939.68 |  | 0 | 0 | 1939.68 | 9d | 0 | 0 | 0 | 1939.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | MEERWERK | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-04-18 08:00 | 20d | 1 | 0 | 0 | 571.25 | 0 | 572.25 | 0 | 100% | Finished | 1 | 1 | 100 | 16000 | 100 | 100 | 57225 | 100

## TP2
| TP Status Date | 2011-05-31 18:00 |  | TP Name | periode 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (3) | 2011-04-18 08:00 | 2011-12-12 17:00 | 171d |  |  | 1 |  |  | 341468.1141 |  | 32d | [5 empty] | 84839.0395 |  | 21.67% |  | 74011.3206 | 15318.9202
16 | Diversen | 2011-04-18 08:00 | 2011-08-31 17:00 | 98d |  | 0 | 0 | 2.3 | 1803.2 | 1803.2 |  | 0 | 0 | 1803.2 | 98d | 0 | 0 | 0 | 1803.2 | 0% | Not Started | 0 | 588.8 | 100 |  | 0 | 100 |  | 0
10 | Opmerkingen oplevering | 2011-09-13 08:00 | 2011-12-12 17:00 | 65d |  | 0 | 0 | 113.01 | 58765.2011 | 58765.2011 |  | 0 | 0 | 58765.2011 | 65d | 0 | 0 | 0 | 58765.2011 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Gipswanden | 2011-05-16 08:00 | 2011-06-28 17:00 | 32d |  | 0 | 0 | 60.82 | 15569.9199 | 15569.9199 | 2011-04-18 08:00 | 30d | 14596.7999 | 19462.3999 | 40d | -2363.71 | 0 | 12233.09 | 19462.3999 | 42.86% | Started | 6672.8229 | 5838.72 | 100 | 93.75 | 42.8571 | 100 | 78.5687 | 42.8571
1 | Vaste plafonds (1) | 2011-05-18 08:00 | 2011-07-01 17:00 | 33d |  | 0 | 0 | 106.8 | 28195.2008 | 28195.2008 | 2011-04-18 08:00 | 30d | 25632.0007 | 34176.001 | 40d | -1759.38 | 0 | 23872.6207 | 34176.001 | 42.86% | Started | 12083.6576 | 8544.0002 | 100 | 90.9091 | 42.8571 | 100 | 84.6691 | 42.8571
9 | Plafonds + AKD | 2011-05-18 08:00 | 2011-08-12 17:00 | 63d |  | 0 | 0 | 4.33 | 2182.32 | 2182.32 | 2011-05-02 08:00 | 22d | 762.08 | 0 | 0 | 1174.5699 | 0 | 1936.6499 | 0 | 100% | Finished | 2182.32 | 346.4 | 100 | 34.9206 | 100 | 100 | 88.7427 | 100
3 | Akoestische dammen (1) | 2011-06-07 08:00 | 2011-06-10 17:00 | 4d |  | 0 | 0 | 106.14 | 3396.48 | 3396.48 | 2011-05-27 08:00 | 3d | 2547.36 | 849.12 | 1d | -158.12 | 0 | 2389.24 | 849.12 | 75% | Started | 2547.36 | 0 | 100 | 75 | 75 | 100 | 70.3446 | 75
8 | Schrijnwerk diversen | 2011-06-14 08:00 | 2011-06-24 17:00 | 9d |  | 0 | 0 | 190.2 | 13694.3998 | 13694.3998 | 2011-04-25 08:00 | 9d | 13694.3998 | 0 | 0 | -1547.05 | 0 | 12147.3497 | 0 | 100% | Finished | 13694.3998 | 0 | 100 | 100 | 100 | 100 | 88.703 | 100
11 | Vaste plafonds (2) | 2011-07-04 08:00 | 2011-08-12 17:00 | 30d |  | 0 | 0 | 12.32 | 2956.7999 | 2956.7999 |  | 0 | 0 | 2956.7999 | 30d | 0 | 0 | 0 | 2956.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Metalen plafonds verdieping 3 | 2011-07-04 08:00 | 2011-08-19 17:00 | 35d |  | 0 | 0 | 209.26 | 58592.7985 | 58592.7985 | 2011-05-02 08:00 | 22d | 36829.759 | 21763.0394 | 13d | -10484.5098 | 0 | 26345.2493 | 21763.0394 | 62.86% | Started | 36829.7603 | 0 | 100 | 62.8571 | 62.8571 | 100 | 44.9633 | 62.8571
13 | Extra ploeg metalen plafonds verdieping 2 | 2011-07-05 08:00 | 2011-07-15 17:00 | 9d |  | 0 | 0 | 121.42 | 8742.2399 | 8742.2399 |  | 0 | 0 | 8742.2399 | 9d | 0 | 0 | 0 | 8742.2399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Akoestische dammen (2) | 2011-07-11 08:00 | 2011-07-15 17:00 | 5d |  | 0 | 0 | 9.78 | 391.2 | 391.2 |  | 0 | 0 | 391.2 | 5d | 0 | 0 | 0 | 391.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Verplaatsbare wanden (1) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 609.41 | 58503.3574 | 58503.3574 |  | 0 | 0 | 58503.3574 | 12d | 0 | 0 | 0 | 58503.3574 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Systeemwanden | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 79.75 | 7656 | 7656 |  | 0 | 0 | 7656 | 12d | 0 | 0 | 0 | 7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Verplaatsbare wanden (2) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 519.66 | 49887.3574 | 49887.3574 |  | 0 | 0 | 49887.3574 | 12d | 0 | 0 | 0 | 49887.3574 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Deuren | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 405.43 | 29190.9595 | 29190.9595 |  | 0 | 0 | 29190.9595 | 9d | 0 | 0 | 0 | 29190.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Schrijnwerk | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 26.94 | 1939.68 | 1939.68 |  | 0 | 0 | 1939.68 | 9d | 0 | 0 | 0 | 1939.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | MEERWERK | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-04-18 08:00 | 30d | 1 | 0 | 0 | 5913.8398 | 0 | 5914.8398 | 0 | 100% | Finished | 1 | 1 | 100 | 24000 | 100 | 100 | 591483.9844 | 100

## TP3
| TP Status Date | 2011-06-30 18:00 |  | TP Name | periode 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (3) | 2011-04-18 08:00 | 2011-12-12 17:00 | 171d |  |  | 1 |  |  | 341468.1141 |  | 54d | [5 empty] | 168378.0474 |  | 56.84% |  | 194104.9305 | 62104.6804
16 | Diversen | 2011-04-18 08:00 | 2011-08-31 17:00 | 98d |  | 0 | 0 | 2.3 | 1803.2 | 1803.2 |  | 0 | 0 | 1803.2 | 98d | 0 | 0 | 0 | 1803.2 | 0% | Not Started | 0 | 993.6 | 100 |  | 0 | 100 |  | 0
10 | Opmerkingen oplevering | 2011-09-13 08:00 | 2011-12-12 17:00 | 65d |  | 0 | 0 | 113.01 | 58765.2011 | 58765.2011 | 2011-06-01 08:00 | 22d | 19889.7604 | 18081.6003 | 20d | 7480.54 | 0 | 27370.3004 | 18081.6003 | 52.38% | Started | 30781.7737 | 0 | 100 | 33.8462 | 52.381 | 100 | 46.5757 | 52.381
6 | Gipswanden | 2011-05-16 08:00 | 2011-06-28 17:00 | 32d |  | 0 | 0 | 60.82 | 15569.9199 | 15569.9199 | 2011-04-18 08:00 | 50d | 24327.9999 | 9731.2 | 20d | -12104.9102 | 0 | 12223.0897 | 9731.2 | 71.43% | Started | 11121.3716 | 15569.9199 | 100 | 156.25 | 71.4286 | 100 | 78.5045 | 71.4286
1 | Vaste plafonds (1) | 2011-05-18 08:00 | 2011-07-01 17:00 | 33d |  | 0 | 0 | 106.8 | 28195.2008 | 28195.2008 | 2011-04-18 08:00 | 50d | 42720.0012 | 17088.0005 | 20d | -17618.1895 | 0 | 25101.8118 | 17088.0005 | 71.43% | Started | 20139.4296 | 27340.8008 | 100 | 151.5152 | 71.4286 | 100 | 89.0287 | 71.4286
9 | Plafonds + AKD | 2011-05-18 08:00 | 2011-08-12 17:00 | 63d |  | 0 | 0 | 4.33 | 2182.32 | 2182.32 | 2011-05-02 08:00 | 22d | 762.08 | 0 | 0 | 1174.5699 | 0 | 1936.6499 | 0 | 100% | Finished | 2182.32 | 1108.48 | 100 | 34.9206 | 100 | 100 | 88.7427 | 100
3 | Akoestische dammen (1) | 2011-06-07 08:00 | 2011-06-10 17:00 | 4d |  | 0 | 0 | 106.14 | 3396.48 | 3396.48 | 2011-05-27 08:00 | 4d | 3396.48 | 0 | 0 | -383.77 | 0 | 3012.71 | 0 | 100% | Finished | 3396.48 | 3396.48 | 100 | 100 | 100 | 100 | 88.7009 | 100
8 | Schrijnwerk diversen | 2011-06-14 08:00 | 2011-06-24 17:00 | 9d |  | 0 | 0 | 190.2 | 13694.3998 | 13694.3998 | 2011-04-25 08:00 | 9d | 13694.3998 | 0 | 0 | -1547.05 | 0 | 12147.3497 | 0 | 100% | Finished | 13694.3998 | 13694.3998 | 100 | 100 | 100 | 100 | 88.703 | 100
11 | Vaste plafonds (2) | 2011-07-04 08:00 | 2011-08-12 17:00 | 30d |  | 0 | 0 | 12.32 | 2956.7999 | 2956.7999 |  | 0 | 0 | 2956.7999 | 30d | 0 | 0 | 0 | 2956.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Metalen plafonds verdieping 3 | 2011-07-04 08:00 | 2011-08-19 17:00 | 35d |  | 0 | 0 | 209.26 | 58592.7985 | 58592.7985 | 2011-05-02 08:00 | 35d | 58592.7985 | 0 | 0 | -16992.0508 | 0 | 41600.7477 | 0 | 100% | Finished | 58592.7985 | 0 | 100 | 100 | 100 | 100 | 70.9998 | 100
13 | Extra ploeg metalen plafonds verdieping 2 | 2011-07-05 08:00 | 2011-07-15 17:00 | 9d |  | 0 | 0 | 121.42 | 8742.2399 | 8742.2399 |  | 0 | 0 | 8742.2399 | 9d | 0 | 0 | 0 | 8742.2399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Akoestische dammen (2) | 2011-07-11 08:00 | 2011-07-15 17:00 | 5d |  | 0 | 0 | 9.78 | 391.2 | 391.2 |  | 0 | 0 | 391.2 | 5d | 0 | 0 | 0 | 391.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Verplaatsbare wanden (1) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 609.41 | 58503.3574 | 58503.3574 | 2011-06-23 08:00 | 6d | 29251.6787 | 29251.6787 | 6d | -7196.8198 | 0 | 22054.8589 | 29251.6787 | 50% | Started | 29251.6787 | 0 | 100 | 50 | 50 | 100 | 37.6984 | 50
14 | Systeemwanden | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 79.75 | 7656 | 7656 |  | 0 | 0 | 7656 | 12d | 0 | 0 | 0 | 7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Verplaatsbare wanden (2) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 519.66 | 49887.3574 | 49887.3574 | 2011-06-23 08:00 | 6d | 24943.6787 | 24943.6787 | 6d | -10188.1396 | 0 | 14755.5391 | 24943.6787 | 50% | Started | 24943.6787 | 0 | 100 | 50 | 50 | 100 | 29.5777 | 50
7 | Deuren | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 405.43 | 29190.9595 | 29190.9595 |  | 0 | 0 | 29190.9595 | 9d | 0 | 0 | 0 | 29190.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Schrijnwerk | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 26.94 | 1939.68 | 1939.68 |  | 0 | 0 | 1939.68 | 9d | 0 | 0 | 0 | 1939.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | MEERWERK | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-04-18 08:00 | 50d | 1 | 0 | 0 | 8173.9902 | 0 | 8174.9902 | 0 | 100% | Finished | 1 | 1 | 100 | 40000 | 100 | 100 | 817499.0234 | 100

## TP4
| TP Status Date | 2011-07-31 18:00 |  | TP Name | periode 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (3) | 2011-04-18 08:00 | 2011-12-12 17:00 | 171d |  |  | 1 |  |  | 341468.1141 |  | 75d | [5 empty] | 298833.8058 |  | 100% |  | 341468.1141 | 108659.1594
16 | Diversen | 2011-04-18 08:00 | 2011-08-31 17:00 | 98d |  | 0 | 0 | 2.3 | 1803.2 | 1803.2 | 2011-07-01 08:00 | 21d | 386.4 | 0 | 0 | 709.94 | 0 | 1096.34 | 0 | 100% | Finished | 1803.2 | 1380 | 100 | 21.4286 | 100 | 100 | 60.7997 | 100
10 | Opmerkingen oplevering | 2011-09-13 08:00 | 2011-12-12 17:00 | 65d |  | 0 | 0 | 113.01 | 58765.2011 | 58765.2011 | 2011-06-01 08:00 | 42d | 37971.3607 | 0 | 0 | 16769.2402 | 0 | 54740.601 | 0 | 100% | Finished | 58765.2011 | 0 | 100 | 64.6154 | 100 | 100 | 93.1514 | 100
6 | Gipswanden | 2011-05-16 08:00 | 2011-06-28 17:00 | 32d |  | 0 | 0 | 60.82 | 15569.9199 | 15569.9199 | 2011-04-18 08:00 | 70d | 34059.1998 | 0 | 0 | -18276.6602 | 0 | 15782.5397 | 0 | 100% | Finished | 15569.9199 | 15569.9199 | 100 | 218.75 | 100 | 100 | 101.3656 | 100
1 | Vaste plafonds (1) | 2011-05-18 08:00 | 2011-07-01 17:00 | 33d |  | 0 | 0 | 106.8 | 28195.2008 | 28195.2008 | 2011-04-18 08:00 | 70d | 59808.0017 | 0 | 0 | -31547.1992 | 0 | 28260.8025 | 0 | 100% | Finished | 28195.2008 | 28195.2008 | 100 | 212.1212 | 100 | 100 | 100.2327 | 100
9 | Plafonds + AKD | 2011-05-18 08:00 | 2011-08-12 17:00 | 63d |  | 0 | 0 | 4.33 | 2182.32 | 2182.32 | 2011-05-02 08:00 | 22d | 762.08 | 0 | 0 | 1174.5699 | 0 | 1936.6499 | 0 | 100% | Finished | 2182.32 | 1835.92 | 100 | 34.9206 | 100 | 100 | 88.7427 | 100
3 | Akoestische dammen (1) | 2011-06-07 08:00 | 2011-06-10 17:00 | 4d |  | 0 | 0 | 106.14 | 3396.48 | 3396.48 | 2011-05-27 08:00 | 4d | 3396.48 | 0 | 0 | -383.77 | 0 | 3012.71 | 0 | 100% | Finished | 3396.48 | 3396.48 | 100 | 100 | 100 | 100 | 88.7009 | 100
8 | Schrijnwerk diversen | 2011-06-14 08:00 | 2011-06-24 17:00 | 9d |  | 0 | 0 | 190.2 | 13694.3998 | 13694.3998 | 2011-04-25 08:00 | 9d | 13694.3998 | 0 | 0 | -1547.05 | 0 | 12147.3497 | 0 | 100% | Finished | 13694.3998 | 13694.3998 | 100 | 100 | 100 | 100 | 88.703 | 100
11 | Vaste plafonds (2) | 2011-07-04 08:00 | 2011-08-12 17:00 | 30d |  | 0 | 0 | 12.32 | 2956.7999 | 2956.7999 | 2011-07-01 08:00 | 21d | 2069.7599 | 0 | 0 | 292.54 | 0 | 2362.3 | 0 | 100% | Finished | 2956.7999 | 1971.2 | 100 | 70 | 100 | 100 | 79.8938 | 100
2 | Metalen plafonds verdieping 3 | 2011-07-04 08:00 | 2011-08-19 17:00 | 35d |  | 0 | 0 | 209.26 | 58592.7985 | 58592.7985 | 2011-05-02 08:00 | 35d | 58592.7985 | 0 | 0 | -16992.0508 | 0 | 41600.7477 | 0 | 100% | Finished | 58592.7985 | 33481.5991 | 100 | 100 | 100 | 100 | 70.9998 | 100
13 | Extra ploeg metalen plafonds verdieping 2 | 2011-07-05 08:00 | 2011-07-15 17:00 | 9d |  | 0 | 0 | 121.42 | 8742.2399 | 8742.2399 | 2011-07-01 08:00 | 9d | 8742.2399 | 0 | 0 | -2103.24 | 0 | 6638.9999 | 0 | 100% | Finished | 8742.2399 | 8742.2399 | 100 | 100 | 100 | 100 | 75.9416 | 100
12 | Akoestische dammen (2) | 2011-07-11 08:00 | 2011-07-15 17:00 | 5d |  | 0 | 0 | 9.78 | 391.2 | 391.2 | 2011-07-01 08:00 | 5d | 391.2 | 0 | 0 | -44.05 | 0 | 347.15 | 0 | 100% | Finished | 391.2 | 391.2 | 100 | 100 | 100 | 100 | 88.7398 | 100
4 | Verplaatsbare wanden (1) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 609.41 | 58503.3574 | 58503.3574 | 2011-06-23 08:00 | 12d | 58503.3574 | 0 | 0 | -19022.0391 | 0 | 39481.3184 | 0 | 100% | Finished | 58503.3574 | 0 | 100 | 100 | 100 | 100 | 67.4856 | 100
14 | Systeemwanden | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 79.75 | 7656 | 7656 | 2011-07-01 08:00 | 12d | 7656 | 0 | 0 | -1607.09 | 0 | 6048.91 | 0 | 100% | Finished | 7656 | 0 | 100 | 100 | 100 | 100 | 79.0088 | 100
5 | Verplaatsbare wanden (2) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 519.66 | 49887.3574 | 49887.3574 | 2011-06-23 08:00 | 12d | 49887.3574 | 0 | 0 | -6953.98 | 0 | 42933.3774 | 0 | 100% | Finished | 49887.3574 | 0 | 100 | 100 | 100 | 100 | 86.0606 | 100
7 | Deuren | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 405.43 | 29190.9595 | 29190.9595 | 2011-07-01 08:00 | 9d | 29190.9595 | 0 | 0 | -2634 | 0 | 26556.9595 | 0 | 100% | Finished | 29190.9595 | 0 | 100 | 100 | 100 | 100 | 90.9767 | 100
15 | Schrijnwerk | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 26.94 | 1939.68 | 1939.68 | 2011-07-01 08:00 | 9d | 1939.68 | 0 | 0 | -175.58 | 0 | 1764.1 | 0 | 100% | Finished | 1939.68 | 0 | 100 | 100 | 100 | 100 | 90.948 | 100
17 | MEERWERK | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-04-18 08:00 | 70d | 1 | 0 | 0 | 14121.9502 | 0 | 14122.9502 | 0 | 100% | Finished | 1 | 1 | 100 | 56000 | 100 | 100 | 1412295.0195 | 100

## TP5
| TP Status Date | 2011-08-31 18:00 |  | TP Name | periode 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (3) | 2011-04-18 08:00 | 2011-12-12 17:00 | 171d |  |  | 1 |  |  | 341468.1141 |  | 75d | [5 empty] | 298833.8058 |  | 100% |  | 341468.1141 | 203219.4757
16 | Diversen | 2011-04-18 08:00 | 2011-08-31 17:00 | 98d |  | 0 | 0 | 2.3 | 1803.2 | 1803.2 | 2011-07-01 08:00 | 21d | 386.4 | 0 | 0 | 709.94 | 0 | 1096.34 | 0 | 100% | Finished | 1803.2 | 1803.2 | 100 | 21.4286 | 100 | 100 | 60.7997 | 100
10 | Opmerkingen oplevering | 2011-09-13 08:00 | 2011-12-12 17:00 | 65d |  | 0 | 0 | 113.01 | 58765.2011 | 58765.2011 | 2011-06-01 08:00 | 42d | 37971.3607 | 0 | 0 | 16769.2402 | 0 | 54740.601 | 0 | 100% | Finished | 58765.2011 | 0 | 100 | 64.6154 | 100 | 100 | 93.1514 | 100
6 | Gipswanden | 2011-05-16 08:00 | 2011-06-28 17:00 | 32d |  | 0 | 0 | 60.82 | 15569.9199 | 15569.9199 | 2011-04-18 08:00 | 70d | 34059.1998 | 0 | 0 | -18276.6602 | 0 | 15782.5397 | 0 | 100% | Finished | 15569.9199 | 15569.9199 | 100 | 218.75 | 100 | 100 | 101.3656 | 100
1 | Vaste plafonds (1) | 2011-05-18 08:00 | 2011-07-01 17:00 | 33d |  | 0 | 0 | 106.8 | 28195.2008 | 28195.2008 | 2011-04-18 08:00 | 70d | 59808.0017 | 0 | 0 | -31547.1992 | 0 | 28260.8025 | 0 | 100% | Finished | 28195.2008 | 28195.2008 | 100 | 212.1212 | 100 | 100 | 100.2327 | 100
9 | Plafonds + AKD | 2011-05-18 08:00 | 2011-08-12 17:00 | 63d |  | 0 | 0 | 4.33 | 2182.32 | 2182.32 | 2011-05-02 08:00 | 22d | 762.08 | 0 | 0 | 1174.5699 | 0 | 1936.6499 | 0 | 100% | Finished | 2182.32 | 2182.32 | 100 | 34.9206 | 100 | 100 | 88.7427 | 100
3 | Akoestische dammen (1) | 2011-06-07 08:00 | 2011-06-10 17:00 | 4d |  | 0 | 0 | 106.14 | 3396.48 | 3396.48 | 2011-05-27 08:00 | 4d | 3396.48 | 0 | 0 | -383.77 | 0 | 3012.71 | 0 | 100% | Finished | 3396.48 | 3396.48 | 100 | 100 | 100 | 100 | 88.7009 | 100
8 | Schrijnwerk diversen | 2011-06-14 08:00 | 2011-06-24 17:00 | 9d |  | 0 | 0 | 190.2 | 13694.3998 | 13694.3998 | 2011-04-25 08:00 | 9d | 13694.3998 | 0 | 0 | -1547.05 | 0 | 12147.3497 | 0 | 100% | Finished | 13694.3998 | 13694.3998 | 100 | 100 | 100 | 100 | 88.703 | 100
11 | Vaste plafonds (2) | 2011-07-04 08:00 | 2011-08-12 17:00 | 30d |  | 0 | 0 | 12.32 | 2956.7999 | 2956.7999 | 2011-07-01 08:00 | 21d | 2069.7599 | 0 | 0 | 292.54 | 0 | 2362.3 | 0 | 100% | Finished | 2956.7999 | 2956.7999 | 100 | 70 | 100 | 100 | 79.8938 | 100
2 | Metalen plafonds verdieping 3 | 2011-07-04 08:00 | 2011-08-19 17:00 | 35d |  | 0 | 0 | 209.26 | 58592.7985 | 58592.7985 | 2011-05-02 08:00 | 35d | 58592.7985 | 0 | 0 | -16992.0508 | 0 | 41600.7477 | 0 | 100% | Finished | 58592.7985 | 58592.7985 | 100 | 100 | 100 | 100 | 70.9998 | 100
13 | Extra ploeg metalen plafonds verdieping 2 | 2011-07-05 08:00 | 2011-07-15 17:00 | 9d |  | 0 | 0 | 121.42 | 8742.2399 | 8742.2399 | 2011-07-01 08:00 | 9d | 8742.2399 | 0 | 0 | -2103.24 | 0 | 6638.9999 | 0 | 100% | Finished | 8742.2399 | 8742.2399 | 100 | 100 | 100 | 100 | 75.9416 | 100
12 | Akoestische dammen (2) | 2011-07-11 08:00 | 2011-07-15 17:00 | 5d |  | 0 | 0 | 9.78 | 391.2 | 391.2 | 2011-07-01 08:00 | 5d | 391.2 | 0 | 0 | -44.05 | 0 | 347.15 | 0 | 100% | Finished | 391.2 | 391.2 | 100 | 100 | 100 | 100 | 88.7398 | 100
4 | Verplaatsbare wanden (1) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 609.41 | 58503.3574 | 58503.3574 | 2011-06-23 08:00 | 12d | 58503.3574 | 0 | 0 | -19022.0391 | 0 | 39481.3184 | 0 | 100% | Finished | 58503.3574 | 34126.9585 | 100 | 100 | 100 | 100 | 67.4856 | 100
14 | Systeemwanden | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 79.75 | 7656 | 7656 | 2011-07-01 08:00 | 12d | 7656 | 0 | 0 | -1607.09 | 0 | 6048.91 | 0 | 100% | Finished | 7656 | 4466 | 100 | 100 | 100 | 100 | 79.0088 | 100
5 | Verplaatsbare wanden (2) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 519.66 | 49887.3574 | 49887.3574 | 2011-06-23 08:00 | 12d | 49887.3574 | 0 | 0 | -6953.98 | 0 | 42933.3774 | 0 | 100% | Finished | 49887.3574 | 29100.9585 | 100 | 100 | 100 | 100 | 86.0606 | 100
7 | Deuren | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 405.43 | 29190.9595 | 29190.9595 | 2011-07-01 08:00 | 9d | 29190.9595 | 0 | 0 | -2634 | 0 | 26556.9595 | 0 | 100% | Finished | 29190.9595 | 0 | 100 | 100 | 100 | 100 | 90.9767 | 100
15 | Schrijnwerk | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 26.94 | 1939.68 | 1939.68 | 2011-07-01 08:00 | 9d | 1939.68 | 0 | 0 | -175.58 | 0 | 1764.1 | 0 | 100% | Finished | 1939.68 | 0 | 100 | 100 | 100 | 100 | 90.948 | 100
17 | MEERWERK | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-04-18 08:00 | 70d | 1 | 0 | 0 | 14121.9502 | 0 | 14122.9502 | 0 | 100% | Finished | 1 | 1 | 100 | 56000 | 100 | 100 | 1412295.0195 | 100

## TP6
| TP Status Date | 2011-09-30 18:00 |  | TP Name | periode 6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (3) | 2011-04-18 08:00 | 2011-12-12 17:00 | 171d |  |  | 1 |  |  | 341468.1141 |  | 115d | [5 empty] | 308343.7755 |  | 100% |  | 341468.1141 | 295360.0333
16 | Diversen | 2011-04-18 08:00 | 2011-08-31 17:00 | 98d |  | 0 | 0 | 2.3 | 1803.2 | 1803.2 | 2011-07-01 08:00 | 21d | 386.4 | 0 | 0 | 709.94 | 0 | 1096.34 | 0 | 100% | Finished | 1803.2 | 1803.2 | 100 | 21.4286 | 100 | 100 | 60.7997 | 100
10 | Opmerkingen oplevering | 2011-09-13 08:00 | 2011-12-12 17:00 | 65d |  | 0 | 0 | 113.01 | 58765.2011 | 58765.2011 | 2011-06-01 08:00 | 42d | 37971.3607 | 0 | 0 | 16769.2402 | 0 | 54740.601 | 0 | 100% | Finished | 58765.2011 | 12657.1202 | 100 | 64.6154 | 100 | 100 | 93.1514 | 100
6 | Gipswanden | 2011-05-16 08:00 | 2011-06-28 17:00 | 32d |  | 0 | 0 | 60.82 | 15569.9199 | 15569.9199 | 2011-04-18 08:00 | 70d | 34059.1998 | 0 | 0 | -18276.6602 | 0 | 15782.5397 | 0 | 100% | Finished | 15569.9199 | 15569.9199 | 100 | 218.75 | 100 | 100 | 101.3656 | 100
1 | Vaste plafonds (1) | 2011-05-18 08:00 | 2011-07-01 17:00 | 33d |  | 0 | 0 | 106.8 | 28195.2008 | 28195.2008 | 2011-04-18 08:00 | 70d | 59808.0017 | 0 | 0 | -31547.1992 | 0 | 28260.8025 | 0 | 100% | Finished | 28195.2008 | 28195.2008 | 100 | 212.1212 | 100 | 100 | 100.2327 | 100
9 | Plafonds + AKD | 2011-05-18 08:00 | 2011-08-12 17:00 | 63d |  | 0 | 0 | 4.33 | 2182.32 | 2182.32 | 2011-05-02 08:00 | 22d | 762.08 | 0 | 0 | 1174.5699 | 0 | 1936.6499 | 0 | 100% | Finished | 2182.32 | 2182.32 | 100 | 34.9206 | 100 | 100 | 88.7427 | 100
3 | Akoestische dammen (1) | 2011-06-07 08:00 | 2011-06-10 17:00 | 4d |  | 0 | 0 | 106.14 | 3396.48 | 3396.48 | 2011-05-27 08:00 | 4d | 3396.48 | 0 | 0 | -383.77 | 0 | 3012.71 | 0 | 100% | Finished | 3396.48 | 3396.48 | 100 | 100 | 100 | 100 | 88.7009 | 100
8 | Schrijnwerk diversen | 2011-06-14 08:00 | 2011-06-24 17:00 | 9d |  | 0 | 0 | 190.2 | 13694.3998 | 13694.3998 | 2011-04-25 08:00 | 9d | 13694.3998 | 0 | 0 | -1547.05 | 0 | 12147.3497 | 0 | 100% | Finished | 13694.3998 | 13694.3998 | 100 | 100 | 100 | 100 | 88.703 | 100
11 | Vaste plafonds (2) | 2011-07-04 08:00 | 2011-08-12 17:00 | 30d |  | 0 | 0 | 12.32 | 2956.7999 | 2956.7999 | 2011-07-01 08:00 | 21d | 2069.7599 | 0 | 0 | 292.54 | 0 | 2362.3 | 0 | 100% | Finished | 2956.7999 | 2956.7999 | 100 | 70 | 100 | 100 | 79.8938 | 100
2 | Metalen plafonds verdieping 3 | 2011-07-04 08:00 | 2011-08-19 17:00 | 35d |  | 0 | 0 | 209.26 | 58592.7985 | 58592.7985 | 2011-05-02 08:00 | 35d | 58592.7985 | 0 | 0 | -16992.0508 | 0 | 41600.7477 | 0 | 100% | Finished | 58592.7985 | 58592.7985 | 100 | 100 | 100 | 100 | 70.9998 | 100
13 | Extra ploeg metalen plafonds verdieping 2 | 2011-07-05 08:00 | 2011-07-15 17:00 | 9d |  | 0 | 0 | 121.42 | 8742.2399 | 8742.2399 | 2011-07-01 08:00 | 9d | 8742.2399 | 0 | 0 | -2103.24 | 0 | 6638.9999 | 0 | 100% | Finished | 8742.2399 | 8742.2399 | 100 | 100 | 100 | 100 | 75.9416 | 100
12 | Akoestische dammen (2) | 2011-07-11 08:00 | 2011-07-15 17:00 | 5d |  | 0 | 0 | 9.78 | 391.2 | 391.2 | 2011-07-01 08:00 | 5d | 391.2 | 0 | 0 | -44.05 | 0 | 347.15 | 0 | 100% | Finished | 391.2 | 391.2 | 100 | 100 | 100 | 100 | 88.7398 | 100
4 | Verplaatsbare wanden (1) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 609.41 | 58503.3574 | 58503.3574 | 2011-06-23 08:00 | 12d | 58503.3574 | 0 | 0 | -19022.0391 | 0 | 39481.3184 | 0 | 100% | Finished | 58503.3574 | 58503.3574 | 100 | 100 | 100 | 100 | 67.4856 | 100
14 | Systeemwanden | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 79.75 | 7656 | 7656 | 2011-07-01 08:00 | 12d | 7656 | 0 | 0 | -1607.09 | 0 | 6048.91 | 0 | 100% | Finished | 7656 | 7656 | 100 | 100 | 100 | 100 | 79.0088 | 100
5 | Verplaatsbare wanden (2) | 2011-08-23 08:00 | 2011-09-07 17:00 | 12d |  | 0 | 0 | 519.66 | 49887.3574 | 49887.3574 | 2011-06-23 08:00 | 12d | 49887.3574 | 0 | 0 | -6953.98 | 0 | 42933.3774 | 0 | 100% | Finished | 49887.3574 | 49887.3574 | 100 | 100 | 100 | 100 | 86.0606 | 100
7 | Deuren | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 405.43 | 29190.9595 | 29190.9595 | 2011-07-01 08:00 | 9d | 29190.9595 | 0 | 0 | -2634 | 0 | 26556.9595 | 0 | 100% | Finished | 29190.9595 | 29190.9595 | 100 | 100 | 100 | 100 | 90.9767 | 100
15 | Schrijnwerk | 2011-09-13 08:00 | 2011-09-23 17:00 | 9d |  | 0 | 0 | 26.94 | 1939.68 | 1939.68 | 2011-07-01 08:00 | 9d | 1939.68 | 0 | 0 | -175.58 | 0 | 1764.1 | 0 | 100% | Finished | 1939.68 | 1939.68 | 100 | 100 | 100 | 100 | 90.948 | 100
17 | MEERWERK | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-04-18 08:00 | 115d | 1 | 0 | 0 | 23631.9199 | 0 | 23632.9199 | 0 | 100% | Finished | 1 | 1 | 100 | 92000 | 100 | 100 | 2363291.9922 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
periode 1 | 2011-04-18 08:00 | 2011-04-30 18:00 | 185 | 13861.1663 | 29047.68 | 2011-05-30 17:00 | 13676.1663 | 7493% | -15186.5137 | 47.72% | 21d | 310% | 44.91% | 2011-12-02 09:00 | 2011-04-20 10:00 | 2011-04-22 15:00 | 2011-04-15 17:00 | 2011-04-20 10:00 | 2011-04-15 17:00 | 2011-11-11 17:00 | 2011-07-04 09:00 | 2011-09-09 14:00 | 356654.6278 | 715585.9951 | 33420.132 | 134727.3406 | 38210.6597 | 250511.6526 | 50366.827 | 356082.5281 | 3.1 | 0.47719 | 74.9252 | 0.44906 | 21 | 0.47719 | 1 | 3.1 | 1
periode 2 | 2011-04-30 18:00 | 2011-05-31 18:00 | 15318.9202 | 74011.3206 | 84839.0395 | 2011-07-08 11:00 | 58692.4004 | 483.1% | -10827.7189 | 87.24% | 27d 3h | 185.5% | 58.72% | 2011-11-01 14:00 | 2011-06-06 11:00 | 2011-06-13 14:00 | 2011-06-23 11:00 | 2011-06-06 11:00 | 2011-06-06 16:00 | 2011-11-03 14:00 | 2011-08-24 09:00 | 2011-09-05 17:00 | 352295.833 | 391424.2658 | 140197.4528 | 228984.1745 | 148296.286 | 250072.3404 | 245553.6686 | 335034.2493 | 1.8555 | 0.87237 | 4.8314 | 0.58723 | 27.375 | 0.87237 | 1 | 1.8555 | 1
periode 3 | 2011-05-31 18:00 | 2011-06-30 18:00 | 62104.6804 | 194104.9305 | 168378.0474 | 2011-08-31 09:00 | 132000.2501 | 312.5% | 25726.8831 | 115.3% | 43d 1h | 179.9% | 83.87% | 2011-09-09 16:00 | 2011-07-01 15:00 | 2011-06-22 12:00 | 2011-07-05 10:00 | 2011-07-01 15:00 | 2011-07-01 14:00 | 2011-10-12 16:00 | 2011-08-29 09:00 | 2011-08-19 14:00 | 315741.231 | 296209.5509 | 215527.5114 | 250309.7016 | 209278.269 | 239450.3891 | 263615.526 | 283329.8623 | 1.7986 | 1.1528 | 3.1254 | 0.83867 | 43.125 | 1.1528 | 1 | 1.7986 | 1
periode 4 | 2011-06-30 18:00 | 2011-07-31 18:00 | 108659.1594 | 341468.1141 | 298833.8058 | 2011-12-12 17:00 | 232808.9548 | 314.3% | 42634.3083 | 114.3% | 96d | 228% | 100% | 2011-07-01 11:00 | 2011-07-01 11:00 | 2011-06-22 14:00 | 2011-05-02 10:00 | 2011-07-01 11:00 | 2011-07-05 17:00 | 2011-07-29 17:00 | 2011-07-29 17:00 | 2011-07-29 17:00 | 298833.8058 | 298833.8058 | 298833.8058 | 298833.8058 | 298833.8058 | 298833.8058 | 298833.8058 | 298833.8058 | 2.28 | 1.1427 | 3.1426 | 1 | 96 | 1.1427 | 1 | 2.28 | 1
periode 5 | 2011-07-31 18:00 | 2011-08-31 18:00 | 203219.4757 | 341468.1141 | 298833.8058 | 2011-12-12 17:00 | 138248.6385 | 168% | 42634.3083 | 114.3% | 73d | 174.5% | 100% | 2011-09-06 15:00 | 2011-09-06 15:00 | 2011-08-18 17:00 | 2011-09-09 11:00 | 2011-09-06 15:00 | 2011-09-06 10:00 | 2011-08-31 17:00 | 2011-08-31 17:00 | 2011-08-31 17:00 | 298833.8058 | 298833.8058 | 298833.8058 | 298833.8058 | 298833.8058 | 298833.8058 | 298833.8058 | 298833.8058 | 1.7449 | 1.1427 | 1.6803 | 1 | 73 | 1.1427 | 1 | 1.7449 | 1
periode 6 | 2011-08-31 18:00 | 2011-09-30 18:00 | 295360.0333 | 341468.1141 | 308343.7755 | 2011-12-12 17:00 | 46108.0809 | 115.6% | 33124.3386 | 110.7% | 51d | 142.5% | 100% | 2011-11-09 16:00 | 2011-11-09 16:00 | 2011-10-20 12:00 | 2011-11-16 10:00 | 2011-11-09 16:00 | 2011-11-07 10:00 | 2011-09-30 17:00 | 2011-09-30 17:00 | 2011-09-30 17:00 | 308343.7755 | 308343.7755 | 308343.7755 | 308343.7755 | 308343.7755 | 308343.7755 | 308343.7755 | 308343.7755 | 1.425 | 1.1074 | 1.1561 | 1 | 51 | 1.1074 | 1 | 1.425 | 1