## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building (1) | 1 |  |  | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 | 317.375
1 | Sondering | 1.1 |  | FS2 | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 0.375
2 | Inrichting | 1.2 | 1FS | FS5 | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 0.375
3 | Bouwput + Kelders | 1.3 | 5FS | FS4 | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 20.375
4 | Bouw rioleringen | 1.4 | 3FS | FS6;FS23 | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 20.375
5 | Afbraakwerken | 1.5 | 2FS | FS3 | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 13.375
6 | Ruwbouw | 1.6 | 4FS | FS7;FS10 | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 97.375
7 | Wachtgevel | 1.7 | 6FS | FS8;FS9 | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 | 20.375
8 | Dakisolatie | 1.8 | 7FS |  | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 | 13.375
9 | Dakbedekking & Zinkwerk | 1.9 | 7FS | FS11;FS12;FS13 | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 | 41.375
10 | Buitenschrijnwerk | 1.10 | 6FS | FS17;FS21 | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 | 27.375
11 | Sanitaire technieken | 1.11 | 9FS | FS21 | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 | 34.375
12 | Electriciteitstechnieken | 1.12 | 9FS | FS21 | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 | 34.375
13 | Ventilatietechnieken | 1.13 | 9FS | FS21 | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 | 13.375
14 | Trappen en Deuren | 1.14 | 16FS | FS24 | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 | 6.375
15 | Keukens | 1.15 | 16FS | FS24 | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 | 6.375
16 | Pleisterwerken | 1.16 | 22FS | FS14;FS15;FS18;FS19;FS20 | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 | 13.375
17 | Buitenpleisterwerk | 1.17 | 10FS |  | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 | 20.375
18 | Afwerking Ventilatie | 1.18 | 16FS | FS24 | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 | 6.375
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 1.19 | 16FS | FS24 | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 | 13.375
20 | Afwerking | 1.20 | 16FS | FS24 | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 | 13.375
21 | Chapewerken | 1.21 | 10FS;11FS;12FS;13FS | FS22 | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 | 13.375
22 | Vloeren | 1.22 | 21FS | FS16 | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 | 13.375
23 | Buitenaanleg | 1.23 | 4FS |  | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 6.375
24 | Schilderwerken | 1.24 | 14FS;15FS;18FS;19FS;20FS | FS25 | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 | 6.375
25 | Opkuis | 1.25 | 24FS |  | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building (1) | 1824h |  |  |  |  | 99 | 100 | 101
1 | Sondering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Inrichting | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Bouwput + Kelders | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Bouw rioleringen | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Afbraakwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Ruwbouw | 560h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Wachtgevel | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Dakisolatie | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Dakbedekking & Zinkwerk | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Buitenschrijnwerk | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Sanitaire technieken | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Electriciteitstechnieken | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Ventilatietechnieken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Trappen en Deuren | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Keukens | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Pleisterwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Buitenpleisterwerk | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Afwerking Ventilatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Afwerking | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Chapewerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Vloeren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Buitenaanleg | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Schilderwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Opkuis | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2011-11-08 17:00 |  | TP Name | 08/11, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 27d | [5 empty] | 34074.0501 |  | 4.941% |  | 26307.6501 | 37402.8505
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 10d | 20252.9604 | 18492.0007 | 15d | 0 | 0 | 20252.9604 | 18492.0007 | 40% | Started | 15321.7604 | 26416.9607 | 100 | 66.6667 | 40 | 100 | 76.6665 | 40
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 |  | 0 | 0 | 31847.8 | 15d | 0 | 0 | 0 | 31847.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 |  | 0 | 0 | 121519.0474 | 70d | 0 | 0 | 0 | 121519.0474 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 |  | 0 | 0 | 9790.35 | 15d | 0 | 0 | 0 | 9790.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 |  | 0 | 0 | 5545.19 | 10d | 0 | 0 | 0 | 5545.19 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 |  | 0 | 0 | 44145.9788 | 30d | 0 | 0 | 0 | 44145.9788 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 |  | 0 | 0 | 71547.1787 | 20d | 0 | 0 | 0 | 71547.1787 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 |  | 0 | 0 | 33402.4412 | 25d | 0 | 0 | 0 | 33402.4412 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 |  | 0 | 0 | 29082.4299 | 25d | 0 | 0 | 0 | 29082.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 |  | 0 | 0 | 6392 | 10d | 0 | 0 | 0 | 6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 |  | 0 | 0 | 9686.8402 | 5d | 0 | 0 | 0 | 9686.8402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 |  | 0 | 0 | 4666.7899 | 5d | 0 | 0 | 0 | 4666.7899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 |  | 0 | 0 | 16596.7402 | 10d | 0 | 0 | 0 | 16596.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 |  | 0 | 0 | 34664.7506 | 15d | 0 | 0 | 0 | 34664.7506 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 |  | 0 | 0 | 3196 | 5d | 0 | 0 | 0 | 3196 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 |  | 0 | 0 | 11133.7498 | 10d | 0 | 0 | 0 | 11133.7498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 |  | 0 | 0 | 9693.7399 | 10d | 0 | 0 | 0 | 9693.7399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 |  | 0 | 0 | 14216.05 | 10d | 0 | 0 | 0 | 14216.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 |  | 0 | 0 | 21777.2102 | 10d | 0 | 0 | 0 | 21777.2102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 |  | 0 | 0 | 6737.19 | 5d | 0 | 0 | 0 | 6737.19 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2011-12-06 17:00 |  | TP Name | 06/12, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 47d | [5 empty] | 69551.451 |  | 9.867% |  | 52530.4506 | 118518.8911
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 5d | 16985.4001 | 22293.5999 | 15d | 0 | 0 | 16985.4001 | 22293.5999 | 25% | Started | 15127.6002 | 31847.8 | 100 | 33.3333 | 25 | 100 | 53.333 | 25
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 |  | 0 | 0 | 121519.0474 | 70d | 0 | 0 | 0 | 121519.0474 | 0% | Not Started | 0 | 42531.0505 | 100 |  | 0 | 100 |  | 0
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 |  | 0 | 0 | 9790.35 | 15d | 0 | 0 | 0 | 9790.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 |  | 0 | 0 | 5545.19 | 10d | 0 | 0 | 0 | 5545.19 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 |  | 0 | 0 | 44145.9788 | 30d | 0 | 0 | 0 | 44145.9788 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 |  | 0 | 0 | 71547.1787 | 20d | 0 | 0 | 0 | 71547.1787 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 |  | 0 | 0 | 33402.4412 | 25d | 0 | 0 | 0 | 33402.4412 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 |  | 0 | 0 | 29082.4299 | 25d | 0 | 0 | 0 | 29082.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 |  | 0 | 0 | 6392 | 10d | 0 | 0 | 0 | 6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 |  | 0 | 0 | 9686.8402 | 5d | 0 | 0 | 0 | 9686.8402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 |  | 0 | 0 | 4666.7899 | 5d | 0 | 0 | 0 | 4666.7899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 |  | 0 | 0 | 16596.7402 | 10d | 0 | 0 | 0 | 16596.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 |  | 0 | 0 | 34664.7506 | 15d | 0 | 0 | 0 | 34664.7506 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 |  | 0 | 0 | 3196 | 5d | 0 | 0 | 0 | 3196 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 |  | 0 | 0 | 11133.7498 | 10d | 0 | 0 | 0 | 11133.7498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 |  | 0 | 0 | 9693.7399 | 10d | 0 | 0 | 0 | 9693.7399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 |  | 0 | 0 | 14216.05 | 10d | 0 | 0 | 0 | 14216.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 |  | 0 | 0 | 21777.2102 | 10d | 0 | 0 | 0 | 21777.2102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 |  | 0 | 0 | 6737.19 | 5d | 0 | 0 | 0 | 6737.19 | 0% | Not Started | 0 | 6737.19 | 100 |  | 0 | 100 |  | 0
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2012-01-10 17:00 |  | TP Name | 10/01, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 72d | [5 empty] | 151905.2912 |  | 22.89% |  | 121894.4465 | 148898.8898
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 100% | Finished | 31847.8 | 31847.8 | 100 | 133.3333 | 100 | 100 | 123.3335 | 100
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 10d | 48607.0503 | 97215.9961 | 80d | 0 | 0 | 48607.0503 | 97215.9961 | 11.11% | Started | 45906.606 | 72911.0493 | 100 | 14.2857 | 11.1111 | 100 | 39.9995 | 11.1111
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 |  | 0 | 0 | 9790.35 | 15d | 0 | 0 | 0 | 9790.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 |  | 0 | 0 | 5545.19 | 10d | 0 | 0 | 0 | 5545.19 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 |  | 0 | 0 | 44145.9788 | 30d | 0 | 0 | 0 | 44145.9788 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 |  | 0 | 0 | 71547.1787 | 20d | 0 | 0 | 0 | 71547.1787 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 |  | 0 | 0 | 33402.4412 | 25d | 0 | 0 | 0 | 33402.4412 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 |  | 0 | 0 | 29082.4299 | 25d | 0 | 0 | 0 | 29082.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 |  | 0 | 0 | 6392 | 10d | 0 | 0 | 0 | 6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 |  | 0 | 0 | 9686.8402 | 5d | 0 | 0 | 0 | 9686.8402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 |  | 0 | 0 | 4666.7899 | 5d | 0 | 0 | 0 | 4666.7899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 |  | 0 | 0 | 16596.7402 | 10d | 0 | 0 | 0 | 16596.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 |  | 0 | 0 | 34664.7506 | 15d | 0 | 0 | 0 | 34664.7506 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 |  | 0 | 0 | 3196 | 5d | 0 | 0 | 0 | 3196 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 |  | 0 | 0 | 11133.7498 | 10d | 0 | 0 | 0 | 11133.7498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 |  | 0 | 0 | 9693.7399 | 10d | 0 | 0 | 0 | 9693.7399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 |  | 0 | 0 | 14216.05 | 10d | 0 | 0 | 0 | 14216.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 |  | 0 | 0 | 21777.2102 | 10d | 0 | 0 | 0 | 21777.2102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 100% | Finished | 6737.19 | 6737.19 | 100 | 200 | 100 | 100 | 169.9995 | 100
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2012-02-14 17:00 |  | TP Name | 14/02, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 97d | [5 empty] | 182285.29 |  | 27.33% |  | 145523.335 | 179278.8886
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 100% | Finished | 31847.8 | 31847.8 | 100 | 133.3333 | 100 | 100 | 123.3335 | 100
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 35d | 78987.0491 | 66835.9973 | 55d | 0 | 0 | 78987.0491 | 66835.9973 | 38.89% | Started | 69535.4945 | 103291.0481 | 100 | 50 | 38.8889 | 100 | 64.9997 | 38.8889
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 |  | 0 | 0 | 9790.35 | 15d | 0 | 0 | 0 | 9790.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 |  | 0 | 0 | 5545.19 | 10d | 0 | 0 | 0 | 5545.19 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 |  | 0 | 0 | 44145.9788 | 30d | 0 | 0 | 0 | 44145.9788 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 |  | 0 | 0 | 71547.1787 | 20d | 0 | 0 | 0 | 71547.1787 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 |  | 0 | 0 | 33402.4412 | 25d | 0 | 0 | 0 | 33402.4412 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 |  | 0 | 0 | 29082.4299 | 25d | 0 | 0 | 0 | 29082.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 |  | 0 | 0 | 6392 | 10d | 0 | 0 | 0 | 6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 |  | 0 | 0 | 9686.8402 | 5d | 0 | 0 | 0 | 9686.8402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 |  | 0 | 0 | 4666.7899 | 5d | 0 | 0 | 0 | 4666.7899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 |  | 0 | 0 | 16596.7402 | 10d | 0 | 0 | 0 | 16596.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 |  | 0 | 0 | 34664.7506 | 15d | 0 | 0 | 0 | 34664.7506 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 |  | 0 | 0 | 3196 | 5d | 0 | 0 | 0 | 3196 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 |  | 0 | 0 | 11133.7498 | 10d | 0 | 0 | 0 | 11133.7498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 |  | 0 | 0 | 9693.7399 | 10d | 0 | 0 | 0 | 9693.7399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 |  | 0 | 0 | 14216.05 | 10d | 0 | 0 | 0 | 14216.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 |  | 0 | 0 | 21777.2102 | 10d | 0 | 0 | 0 | 21777.2102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 100% | Finished | 6737.19 | 6737.19 | 100 | 200 | 100 | 100 | 169.9995 | 100
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2012-03-06 17:00 |  | TP Name | 06/03, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 112d | [5 empty] | 200513.2892 |  | 30% |  | 159700.6694 | 197506.8879
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 100% | Finished | 31847.8 | 31847.8 | 100 | 133.3333 | 100 | 100 | 123.3335 | 100
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 50d | 97215.0483 | 48607.998 | 40d | 0 | 0 | 97215.0483 | 48607.998 | 55.56% | Started | 83712.8289 | 121519.0474 | 100 | 71.4286 | 55.5556 | 100 | 79.9998 | 55.5556
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 |  | 0 | 0 | 9790.35 | 15d | 0 | 0 | 0 | 9790.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 |  | 0 | 0 | 5545.19 | 10d | 0 | 0 | 0 | 5545.19 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 |  | 0 | 0 | 44145.9788 | 30d | 0 | 0 | 0 | 44145.9788 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 |  | 0 | 0 | 71547.1787 | 20d | 0 | 0 | 0 | 71547.1787 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 |  | 0 | 0 | 33402.4412 | 25d | 0 | 0 | 0 | 33402.4412 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 |  | 0 | 0 | 29082.4299 | 25d | 0 | 0 | 0 | 29082.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 |  | 0 | 0 | 6392 | 10d | 0 | 0 | 0 | 6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 |  | 0 | 0 | 9686.8402 | 5d | 0 | 0 | 0 | 9686.8402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 |  | 0 | 0 | 4666.7899 | 5d | 0 | 0 | 0 | 4666.7899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 |  | 0 | 0 | 16596.7402 | 10d | 0 | 0 | 0 | 16596.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 |  | 0 | 0 | 34664.7506 | 15d | 0 | 0 | 0 | 34664.7506 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 |  | 0 | 0 | 3196 | 5d | 0 | 0 | 0 | 3196 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 |  | 0 | 0 | 11133.7498 | 10d | 0 | 0 | 0 | 11133.7498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 |  | 0 | 0 | 9693.7399 | 10d | 0 | 0 | 0 | 9693.7399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 |  | 0 | 0 | 14216.05 | 10d | 0 | 0 | 0 | 14216.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 |  | 0 | 0 | 21777.2102 | 10d | 0 | 0 | 0 | 21777.2102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 100% | Finished | 6737.19 | 6737.19 | 100 | 200 | 100 | 100 | 169.9995 | 100
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2012-04-10 17:00 |  | TP Name | 10/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 137d | [5 empty] | 230893.288 |  | 34.43% |  | 183329.5534 | 326421.9363
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 100% | Finished | 31847.8 | 31847.8 | 100 | 133.3333 | 100 | 100 | 123.3335 | 100
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 75d | 127595.0471 | 18227.9993 | 15d | 0 | 0 | 127595.0471 | 18227.9993 | 83.33% | Started | 107341.7129 | 121519.0474 | 100 | 107.1429 | 83.3333 | 100 | 105 | 83.3333
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 |  | 0 | 0 | 9790.35 | 15d | 0 | 0 | 0 | 9790.35 | 0% | Not Started | 0 | 9790.35 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 |  | 0 | 0 | 5545.19 | 10d | 0 | 0 | 0 | 5545.19 | 0% | Not Started | 0 | 5545.19 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 |  | 0 | 0 | 44145.9788 | 30d | 0 | 0 | 0 | 44145.9788 | 0% | Not Started | 0 | 23544.3796 | 100 |  | 0 | 100 |  | 0
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 |  | 0 | 0 | 71547.1787 | 20d | 0 | 0 | 0 | 71547.1787 | 0% | Not Started | 0 | 71547.1787 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 |  | 0 | 0 | 33402.4412 | 25d | 0 | 0 | 0 | 33402.4412 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 |  | 0 | 0 | 29082.4299 | 25d | 0 | 0 | 0 | 29082.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 |  | 0 | 0 | 6392 | 10d | 0 | 0 | 0 | 6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 |  | 0 | 0 | 9686.8402 | 5d | 0 | 0 | 0 | 9686.8402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 |  | 0 | 0 | 4666.7899 | 5d | 0 | 0 | 0 | 4666.7899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 |  | 0 | 0 | 16596.7402 | 10d | 0 | 0 | 0 | 16596.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 |  | 0 | 0 | 34664.7506 | 15d | 0 | 0 | 0 | 34664.7506 | 0% | Not Started | 0 | 18487.9501 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 |  | 0 | 0 | 3196 | 5d | 0 | 0 | 0 | 3196 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 |  | 0 | 0 | 11133.7498 | 10d | 0 | 0 | 0 | 11133.7498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 |  | 0 | 0 | 9693.7399 | 10d | 0 | 0 | 0 | 9693.7399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 |  | 0 | 0 | 14216.05 | 10d | 0 | 0 | 0 | 14216.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 |  | 0 | 0 | 21777.2102 | 10d | 0 | 0 | 0 | 21777.2102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 100% | Finished | 6737.19 | 6737.19 | 100 | 200 | 100 | 100 | 169.9995 | 100
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2012-05-01 17:00 |  | TP Name | 01/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 152d | [5 empty] | 249121.2873 |  | 37.1% |  | 197506.8879 | 358049.9362
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 100% | Finished | 31847.8 | 31847.8 | 100 | 133.3333 | 100 | 100 | 123.3335 | 100
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 90d | 145823.0464 | 0 | 0 | 0 | 0 | 145823.0464 | 0 | 100% | Finished | 121519.0474 | 121519.0474 | 100 | 128.5714 | 100 | 100 | 120.0002 | 100
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 |  | 0 | 0 | 9790.35 | 15d | 0 | 0 | 0 | 9790.35 | 0% | Not Started | 0 | 9790.35 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 |  | 0 | 0 | 5545.19 | 10d | 0 | 0 | 0 | 5545.19 | 0% | Not Started | 0 | 5545.19 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 |  | 0 | 0 | 44145.9788 | 30d | 0 | 0 | 0 | 44145.9788 | 0% | Not Started | 0 | 38995.579 | 100 |  | 0 | 100 |  | 0
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 |  | 0 | 0 | 71547.1787 | 20d | 0 | 0 | 0 | 71547.1787 | 0% | Not Started | 0 | 71547.1787 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 |  | 0 | 0 | 33402.4412 | 25d | 0 | 0 | 0 | 33402.4412 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 |  | 0 | 0 | 29082.4299 | 25d | 0 | 0 | 0 | 29082.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 |  | 0 | 0 | 6392 | 10d | 0 | 0 | 0 | 6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 |  | 0 | 0 | 9686.8402 | 5d | 0 | 0 | 0 | 9686.8402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 |  | 0 | 0 | 4666.7899 | 5d | 0 | 0 | 0 | 4666.7899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 |  | 0 | 0 | 16596.7402 | 10d | 0 | 0 | 0 | 16596.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 |  | 0 | 0 | 34664.7506 | 15d | 0 | 0 | 0 | 34664.7506 | 0% | Not Started | 0 | 34664.7506 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 |  | 0 | 0 | 3196 | 5d | 0 | 0 | 0 | 3196 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 |  | 0 | 0 | 11133.7498 | 10d | 0 | 0 | 0 | 11133.7498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 |  | 0 | 0 | 9693.7399 | 10d | 0 | 0 | 0 | 9693.7399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 |  | 0 | 0 | 14216.05 | 10d | 0 | 0 | 0 | 14216.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 |  | 0 | 0 | 21777.2102 | 10d | 0 | 0 | 0 | 21777.2102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 100% | Finished | 6737.19 | 6737.19 | 100 | 200 | 100 | 100 | 169.9995 | 100
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2012-06-12 17:00 |  | TP Name | 12/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 182d | [5 empty] | 391275.1357 |  | 64.38% |  | 342750.9774 | 432077.207
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 100% | Finished | 31847.8 | 31847.8 | 100 | 133.3333 | 100 | 100 | 123.3335 | 100
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 90d | 145823.0464 | 0 | 0 | 0 | 0 | 145823.0464 | 0 | 100% | Finished | 121519.0474 | 121519.0474 | 100 | 128.5714 | 100 | 100 | 120.0002 | 100
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 | 2012-05-02 08:00 | 15d | 9790.35 | 0 | 0 | 0 | 0 | 9790.35 | 0 | 100% | Finished | 9790.35 | 9790.35 | 100 | 100 | 100 | 100 | 100 | 100
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 | 2012-05-23 08:00 | 10d | 5545.19 | 0 | 0 | 0 | 0 | 5545.19 | 0 | 100% | Finished | 5545.19 | 5545.19 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 | 2012-05-23 08:00 | 15d | 28694.7794 | 10300.7996 | 10d | 0 | 0 | 28694.7794 | 10300.7996 | 60% | Started | 31785.02 | 44145.9788 | 100 | 50 | 60 | 100 | 64.9998 | 60
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 | 2012-05-02 08:00 | 20d | 71547.1787 | 0 | 0 | 0 | 0 | 71547.1787 | 0 | 100% | Finished | 71547.1787 | 71547.1787 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 |  | 0 | 0 | 33402.4412 | 25d | 0 | 0 | 0 | 33402.4412 | 0% | Not Started | 0 | 33402.4412 | 100 |  | 0 | 100 |  | 0
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 |  | 0 | 0 | 29082.4299 | 25d | 0 | 0 | 0 | 29082.4299 | 0% | Not Started | 0 | 29082.4299 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 |  | 0 | 0 | 6392 | 10d | 0 | 0 | 0 | 6392 | 0% | Not Started | 0 | 6392 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 |  | 0 | 0 | 9686.8402 | 5d | 0 | 0 | 0 | 9686.8402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 |  | 0 | 0 | 4666.7899 | 5d | 0 | 0 | 0 | 4666.7899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 |  | 0 | 0 | 16596.7402 | 10d | 0 | 0 | 0 | 16596.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 | 2012-05-30 08:00 | 10d | 26576.3503 | 8088.4003 | 5d | 0 | 0 | 26576.3503 | 8088.4003 | 66.67% | Started | 26576.3508 | 34664.7506 | 100 | 66.6667 | 66.6667 | 100 | 76.6668 | 66.6667
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 |  | 0 | 0 | 3196 | 5d | 0 | 0 | 0 | 3196 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 |  | 0 | 0 | 11133.7498 | 10d | 0 | 0 | 0 | 11133.7498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 |  | 0 | 0 | 9693.7399 | 10d | 0 | 0 | 0 | 9693.7399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 |  | 0 | 0 | 14216.05 | 10d | 0 | 0 | 0 | 14216.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 |  | 0 | 0 | 21777.2102 | 10d | 0 | 0 | 0 | 21777.2102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 100% | Finished | 6737.19 | 6737.19 | 100 | 200 | 100 | 100 | 169.9995 | 100
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2012-07-10 17:00 |  | TP Name | 10/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 202d | [5 empty] | 452297.2061 |  | 76.04% |  | 404818.74 | 468070.4672
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 100% | Finished | 31847.8 | 31847.8 | 100 | 133.3333 | 100 | 100 | 123.3335 | 100
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 90d | 145823.0464 | 0 | 0 | 0 | 0 | 145823.0464 | 0 | 100% | Finished | 121519.0474 | 121519.0474 | 100 | 128.5714 | 100 | 100 | 120.0002 | 100
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 | 2012-05-02 08:00 | 15d | 9790.35 | 0 | 0 | 0 | 0 | 9790.35 | 0 | 100% | Finished | 9790.35 | 9790.35 | 100 | 100 | 100 | 100 | 100 | 100
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 | 2012-05-23 08:00 | 10d | 5545.19 | 0 | 0 | 0 | 0 | 5545.19 | 0 | 100% | Finished | 5545.19 | 5545.19 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 | 2012-05-23 08:00 | 25d | 38995.579 | 0 | 0 | 0 | 0 | 38995.579 | 0 | 100% | Finished | 44145.9788 | 44145.9788 | 100 | 83.3333 | 100 | 100 | 88.3333 | 100
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 | 2012-05-02 08:00 | 20d | 71547.1787 | 0 | 0 | 0 | 0 | 71547.1787 | 0 | 100% | Finished | 71547.1787 | 71547.1787 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 | 2012-06-27 08:00 | 10d | 19373.2407 | 18705.6006 | 20d | 0 | 0 | 19373.2407 | 18705.6006 | 33.33% | Started | 17814.4409 | 33402.4412 | 100 | 40 | 33.3333 | 100 | 57.9995 | 33.3333
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 | 2012-06-27 08:00 | 10d | 16867.6298 | 8143.2001 | 10d | 0 | 0 | 16867.6298 | 8143.2001 | 50% | Started | 18903.4298 | 29082.4299 | 100 | 40 | 50 | 100 | 57.9994 | 50
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 | 2012-06-27 08:00 | 10d | 6392 | 2237.2 | 5d | 0 | 0 | 6392 | 2237.2 | 66.67% | Started | 4900.5334 | 6392 | 100 | 100 | 66.6667 | 100 | 100 | 66.6667
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 |  | 0 | 0 | 9686.8402 | 5d | 0 | 0 | 0 | 9686.8402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 |  | 0 | 0 | 4666.7899 | 5d | 0 | 0 | 0 | 4666.7899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 |  | 0 | 0 | 16596.7402 | 10d | 0 | 0 | 0 | 16596.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 | 2012-05-30 08:00 | 15d | 34664.7506 | 0 | 0 | 0 | 0 | 34664.7506 | 0 | 100% | Finished | 34664.7506 | 34664.7506 | 100 | 100 | 100 | 100 | 100 | 100
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 |  | 0 | 0 | 3196 | 5d | 0 | 0 | 0 | 3196 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 |  | 0 | 0 | 11133.7498 | 10d | 0 | 0 | 0 | 11133.7498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 |  | 0 | 0 | 9693.7399 | 10d | 0 | 0 | 0 | 9693.7399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 |  | 0 | 0 | 14216.05 | 10d | 0 | 0 | 0 | 14216.05 | 0% | Not Started | 0 | 14216.05 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 |  | 0 | 0 | 21777.2102 | 10d | 0 | 0 | 0 | 21777.2102 | 0% | Not Started | 0 | 21777.2102 | 100 |  | 0 | 100 |  | 0
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 100% | Finished | 6737.19 | 6737.19 | 100 | 200 | 100 | 100 | 169.9995 | 100
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2012-08-07 17:00 |  | TP Name | 07/08, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 222d | [5 empty] | 481383.2067 |  | 81.15% |  | 432077.207 | 523044.3272
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 100% | Finished | 31847.8 | 31847.8 | 100 | 133.3333 | 100 | 100 | 123.3335 | 100
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 90d | 145823.0464 | 0 | 0 | 0 | 0 | 145823.0464 | 0 | 100% | Finished | 121519.0474 | 121519.0474 | 100 | 128.5714 | 100 | 100 | 120.0002 | 100
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 | 2012-05-02 08:00 | 15d | 9790.35 | 0 | 0 | 0 | 0 | 9790.35 | 0 | 100% | Finished | 9790.35 | 9790.35 | 100 | 100 | 100 | 100 | 100 | 100
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 | 2012-05-23 08:00 | 10d | 5545.19 | 0 | 0 | 0 | 0 | 5545.19 | 0 | 100% | Finished | 5545.19 | 5545.19 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 | 2012-05-23 08:00 | 25d | 38995.579 | 0 | 0 | 0 | 0 | 38995.579 | 0 | 100% | Finished | 44145.9788 | 44145.9788 | 100 | 83.3333 | 100 | 100 | 88.3333 | 100
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 | 2012-05-02 08:00 | 20d | 71547.1787 | 0 | 0 | 0 | 0 | 71547.1787 | 0 | 100% | Finished | 71547.1787 | 71547.1787 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 | 2012-06-27 08:00 | 30d | 38078.8413 | 0 | 0 | 0 | 0 | 38078.8413 | 0 | 100% | Finished | 33402.4412 | 33402.4412 | 100 | 120 | 100 | 100 | 114.0002 | 100
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 | 2012-06-27 08:00 | 20d | 25010.8298 | 0 | 0 | 0 | 0 | 25010.8298 | 0 | 100% | Finished | 29082.4299 | 29082.4299 | 100 | 80 | 100 | 100 | 85.9998 | 100
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 | 2012-06-27 08:00 | 15d | 8629.2 | 0 | 0 | 0 | 0 | 8629.2 | 0 | 100% | Finished | 6392 | 6392 | 100 | 150 | 100 | 100 | 135 | 100
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 |  | 0 | 0 | 9686.8402 | 5d | 0 | 0 | 0 | 9686.8402 | 0% | Not Started | 0 | 9686.8402 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 |  | 0 | 0 | 4666.7899 | 5d | 0 | 0 | 0 | 4666.7899 | 0% | Not Started | 0 | 4666.7899 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 |  | 0 | 0 | 16596.7402 | 10d | 0 | 0 | 0 | 16596.7402 | 0% | Not Started | 0 | 16596.7402 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 | 2012-05-30 08:00 | 15d | 34664.7506 | 0 | 0 | 0 | 0 | 34664.7506 | 0 | 100% | Finished | 34664.7506 | 34664.7506 | 100 | 100 | 100 | 100 | 100 | 100
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 |  | 0 | 0 | 3196 | 5d | 0 | 0 | 0 | 3196 | 0% | Not Started | 0 | 3196 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 |  | 0 | 0 | 11133.7498 | 10d | 0 | 0 | 0 | 11133.7498 | 0% | Not Started | 0 | 11133.7498 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 |  | 0 | 0 | 9693.7399 | 10d | 0 | 0 | 0 | 9693.7399 | 0% | Not Started | 0 | 9693.7399 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 |  | 0 | 0 | 14216.05 | 10d | 0 | 0 | 0 | 14216.05 | 0% | Not Started | 0 | 14216.05 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 |  | 0 | 0 | 21777.2102 | 10d | 0 | 0 | 0 | 21777.2102 | 0% | Not Started | 0 | 21777.2102 | 100 |  | 0 | 100 |  | 0
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 100% | Finished | 6737.19 | 6737.19 | 100 | 200 | 100 | 100 | 169.9995 | 100
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2012-09-04 17:00 |  | TP Name | 04/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 242d | [5 empty] | 517376.467 |  | 87.92% |  | 468070.4672 | 532410.2874
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 100% | Finished | 31847.8 | 31847.8 | 100 | 133.3333 | 100 | 100 | 123.3335 | 100
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 90d | 145823.0464 | 0 | 0 | 0 | 0 | 145823.0464 | 0 | 100% | Finished | 121519.0474 | 121519.0474 | 100 | 128.5714 | 100 | 100 | 120.0002 | 100
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 | 2012-05-02 08:00 | 15d | 9790.35 | 0 | 0 | 0 | 0 | 9790.35 | 0 | 100% | Finished | 9790.35 | 9790.35 | 100 | 100 | 100 | 100 | 100 | 100
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 | 2012-05-23 08:00 | 10d | 5545.19 | 0 | 0 | 0 | 0 | 5545.19 | 0 | 100% | Finished | 5545.19 | 5545.19 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 | 2012-05-23 08:00 | 25d | 38995.579 | 0 | 0 | 0 | 0 | 38995.579 | 0 | 100% | Finished | 44145.9788 | 44145.9788 | 100 | 83.3333 | 100 | 100 | 88.3333 | 100
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 | 2012-05-02 08:00 | 20d | 71547.1787 | 0 | 0 | 0 | 0 | 71547.1787 | 0 | 100% | Finished | 71547.1787 | 71547.1787 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 | 2012-06-27 08:00 | 30d | 38078.8413 | 0 | 0 | 0 | 0 | 38078.8413 | 0 | 100% | Finished | 33402.4412 | 33402.4412 | 100 | 120 | 100 | 100 | 114.0002 | 100
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 | 2012-06-27 08:00 | 20d | 25010.8298 | 0 | 0 | 0 | 0 | 25010.8298 | 0 | 100% | Finished | 29082.4299 | 29082.4299 | 100 | 80 | 100 | 100 | 85.9998 | 100
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 | 2012-06-27 08:00 | 15d | 8629.2 | 0 | 0 | 0 | 0 | 8629.2 | 0 | 100% | Finished | 6392 | 6392 | 100 | 150 | 100 | 100 | 135 | 100
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 |  | 0 | 0 | 9686.8402 | 5d | 0 | 0 | 0 | 9686.8402 | 0% | Not Started | 0 | 9686.8402 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 |  | 0 | 0 | 4666.7899 | 5d | 0 | 0 | 0 | 4666.7899 | 0% | Not Started | 0 | 4666.7899 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 |  | 0 | 0 | 16596.7402 | 10d | 0 | 0 | 0 | 16596.7402 | 0% | Not Started | 0 | 16596.7402 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 | 2012-05-30 08:00 | 15d | 34664.7506 | 0 | 0 | 0 | 0 | 34664.7506 | 0 | 100% | Finished | 34664.7506 | 34664.7506 | 100 | 100 | 100 | 100 | 100 | 100
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 |  | 0 | 0 | 3196 | 5d | 0 | 0 | 0 | 3196 | 0% | Not Started | 0 | 3196 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 |  | 0 | 0 | 11133.7498 | 10d | 0 | 0 | 0 | 11133.7498 | 0% | Not Started | 0 | 11133.7498 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 |  | 0 | 0 | 9693.7399 | 10d | 0 | 0 | 0 | 9693.7399 | 0% | Not Started | 0 | 9693.7399 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 | 2012-08-08 08:00 | 10d | 14216.05 | 0 | 0 | 0 | 0 | 14216.05 | 0 | 100% | Finished | 14216.05 | 14216.05 | 100 | 100 | 100 | 100 | 100 | 100
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 | 2012-08-22 08:00 | 10d | 21777.2102 | 0 | 0 | 0 | 0 | 21777.2102 | 0 | 100% | Finished | 21777.2102 | 21777.2102 | 100 | 100 | 100 | 100 | 100 | 100
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 100% | Finished | 6737.19 | 6737.19 | 100 | 200 | 100 | 100 | 169.9995 | 100
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 9072.5201 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 293.44 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2012-10-02 17:00 |  | TP Name | 02/10, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 262d | [5 empty] | 577854.3269 |  | 97.75% |  | 520446.4607 | 532410.2874
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 100% | Finished | 31847.8 | 31847.8 | 100 | 133.3333 | 100 | 100 | 123.3335 | 100
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 90d | 145823.0464 | 0 | 0 | 0 | 0 | 145823.0464 | 0 | 100% | Finished | 121519.0474 | 121519.0474 | 100 | 128.5714 | 100 | 100 | 120.0002 | 100
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 | 2012-05-02 08:00 | 15d | 9790.35 | 0 | 0 | 0 | 0 | 9790.35 | 0 | 100% | Finished | 9790.35 | 9790.35 | 100 | 100 | 100 | 100 | 100 | 100
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 | 2012-05-23 08:00 | 10d | 5545.19 | 0 | 0 | 0 | 0 | 5545.19 | 0 | 100% | Finished | 5545.19 | 5545.19 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 | 2012-05-23 08:00 | 25d | 38995.579 | 0 | 0 | 0 | 0 | 38995.579 | 0 | 100% | Finished | 44145.9788 | 44145.9788 | 100 | 83.3333 | 100 | 100 | 88.3333 | 100
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 | 2012-05-02 08:00 | 20d | 71547.1787 | 0 | 0 | 0 | 0 | 71547.1787 | 0 | 100% | Finished | 71547.1787 | 71547.1787 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 | 2012-06-27 08:00 | 30d | 38078.8413 | 0 | 0 | 0 | 0 | 38078.8413 | 0 | 100% | Finished | 33402.4412 | 33402.4412 | 100 | 120 | 100 | 100 | 114.0002 | 100
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 | 2012-06-27 08:00 | 20d | 25010.8298 | 0 | 0 | 0 | 0 | 25010.8298 | 0 | 100% | Finished | 29082.4299 | 29082.4299 | 100 | 80 | 100 | 100 | 85.9998 | 100
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 | 2012-06-27 08:00 | 15d | 8629.2 | 0 | 0 | 0 | 0 | 8629.2 | 0 | 100% | Finished | 6392 | 6392 | 100 | 150 | 100 | 100 | 135 | 100
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 | 2012-09-19 08:00 | 5d | 9686.8402 | 0 | 0 | 0 | 0 | 9686.8402 | 0 | 100% | Finished | 9686.8402 | 9686.8402 | 100 | 100 | 100 | 100 | 100 | 100
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 | 2012-09-19 08:00 | 10d | 7933.5898 | 0 | 0 | 0 | 0 | 7933.5898 | 0 | 100% | Finished | 4666.7899 | 4666.7899 | 100 | 200 | 100 | 100 | 170.001 | 100
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 | 2012-09-05 08:00 | 10d | 16596.7402 | 0 | 0 | 0 | 0 | 16596.7402 | 0 | 100% | Finished | 16596.7402 | 16596.7402 | 100 | 100 | 100 | 100 | 100 | 100
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 | 2012-05-30 08:00 | 15d | 34664.7506 | 0 | 0 | 0 | 0 | 34664.7506 | 0 | 100% | Finished | 34664.7506 | 34664.7506 | 100 | 100 | 100 | 100 | 100 | 100
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 | 2012-09-19 08:00 | 10d | 5433.2 | 0 | 0 | 0 | 0 | 5433.2 | 0 | 100% | Finished | 3196 | 3196 | 100 | 200 | 100 | 100 | 170 | 100
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 | 2012-09-19 08:00 | 10d | 11133.7498 | 3896.7999 | 5d | 0 | 0 | 11133.7498 | 3896.7999 | 66.67% | Started | 8535.8833 | 11133.7498 | 100 | 100 | 66.6667 | 100 | 100 | 66.6667
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 | 2012-09-19 08:00 | 10d | 9693.7399 | 0 | 0 | 0 | 0 | 9693.7399 | 0 | 100% | Finished | 9693.7399 | 9693.7399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 | 2012-08-08 08:00 | 10d | 14216.05 | 0 | 0 | 0 | 0 | 14216.05 | 0 | 100% | Finished | 14216.05 | 14216.05 | 100 | 100 | 100 | 100 | 100 | 100
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 | 2012-08-22 08:00 | 10d | 21777.2102 | 0 | 0 | 0 | 0 | 21777.2102 | 0 | 100% | Finished | 21777.2102 | 21777.2102 | 100 | 100 | 100 | 100 | 100 | 100
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 100% | Finished | 6737.19 | 6737.19 | 100 | 200 | 100 | 100 | 169.9995 | 100
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 |  | 0 | 0 | 9072.5201 | 5d | 0 | 0 | 0 | 9072.5201 | 0% | Not Started | 0 | 9072.5201 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 |  | 0 | 0 | 293.44 | 1d | 0 | 0 | 0 | 293.44 | 0% | Not Started | 0 | 293.44 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2012-10-18 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (1) | 2011-10-03 08:00 | 2012-08-15 17:00 | 228d |  |  | 160067.4112 |  |  | 532410.2874 |  | 274d | [5 empty] | 591410.527 |  | 100% |  | 532410.2874 | 532410.2874
1 | Sondering | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d |  | 0 | 620 | 0 | 0 | 620 | 2011-10-03 08:00 | 1d | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 100% | Finished | 620 | 620 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2011-10-04 08:00 | 2011-10-04 17:00 | 1d |  | 0 | 679.65 | 198.23 | 1585.84 | 2265.49 | 2011-10-04 08:00 | 1d | 2265.49 | 0 | 0 | 0 | 0 | 2265.49 | 0 | 100% | Finished | 2265.49 | 2265.49 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2011-10-19 08:00 | 2011-11-08 17:00 | 15d |  | 0 | 7924.96 | 154.1 | 18492.0007 | 26416.9607 | 2011-10-26 08:00 | 25d | 38744.9612 | 0 | 0 | 0 | 0 | 38744.9612 | 0 | 100% | Finished | 26416.9607 | 26416.9607 | 100 | 166.6667 | 100 | 100 | 146.667 | 100
4 | Bouw rioleringen | 2011-11-09 08:00 | 2011-11-29 17:00 | 15d |  | 0 | 9554.2002 | 185.78 | 22293.5999 | 31847.8 | 2011-11-30 08:00 | 20d | 39279 | 0 | 0 | 0 | 0 | 39279 | 0 | 100% | Finished | 31847.8 | 31847.8 | 100 | 133.3333 | 100 | 100 | 123.3335 | 100
5 | Afbraakwerken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 2430 | 70.88 | 5670.3998 | 8100.3998 | 2011-10-05 08:00 | 15d | 10935.5997 | 0 | 0 | 0 | 0 | 10935.5997 | 0 | 100% | Finished | 8100.3998 | 8100.3998 | 100 | 150 | 100 | 100 | 135.0007 | 100
6 | Ruwbouw | 2011-11-30 08:00 | 2012-03-06 17:00 | 70d |  | 0 | 36455.0508 | 151.9 | 85063.9966 | 121519.0474 | 2011-12-28 08:00 | 90d | 145823.0464 | 0 | 0 | 0 | 0 | 145823.0464 | 0 | 100% | Finished | 121519.0474 | 121519.0474 | 100 | 128.5714 | 100 | 100 | 120.0002 | 100
7 | Wachtgevel | 2012-03-07 08:00 | 2012-03-27 17:00 | 15d |  | 0 | 2937.1499 | 57.11 | 6853.2001 | 9790.35 | 2012-05-02 08:00 | 15d | 9790.35 | 0 | 0 | 0 | 0 | 9790.35 | 0 | 100% | Finished | 9790.35 | 9790.35 | 100 | 100 | 100 | 100 | 100 | 100
8 | Dakisolatie | 2012-03-28 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 1663.59 | 48.52 | 3881.6 | 5545.19 | 2012-05-23 08:00 | 10d | 5545.19 | 0 | 0 | 0 | 0 | 5545.19 | 0 | 100% | Finished | 5545.19 | 5545.19 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2012-03-28 08:00 | 2012-05-08 17:00 | 30d |  | 0 | 13243.5801 | 128.76 | 30902.3987 | 44145.9788 | 2012-05-23 08:00 | 25d | 38995.579 | 0 | 0 | 0 | 0 | 38995.579 | 0 | 100% | Finished | 44145.9788 | 44145.9788 | 100 | 83.3333 | 100 | 100 | 88.3333 | 100
10 | Buitenschrijnwerk | 2012-03-07 08:00 | 2012-04-03 17:00 | 20d |  | 0 | 21463.9805 | 313.02 | 50083.1982 | 71547.1787 | 2012-05-02 08:00 | 20d | 71547.1787 | 0 | 0 | 0 | 0 | 71547.1787 | 0 | 100% | Finished | 71547.1787 | 71547.1787 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitaire technieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 10020.4404 | 116.91 | 23382.0007 | 33402.4412 | 2012-06-27 08:00 | 30d | 38078.8413 | 0 | 0 | 0 | 0 | 38078.8413 | 0 | 100% | Finished | 33402.4412 | 33402.4412 | 100 | 120 | 100 | 100 | 114.0002 | 100
12 | Electriciteitstechnieken | 2012-05-09 08:00 | 2012-06-12 17:00 | 25d |  | 0 | 8724.4297 | 101.79 | 20358.0002 | 29082.4299 | 2012-06-27 08:00 | 20d | 25010.8298 | 0 | 0 | 0 | 0 | 25010.8298 | 0 | 100% | Finished | 29082.4299 | 29082.4299 | 100 | 80 | 100 | 100 | 85.9998 | 100
13 | Ventilatietechnieken | 2012-05-09 08:00 | 2012-05-22 17:00 | 10d |  | 0 | 1917.6 | 55.93 | 4474.4 | 6392 | 2012-06-27 08:00 | 15d | 8629.2 | 0 | 0 | 0 | 0 | 8629.2 | 0 | 100% | Finished | 6392 | 6392 | 100 | 150 | 100 | 100 | 135 | 100
14 | Trappen en Deuren | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 2906.04 | 169.52 | 6780.8002 | 9686.8402 | 2012-09-19 08:00 | 5d | 9686.8402 | 0 | 0 | 0 | 0 | 9686.8402 | 0 | 100% | Finished | 9686.8402 | 9686.8402 | 100 | 100 | 100 | 100 | 100 | 100
15 | Keukens | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 1399.99 | 81.67 | 3266.7999 | 4666.7899 | 2012-09-19 08:00 | 10d | 7933.5898 | 0 | 0 | 0 | 0 | 7933.5898 | 0 | 100% | Finished | 4666.7899 | 4666.7899 | 100 | 200 | 100 | 100 | 170.001 | 100
16 | Pleisterwerken | 2012-07-11 08:00 | 2012-07-24 17:00 | 10d |  | 0 | 4979.1401 | 145.22 | 11617.6001 | 16596.7402 | 2012-09-05 08:00 | 10d | 16596.7402 | 0 | 0 | 0 | 0 | 16596.7402 | 0 | 100% | Finished | 16596.7402 | 16596.7402 | 100 | 100 | 100 | 100 | 100 | 100
17 | Buitenpleisterwerk | 2012-04-04 08:00 | 2012-04-24 17:00 | 15d |  | 0 | 10399.5498 | 202.21 | 24265.2008 | 34664.7506 | 2012-05-30 08:00 | 15d | 34664.7506 | 0 | 0 | 0 | 0 | 34664.7506 | 0 | 100% | Finished | 34664.7506 | 34664.7506 | 100 | 100 | 100 | 100 | 100 | 100
18 | Afwerking Ventilatie | 2012-07-25 08:00 | 2012-07-31 17:00 | 5d |  | 0 | 958.8 | 55.93 | 2237.2 | 3196 | 2012-09-19 08:00 | 10d | 5433.2 | 0 | 0 | 0 | 0 | 5433.2 | 0 | 100% | Finished | 3196 | 3196 | 100 | 200 | 100 | 100 | 170 | 100
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 3340.1499 | 97.42 | 7793.5999 | 11133.7498 | 2012-09-19 08:00 | 15d | 15030.5497 | 0 | 0 | 0 | 0 | 15030.5497 | 0 | 100% | Finished | 11133.7498 | 11133.7498 | 100 | 150 | 100 | 100 | 134.9999 | 100
20 | Afwerking | 2012-07-25 08:00 | 2012-08-07 17:00 | 10d |  | 0 | 2908.1399 | 84.82 | 6785.6 | 9693.7399 | 2012-09-19 08:00 | 10d | 9693.7399 | 0 | 0 | 0 | 0 | 9693.7399 | 0 | 100% | Finished | 9693.7399 | 9693.7399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Chapewerken | 2012-06-13 08:00 | 2012-06-26 17:00 | 10d |  | 0 | 4264.8501 | 124.39 | 9951.2 | 14216.05 | 2012-08-08 08:00 | 10d | 14216.05 | 0 | 0 | 0 | 0 | 14216.05 | 0 | 100% | Finished | 14216.05 | 14216.05 | 100 | 100 | 100 | 100 | 100 | 100
22 | Vloeren | 2012-06-27 08:00 | 2012-07-10 17:00 | 10d |  | 0 | 6533.21 | 190.55 | 15244.0002 | 21777.2102 | 2012-08-22 08:00 | 10d | 21777.2102 | 0 | 0 | 0 | 0 | 21777.2102 | 0 | 100% | Finished | 21777.2102 | 21777.2102 | 100 | 100 | 100 | 100 | 100 | 100
23 | Buitenaanleg | 2011-11-30 08:00 | 2011-12-06 17:00 | 5d |  | 0 | 2021.1899 | 117.9 | 4716.0001 | 6737.19 | 2011-12-28 08:00 | 10d | 11453.1901 | 0 | 0 | 0 | 0 | 11453.1901 | 0 | 100% | Finished | 6737.19 | 6737.19 | 100 | 200 | 100 | 100 | 169.9995 | 100
24 | Schilderwerken | 2012-08-08 08:00 | 2012-08-14 17:00 | 5d |  | 0 | 2721.72 | 158.77 | 6350.8002 | 9072.5201 | 2012-10-10 08:00 | 5d | 9072.5201 | 0 | 0 | 0 | 0 | 9072.5201 | 0 | 100% | Finished | 9072.5201 | 9072.5201 | 100 | 100 | 100 | 100 | 100 | 100
25 | Opkuis | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 36.68 | 293.44 | 293.44 | 2012-10-17 08:00 | 2d | 586.88 | 0 | 0 | 0 | 0 | 586.88 | 0 | 100% | Finished | 293.44 | 293.44 | 100 | 200 | 100 | 100 | 200 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
08/11, 2011 | 2011-10-03 08:00 | 2011-11-08 17:00 | 37402.8505 | 26307.6501 | 34074.0501 | 2011-10-26 17:00 | -11095.2003 | 70.34% | -7766.4 | 77.21% | -9d | 66.67% | 100% | 2012-08-22 15:00 | 2012-12-28 09:00 | 2013-05-10 16:00 | 2012-08-27 17:00 | 2012-12-28 09:00 | 2013-04-30 16:00 | 2012-08-28 17:00 | 2013-01-22 17:00 | 2013-05-31 17:00 | 540176.6873 | 689585.5281 | 753624.4912 | 793228.0059 | 966046.2203 | 1017341.267 | 701464.8948 | 707986.5279 | 0.66667 | 0.77207 | 0.70336 | 1 | -9 | 0.77207 | 1 | 0.66667 | 1
06/12, 2011 | 2011-11-08 17:00 | 2011-12-06 17:00 | 118518.8911 | 52530.4506 | 69551.451 | 2011-11-14 15:00 | -65988.4404 | 44.32% | -17021.0004 | 75.53% | -16d 2h | 65.43% | 100% | 2012-09-25 10:00 | 2013-09-20 11:00 | 2014-05-13 09:00 | 2012-09-21 09:00 | 2013-09-20 11:00 | 2014-04-21 16:00 | 2012-09-07 10:00 | 2013-01-31 12:00 | 2013-06-18 09:00 | 549431.2877 | 704922.7175 | 1152253.4917 | 803026.3234 | 1503072.3332 | 1040688.021 | 762154.061 | 722386.2883 | 0.65426 | 0.75527 | 0.44322 | 1 | -16.25 | 0.75527 | 1 | 0.65426 | 1
10/01, 2012 | 2011-12-06 17:00 | 2012-01-10 17:00 | 148898.8898 | 121894.4465 | 151905.2912 | 2011-12-09 15:00 | -27004.4433 | 81.86% | -30010.8447 | 80.24% | -22d 2h | 69.1% | 100% | 2012-08-31 14:00 | 2012-10-25 12:00 | 2013-01-30 09:00 | 2012-09-03 17:00 | 2012-10-25 12:00 | 2013-01-04 11:00 | 2012-09-17 10:00 | 2013-01-04 17:00 | 2013-04-04 12:00 | 562421.132 | 663491.5866 | 653366.6349 | 746018.6689 | 776828.1946 | 892291.4876 | 661434.0188 | 678110.4032 | 0.69097 | 0.80244 | 0.81864 | 1 | -22.25 | 0.80244 | 1 | 0.69097 | 1
14/02, 2012 | 2012-01-10 17:00 | 2012-02-14 17:00 | 179278.8886 | 145523.335 | 182285.29 | 2012-01-06 09:00 | -33755.5536 | 81.17% | -36761.955 | 79.83% | -27d 7h | 71.26% | 100% | 2012-09-05 12:00 | 2012-10-29 16:00 | 2013-02-05 16:00 | 2012-09-11 10:00 | 2012-10-29 16:00 | 2013-01-02 11:00 | 2012-09-24 16:00 | 2012-12-21 17:00 | 2013-03-12 10:00 | 569172.2424 | 666907.2258 | 658914.4358 | 725186.3298 | 779319.9997 | 862333.4314 | 665287.294 | 677540.1054 | 0.71263 | 0.79833 | 0.81171 | 1 | -27.875 | 0.79833 | 1 | 0.71263 | 1
06/03, 2012 | 2012-02-14 17:00 | 2012-03-06 17:00 | 197506.8879 | 159700.6694 | 200513.2892 | 2012-01-23 16:00 | -37806.2184 | 80.86% | -40812.6198 | 79.65% | -31d 1h | 72.21% | 100% | 2012-09-07 10:00 | 2012-10-30 17:00 | 2013-02-07 17:00 | 2012-09-14 12:00 | 2012-10-30 17:00 | 2012-12-31 11:00 | 2012-09-28 09:00 | 2012-12-17 15:00 | 2013-02-27 16:00 | 573222.9072 | 668471.4493 | 661455.1061 | 716661.3845 | 779252.002 | 848566.6299 | 667051.1443 | 677375.8613 | 0.7221 | 0.79646 | 0.80858 | 1 | -31.125 | 0.79646 | 1 | 0.7221 | 1
10/04, 2012 | 2012-03-06 17:00 | 2012-04-10 17:00 | 326421.9363 | 183329.5534 | 230893.288 | 2012-02-20 10:00 | -143092.3829 | 56.16% | -47563.7346 | 79.4% | -36d 6h | 73.18% | 100% | 2012-11-09 10:00 | 2013-04-22 17:00 | 2013-09-17 10:00 | 2012-11-07 17:00 | 2013-04-22 17:00 | 2013-07-29 15:00 | 2012-10-05 15:00 | 2012-12-11 14:00 | 2013-02-12 16:00 | 579974.022 | 670540.8895 | 852438.516 | 707941.2735 | 1013694.635 | 831708.4641 | 697873.6108 | 677544.3447 | 0.73175 | 0.794 | 0.56163 | 1 | -36.75 | 0.794 | 1 | 0.73175 | 1
01/05, 2012 | 2012-04-10 17:00 | 2012-05-01 17:00 | 358049.9362 | 197506.8879 | 249121.2873 | 2012-03-06 17:00 | -160543.0483 | 55.16% | -51614.3994 | 79.28% | -40d | 73.68% | 100% | 2012-11-20 15:00 | 2013-05-02 11:00 | 2013-10-01 11:00 | 2012-11-20 09:00 | 2013-05-02 11:00 | 2013-08-06 14:00 | 2012-10-10 17:00 | 2012-12-07 11:00 | 2013-02-04 14:00 | 584024.6868 | 671544.864 | 856250.1935 | 703633.0437 | 1014910.9581 | 822410.4271 | 698912.6471 | 677594.8446 | 0.73684 | 0.79281 | 0.55162 | 1 | -40 | 0.79281 | 1 | 0.73684 | 1
12/06, 2012 | 2012-05-01 17:00 | 2012-06-12 17:00 | 432077.207 | 342750.9774 | 391275.1357 | 2012-04-19 09:00 | -89326.2296 | 79.33% | -48524.1583 | 87.6% | -38d 7h | 78.64% | 99.47% | 2012-10-09 10:00 | 2012-11-07 11:00 | 2013-01-03 09:00 | 2012-10-08 14:00 | 2012-11-07 11:00 | 2012-11-28 11:00 | 2012-10-09 16:00 | 2012-11-09 16:00 | 2012-12-03 10:00 | 580934.4457 | 607785.0136 | 630362.6083 | 632448.8958 | 664210.8513 | 666592.5 | 611952.8369 | 612305.7991 | 0.7864 | 0.87598 | 0.79326 | 0.99469 | -38.875 | 0.87598 | 1 | 0.7864 | 1
10/07, 2012 | 2012-06-12 17:00 | 2012-07-10 17:00 | 468070.4672 | 404818.74 | 452297.2061 | 2012-05-22 12:00 | -63251.7272 | 86.49% | -47478.466 | 89.5% | -35d 4h | 82.43% | 99.42% | 2012-09-24 09:00 | 2012-10-04 14:00 | 2012-11-16 12:00 | 2012-09-24 10:00 | 2012-10-04 14:00 | 2012-10-15 16:00 | 2012-10-04 12:00 | 2012-10-23 14:00 | 2012-11-05 11:00 | 579888.7534 | 594853.1074 | 599824.5541 | 607092.9572 | 617127.0441 | 625247.9092 | 595820.41 | 597143.7385 | 0.82426 | 0.89503 | 0.86487 | 0.99417 | -35.5 | 0.89503 | 1 | 0.82426 | 1
07/08, 2012 | 2012-07-10 17:00 | 2012-08-07 17:00 | 523044.3272 | 432077.207 | 481383.2067 | 2012-06-12 17:00 | -90967.1202 | 82.61% | -49305.9998 | 89.76% | -40d | 81.98% | 100% | 2012-10-09 17:00 | 2012-10-22 17:00 | 2012-12-05 12:00 | 2012-10-09 14:00 | 2012-10-22 17:00 | 2012-10-31 09:00 | 2012-10-10 17:00 | 2012-10-25 09:00 | 2012-11-02 12:00 | 581716.2871 | 593165.6826 | 602839.8531 | 603767.5136 | 616699.7403 | 617733.2597 | 594975.2314 | 595136.5126 | 0.81982 | 0.89757 | 0.82608 | 1 | -40 | 0.89757 | 1 | 0.81982 | 1
04/09, 2012 | 2012-08-07 17:00 | 2012-09-04 17:00 | 532410.2874 | 468070.4672 | 517376.467 | 2012-07-10 17:00 | -64339.8201 | 87.92% | -49305.9998 | 90.47% | -40d | 83.47% | 100% | 2012-09-24 12:00 | 2012-09-28 11:00 | 2012-11-06 14:00 | 2012-10-16 10:00 | 2012-10-22 10:00 | 2012-10-25 15:00 | 2012-10-10 17:00 | 2012-10-18 09:00 | 2012-10-23 11:00 | 581716.2871 | 588493.7691 | 590560.2812 | 594456.8456 | 598269.3793 | 602576.4032 | 588897.6821 | 589611.4141 | 0.83471 | 0.9047 | 0.87915 | 1 | -40 | 0.9047 | 1 | 0.83471 | 1
02/10, 2012 | 2012-09-04 17:00 | 2012-10-02 17:00 | 532410.2874 | 520446.4607 | 577854.3269 | 2012-08-06 09:00 | -11963.8266 | 97.75% | -57407.8662 | 90.07% | -41d 7h | 84.02% | 99.78% | 2012-08-23 09:00 | 2012-08-23 10:00 | 2012-09-27 17:00 | 2012-10-10 16:00 | 2012-10-10 17:00 | 2012-10-11 14:00 | 2012-10-12 16:00 | 2012-10-16 11:00 | 2012-10-17 11:00 | 589818.1535 | 591137.8238 | 590093.1734 | 592094.066 | 591443.1799 | 593664.781 | 590914.8666 | 591318.6581 | 0.84017 | 0.90065 | 0.97753 | 0.99782 | -41.875 | 0.90065 | 1 | 0.84017 | 1
Actual Schedule | 2012-10-02 17:00 | 2012-10-18 17:00 | 532410.2874 | 532410.2874 | 591410.527 | 2012-08-15 17:00 | 0 | 100% | -59000.2396 | 90.02% | -46d | 83.21% | 100% | 2012-08-15 17:00 | 2012-08-15 17:00 | 2012-09-20 10:00 | 2012-10-18 17:00 | 2012-10-18 17:00 | 2012-10-18 17:00 | 2012-10-18 17:00 | 2012-10-18 17:00 | 2012-10-18 17:00 | 591410.527 | 591410.527 | 591410.527 | 591410.527 | 591410.527 | 591410.527 | 591410.527 | 591410.527 | 0.83212 | 0.90024 | 1 | 1 | -46 | 0.90024 | 1 | 0.83212 | 1